## Capital
No | MIG No: | Municipality | PROJECT NAME | Contractor | Consultants | % award Engineer | Start Date | End Date | Progress Status | Date of Practical completion | Date of Final Completion | Contractor amount (R) | Consultant fee (R) | Total Project Amount | Variation order "R Contractor | Variation order "R Consultant | Revised Amount - Contractor | Revised Amount-Consultant | Revised Project Amount | Consultant expenditure | Contractor Expenditure | TOTAL EXPENDITURE | Total Retention Held | Retention paid | Retention Outstanding | Balance of contract | Commitment 2018-19
1 | 2016MIGFK236240855 | Imbabazane | Thwathwa link Road | Ziyamasha Trading & Contractors | TL Engineering Consulting | 12% | 07/12/2017 | 07/09/2018 | Practical Completion | 06/03/2018 | 28/09/2018 | 4185988.62 | 586038.37 | 4772026.99 | 188043.64 | 22565.24 | 4374032.26 | 608603.61 | 4982635.87 | 599143.37 | 4365458.2 | 4964601.57 | 437403.226 | 380544.42 | 56858.806 | -419368.926 | 18034.3
2 | 2017MIGFK237218662 | Umtshezi | Newlands/lochsloy Pedestrian bridge | NDU Civils | TL Engineering Consulting |  | 07/12/2017 | 07/09/2018 | Practical Completion | 31/05/2019 |  | 1416418.08 | 169970.16 | 1586388.24 | 0 | 0 | 1416418.08 | 169970.16 | 1586388.24 | 248947.07 | 1228898.23 | 1477845.3 | 141641.808 | 0 | 141641.808 | -33098.868 | 108542.94
3 | 2017MIGFK237263351 | Umtshezi | Haviland Creche | Intsabula Trading Enterprise | Leja And Associates |  | 04/12/2017 | 07/04/2018 | Practical Completion | 14/09/2018 |  | 1062072 | 148690.08 | 1210762.08 | 0 |  | 1062072 | 148690.08 | 1210762.08 | 449158.54 | 1007916.4 | 1457074.94 | 106207.2 |  | 106207.2 | -352520.06 | -246312.86
4 | 2017MIGFK237263352 | Umtshezi | Thembalihle Creche | Intsabula Trading Enterprise | Leja And Associates |  | 04/12/2017 | 07/04/2018 | Practical Completion | 14/09/2018 |  | 1062072 | 148690.08 | 1210762.08 | 0 |  | 1062072 | 148690.08 | 1210762.08 | 432765.52 | 1009166.4 | 1441931.92 | 106207.2 |  | 106207.2 | -337377.04 | -231169.84
5 | 2017MIGFK237263354 | Umtshezi | Msobotsheni hall/creche | Intsabula Trading Enterprise | DlaminiNdlovu |  | 04/12/2017 | 29/06/2018 | Practical Completion | 28/06/2019 |  | 3570558 | 499878.12 | 4070436.12 | 0 |  | 3570558 | 499878.12 | 4070436.12 | 416973.03 | 2762522.09 | 3179495.12 | 357055.8 |  | 357055.8 | 533885.2 | 890941
6 | 2017MIGFK237265037 | Umtshezi | Dikwe/Slimangamehlo Pedestrian Bridge | Khindlinuka Plumbing and Civil Work | TL Engineering Consulting |  | 04/12/2017 | 07/09/2018 | Practical Completion | 17/01/2019 |  | 2012381.58 | 241485.79 | 2253867.37 | 0 |  | 2012381.58 | 241485.79 | 2253867.37 | 241478.46 | 1888467.53 | 2129945.99 | 201238.158 |  | 201238.158 | -77316.778 | 123921.38
[17 empty] | 0 |  | 0 |  |  |  | 0 |  |  |  | 0
7 | 2017MIGFK237270648 | ILM | Intshana/Moyeni Gravel Road | Sele and Musa Trading & Tours | Simphulwazi Engineers |  | 01/03/2018 | 31/05/2018 | Construction phase |  |  | 7742792.72 | 1083990.98 | 8826783.7 | 0 |  | 7742792.72 | 1083990.98 | 8826783.7 | 1082854.57 | 6961176.96 | 8044031.53 | 774279.272 |  | 774279.272 | 8472.898 | 782752.17
8 | 2017MIGFK237270764 | ILM | C-Section Black Top | Sinothando Construction cc | DlaminiNdlovu |  | 14/02/2018 | 14/09/2018 | Construction phase |  |  | 9066203.06 | 1269268.43 | 10335471.49 | 1374929.54 | 265654.86 | 10441132.6 | 1534923.29 | 11976055.89 | 1271022.06 | 9254141.98 | 10525164.04 | 1044113.26 |  | 1044113.26 | 406778.59 | 1450891.85
9 | 2017MIGFK237270765 | ILM | Ezimfeneni Community Hall & Creche Facility | Mchilobuvu Civils Construction | Mgamule Consulting Engineers |  | 11/12/2017 | 11/06/2018 | Practical Completion | 17/08/2018 |  | 2973390.75 | 329339.08 | 3302729.83 | 0 | 0 | 2973390.75 | 329339.08 | 3302729.83 | 425297.27 | 2817206.69 | 3242503.96 | 297339.075 | 135270.19 | 162068.885 | -237113.205 | 60225.87
10 | 2017MIGFK237270769 | ILM | Jennings Road Black Top | R and D Contractors | Gendu Consulting |  | 12/12/2017 | 13/07/2018 | Practical Completion | 28/06/2019 |  | 10600000 | 1004400 | 11604400 | 1903489.12 | 216146.42 | 12503489.12 | 1220546.42 | 13724035.54 | 1519176.53 | 11189585.64 | 12708762.17 | 1250348.912 |  | 1250348.912 | -235075.542 | 1015273.37
11 |  |  | High Mast Lighting in Weenen & Ezitendeni (Ward 20 & 21) | Gemini Garden Trading 400 | Baithusi Consulting |  | 14/12/2018 | 14/12/2019 | Practical Completion | 07/06/2019 |  | 2299483 | 275937.96 | 2575420.96 | 0 | 0 | 2299483 | 275937.96 | 2575420.96 | 275934.91 | 1720371.84 | 1996306.75 | 229948.3 |  | 229948.3 | 349165.91 | 579114.21
12 | 2017MIGFK237270772 | ILM | Mshayazafe black Top | Baithusi Trading 117 | DlaminiNdlovu |  | 25/01/2018 | 25/07/2018 | Practical Completion | 31/05/2019 |  | 9921503.16 | 1389010.44 | 11310513.6 | 0 |  | 9921503.16 | 1389010.44 | 11310513.6 | 1351825.51 | 9369474.23 | 10721299.74 | 992150.316 | 0 | 992150.316 | -402936.456 | 589213.86
13 | 2017MIGFK237270784 | ILM | Upgrading of Weenen Rank Market Stalls | XJR Construction | Awa Consulting |  | 12/11/2017 | 30/05/2018 | Practical Completion | 20/07/2018 |  | 2973992.67 | 416358.97 | 3390351.64 | 1072117.332 | 110245.61 | 4046110.002 | 526604.58 | 4572714.582 | 526668.95 | 3546942.47 | 4073611.42 | 404611.0002 | 0 | 404611.0002 | 94492.1618 | 499103.162
14 |  | ILM | Siphokuhle Gravel Roads and Access Roads in Ward 16 | Ziyamasha Trading & Contractors | Yintwenhle Consulting |  |  |  | Construction phase |  |  | 9932640.85 | 987137.68 | 10919778.53 | 0 | 0 | 9932640.85 | 987137.68 | 10919778.53 | 956262.1 | 1239688.5 | 2195950.6 | 993264.085 | 0 | 993264.085 | 7730563.845 | 8723827.93
15 |  | ILM | Insonge Gravel Road in Ward 11 | Skova Construction JV Mageja Construction | Gendu Consulting |  |  |  | Construction phase |  |  | 4968780.85 | 491990.28 | 5460771.13 | 0 | 0 | 4968780.85 | 491990.28 | 5460771.13 | 540672.83 | 1461420 | 2002092.83 | 496878.085 | 0 | 496878.085 | 2961800.215 | 3458678.3
16 |  | ILM | Colita Pedestrian Bridge | Silo Construction SA | Simphulwazi Engineers |  |  |  | Construction phase |  |  | 4078840.2 | 603107.22 | 4681947.42 | 0 | 0 | 4078840.2 | 603107.22 | 4681947.42 | 584939.13 | 742985.9 | 1327925.03 | 407884.02 | 0 | 407884.02 | 2946138.37 | 3354022.39
17 |  | ILM | Supply and Installation of a Park Home | Building (Pty) Ltd | In house |  | 10/07/2018 | 12/10/2018 | Completed |  | 12/10/2018 | 949800 | 0 | 949800 | 0 | 0 | 949800 | 0 | 949800 | 0 | 949800 | 949800 | 94980 | 0 | 0 | -94980 | 0
[23 empty] | 0 |  |  |  | 0
xx | [22 empty] | 0 |  |  |  | 0
18 | NA | ILM | Esigodlweni Electrification Project Phase 3 | Ezweni Electrification & Trading Services | Khanyisa Africa |  | 08/05/2015 | 24/07/2015 | Construction phase |  |  | 5498992.38 |  | 5498992.38 | 0 | 0 | 5498992.38 | 0 | 5498992.38 | 962418.78 | 0 | 962418.78 | 549899.238 | 0 | 549899.238 | 3986674.362 | 4536573.6
19 | NA | ILM | Electrical Engineer To Undertake Design And Oversee Construction Of A New Switching 11Kv Substation | Imbawula Technical Services Pty Ltd | Theshani Enterprise cc |  | 08/05/2018 | 22/11/2018 | Construction phase |  |  | 7820653.2 | 600000 | 8420653.2 | 0 | 0 | 7820653.2 | 600000 | 8420653.2 | 1955529.61 | 5444634.75 | 7400164.36 | 782065.32 | 0 | 782065.32 | 238423.52 | 1020488.84
|  |  | TOTALS | [8 empty] | 92136563.12 | 10245293.64 | 102381856.76 | 4538579.632 | 614612.13 | 96675142.752 | 10859905.77 | 107535048.522 | 13841068.24 | 66959857.81 | 80800926.05 | 9667514.2752 | 515814.61 | 9056719.6652 | 17066608.1968 | 26734122.472
Note on Y3: Nemo: incl VAT 15%
Note on Y4: Nemo: Max retention 10 % reached. No vat on contractor
Note on Y5: Nemo: Max retention 10 % reached. No vat on contractor
Note on Y6: Nemo: Max ret R284 733.49 No vat
Note on Y7: Nemo: Incl Vat 15%
Note on Y9: Nemo: incl Vat 15%
Note on Y10: Nemo: incl VAT 15% max ret = 722 982.70
Note on Y11: Nemo: Incl Vat 15%
Note on Y12: Nemo: incl Vat 15%
Note on Y14: Nemo: Max ret = R791 188.45 incl Vat 15%
Note on Y15: Nemo: Max retention R237 160.50
Note on N22: Nemo: Appointed on risk basis therefore no amount on award letter

## Operational
Type of commitment | Municipality | PROJECT NAME | Supplier | Start Date | End Date | Contract information | Progress Status | Amount per month | Total Project Amount | Variation order (R) | TOTAL EXPENDITURE 2018-19 | Commitment 2018-19
Operational | Umtshezi - ILM | Valuation Roll - Maintenance | Mills Fitchet | 2012-05-15 |  | 1 July 18 - 30 June 19 | Expired | 34500 | 414000 |  | 414000 | 0
Operational | Umtshezi - ILM | Insurance | Indwe Risk Services Pty Ltd | 2013-10-01 | 2018-09-30 | Insurance extension | Expired |  | 621677 |  | 621677 | 0
Operational | Umtshezi - ILM | Banking Service - cash collections | G4S Cash Solution | 2018-10-18 | 2019-06-18 | As per contract if not terminated, contract is renewed for a period of 1 year | Expired |  |  |  | 412958.15 | 0
Operational | ILM | Security Services | Khuselani Security & Risk Management | 2016-01-01 | 2018-12-31 | Contract have a session for the former Imbabazane Sites | Expired |  | 35060552.28 |  | 69577403.34 | 0
Operational | Umtshezi - ILM | Maintenance of IT equipment | First Technology | 2016-11-01 | 2018-10-31 | As per contract if negotiations are unsuccessful, contract will continue for a further 3 months and automatically terminate afterwards then client to return to ad-hoc client status. | Expired |  | as and when needed |  | 304836.51 | 0
Operational | Umtshezi - ILM | Maintenance of IT equipment | Duxbury | 2017-01-01 | 2017-12-31 | As per contract if not terminated, contract is renewed for a period of 1 year |  | 36097.53 | 433170.36 |  |  | 433170.36
Operational | ILM | Financial System | Munsoft - Monthly | 2016-11-01 | 2019-10-31 |  | Valid |  | 5642592 |  | 4942162.05 | 700429.95
|  |  | Munsoft - Annual | 2016-11-01 | 2019-10-31 |  | Valid |  | 1034166.6 |  | 655122 | 379044.6
Operational | ILM | AFS 2017-18 | Munsoft | 2018-04-11 | 2018-11-30 |  | Expired |  | 3105000 |  | 2947615.35 | 157384.65
Operational | ILM | Payroll System | VIP | 2017-09-01 | 2018-02-28 | Annual licence fee | Valid |  | 89061.75 |  | 89061.75 | 0
Operational | ILM | Fixed asset register | Quartex & Dynamic Dash solutions | 2018-06-30 |  |  | Expired |  | 1820181 |  | 1820181 | 0
Operational | ILM | Panel of Consultants for the Preparation of Financial Statements for a Period of 3 Years | Bonakude Consulting | 2019-02-05 |  |  | Valid |  | 1633826.51 |  | 325065.68 | 1308760.83
Operational | ILM | Panel of Financial Management Specialists for the Provision of VAT Services | Bana Consulting | 31/10/2018 | 30/06/2019 |  | Valid |  | 17.5% of the total collection |  | 11447205.7 | 0
Operational | ILM | Panel of Financial Management Specialists for the Provision of Internal Audit Services for a Period of 3 Years | Mntambo Financial Consulting |  |  |  | Valid |  | Hourly Rate |  | 3964229 | 0
Operational | ILM | Panel of Consultants for Asset Management for a Period of 3 Years | Bonakude Consulting |  |  |  | Valid |  | 2838920 |  | 667071.28 | 2171848.72
Operational | ILM | Panel of Consultants for the Supply of Electrical Material for a Period of 3 Years | Malasela Taihan Electric Cable |  |  |  | Valid |  | as and when needed |  | 0 | 0
|  |  | Arb Electrical Wholesalers Pty Ltd |  |  |  | Valid |  | as and when needed |  | 1341038 | 1856699
|  |  | Uptown Trading 475 cc |  |  |  | Valid |  | as and when needed |  | 244921.25 | 0
|  |  | Conlog Pty Ltd |  |  |  | Valid |  | as and when needed |  |  | 0
|  |  | Sisandza Technology Services |  |  |  | Valid |  | as and when needed |  |  | 0
Operational | ILM | Consultant to Manage MIG Projects | Ilungelo Lami |  |  |  | Valid |  | 1846800 |  | 104650 | 1742150
Operational | ILM | Provision of Banking Services | First National Bank |  |  |  | Valid
[9 empty] | 48220400.99 | 0 | 81785017.15 | 1670029.56