2014/15

PO Box 15, Estcourt, 3310

Civic Building, Victoria Street, Estcourt

Tel: 036 342 7800

Fax: 036 352 5829

Web: www.umtshezi.co.za

UMTSHEZI LOCAL MUNICIPALITY

DRAFT 2014/15 IDP REVIEW

UMTSHEZI VISION “BY 2016 UMTSHEZI MUNICIPALITY WILL BE THE CHAMPION OF A SUSTAINABLEGROWTH WITH AN AIM OF BUILDING BETTER COMMUNITIES.”

MISSION STATEMENT

Umtshezi Municipality in partnership with other stakeholders is committed to:

- Provide an enabling economic and social development environment;

- Provide a robust plan for the vulnerable, including youth, physically challenged, gender and aged persons;

- Work co-operatively to unlock resources from other spheres of Government and the Private Sector;

- Continuously provide services in an equitable manner taking Batho Pele Principles into cognizance;

- Establish and maintain community networks that promote healthy engagements between the Municipality and other stakeholders;

- Strive to facilitate the provision of basic services; and

- Develop Umtshezi in a sustainable manner that does not compromise current and future generations.

- Table of Contents

1	section a: EXECUTIVE SUMMARY	1

1.1	UMTSHEZI LOCAL MUNICIPALITY (KZN234)	1

1.1.1	Demographic Profile	1

1.1.2	Wards and Traditional Authority	2

1.1.3	Economic Profile	2

1.2	LONG TERM VISION	3

1.3	DEVELOPMENT OF THE IDP	3

1.4	KEY CHALLENGES FACING THE MUNICIPALITY	8

1.4.1	Municipal Transformation and Institutional Development	8

1.4.2	Service Delivery and Infrastructure	9

1.1.1	Local Economic Development	10

1.4.3	Municipal Financial Viability and Management	10

1.4.4	Good Governance and Public Participation	10

1.4.5	Spatial AND EnvironmentAL	10

1.5	MUNICIPAL STRATEGY to Unlock the Key Challenges	11

1.6	our expectations From The District (dc23), In Terms Outputs, Outcomes And Deliverables, Over The Next (5) Five Years	12

1.7	monitoring and evaluation	13

2	SECTION B: PLANNING & DEVELOPMENT PRINCIPLES & GOVERNMENT POLICIES & IMPERATIVES	14

2.1	PLANNING AND DEVELOPMENT PRINCIPLES	14

2.2	GOVERNMENT POLICIES AND IMPERATIVES	17

2.2.1	The Millennium Development Goals 2015	18

2.2.2	Provincial Growth & Development Strategy (PGDS)	18

2.2.3	The 12 National Outcomes	21

2.2.4	STATE OF THE NATION ADDRESS	21

2.2.5	State of the Province of KZN Address	21

2.2.6	OPERATION CLEAN AUDIT	21

3	Section c: situational analysis	22

3.1	Spatial, environmental and disaster analysis	22

3.1.1	Spatial Analysis	22

3.1.2	Environmental Analysis	35

3.1.4	Disaster Management	43

3.2	DEMOGRAPHIC CHARACTERISTICS	48

3.2.1	POPULATION SIZE AND STRUCTURE	48

3.2.2	AGE BREAKDOWN	50

3.2.3	Mortality Rate	51

3.3	MUNICPAL TRANSFORMATION AND INSTITUTIONAL DEVELOPMENT	52

3.3.1	Municipal Transformation and ORGANIZATIONAL DEVELOPMENT	52

3.3.2	Institutional Arrangements	53

3.3.3	Organizational Structure / ORGANOGRAM	54

3.3.4	Municipal Institutional Capacity and Status Of Critical Posts	55

3.3.5	HUMAN RESOURCE STRATEGY	55

3.4	SERVICE DELIVERY AND INFRASTRUCTURE ANALYSIS	57

3.4.1	Water and Sanitation	57

3.4.2	Solid Waste Management	58

3.4.3	Transportation Infrastructure	59

3.4.4	Energy	60

3.4.5	Access to Community Facilities	62

3.4.6	Human Settlements	63

3.4.7	Telecommunications	65

3.5	LOCAL ECONOMIC DEVELOPMENT AND SOCIAL DEVELOPMENT ANALYSIS	65

3.5.1	Local Economic Development Analysis	65

3.5.2	Social Development	72

3.6	Municipal Financial Viability and Management Analysis	79

3.6.1	Financial Viability and Management Analysis	79

3.6.2	Financial Viability & Management: SWOT Analysis	88

3.7	Good Governance & Public Participation Analysis	88

3.7.1	National and Provincial Programmes	88

3.7.2 Intergovernmental Relations (IGR) Structures Operating in Umtshezi	89

3.7.3	Municipal Structures	90

3.7.4	Audit Committee	96

Status of Municipal Policies	97

3.7.5	Municipal Bylaws	97

4	Combined SWOT Analysis	98

5	VISION, GOALS, OBJECTIVES AND STRATEGIES	100

5.1	UMTSHEZI VISION	100

5.1.1	STRATEGIC OBJECTIVES	100

6	STRATEGIC MAPPING	102

6.1	Spatial Planning Principles	102

6.2	ENVIRONMENTAL MANAGEMENT	104

6.2.1	Areas Suitable for Planning & Development	104

6.2.2	Issues Impacting on Planning and Development	106

6.2.3	Protection and Conservation of Agricultural Land	108

6.2.4	DESIRED DIRECTION OF GROWTH	110

6.3	Desired spatial form and land use	111

7	IMPLEMENTATION PLAN	113

8	FINANCIAL PLAN	116

8.1	Municipal Budget Overview	117

8.2	Three (3) Year Municipal Budget	118

8.3	OTHER MUNICIPAL PROJECTS	125

8.3.1	UMTSHEZI MUNICIPALITY MUNICIPAL CIVIL DEPARTMENT PROJECT REPORT 2013-2015	125

8.3.2	Umtshezi Municipality ELECTRICITY DEPARTMENT PROJECT REPORT – 2013 to 2015	126

-	33 Kv Circuit Breakers delivered and installed	127

Work in progress	128

Planning in progress	128

8.4	SECTOR DEPARTMENT Projects	129

9	ANNUAL OPERATIONAL PLAN (DRAFT SDBIP)	130

The SDBIP Process	132

QUARTERLY PROJECTIONS OF SERVICE DELIVERY TARGETS AND PERFORMANCE INDICATORS	138

10	ORGANIZATIONAL AND INDIVIDUAL PERFORMANCE MANAGEMENT SYSTEM	148

10.1	Objectives of the Umtshezi Municipality Performance Management System	148

10.2	Annual Performance Report of the previous Year	148

10.3	Managing and measuring performance at various levels	148

10.3.1	Strategic (Organisational) Performance linked to the integrated development plan (IDP) of a municipality	149

10.3.2	Departmental Indicators linked to outputs in the Performance Agreements	149

10.3.3	Individual Performance linked to OPMS and the individuals key performance areas and job descriptions	150

11	Annexures	150

LIST OF TABLES

Table 1: Process Plan Activity Schedule

Table 2: Municipal Transformation & Institutional Key Challenge(s)

Table 3: Service Delivery and Infrastructure Key Challenge(s)	Error! Bookmark not defined.

Table 4: Local Economic Development Key Challenge(s)

Table 5: Municipal Financial Viability Key Challenge(s)	Error! Bookmark not defined.

Table 6: Good Governance & Public Participation Key Challenge(s)	Error! Bookmark not defined.

Table 7: Spatial Environment Key Challenges	Error! Bookmark not defined.

Table 2: Planning and Development Principles

Table 3: The 12 National Outcomes	Error! Bookmark not defined.

Table 4: Government Policies and how the Municipality is applying / addressing them	Error! Bookmark not defined.

Table 5: Disaster Management SWOT Analysis

Table 6: Municipal Departments and Their Functions	Error! Bookmark not defined.

Table 8: Status of Council Adopted Municipal Policies

LIST OF FIGURES

Figure 1: Location of Umtshezi Municipality within the UThukela District	Error! Bookmark not defined.

# section a: EXECUTIVE SUMMARY

## UMTSHEZI LOCAL MUNICIPALITY (KZN234)

uMtshezi Local Municipality is located within the midlands in the South-Western quadrant of uThukela District Municipality and bordered in the north by Indaka and Emnambithi Local Municipalities, in the west by Okhahlamba and Imbabazane local municipalities, and in the south by Mpofana Local Municipality.

### Demographic Profile

Although the SDF has a clear spatial focus, it is critically important to locate it within the broader development profile of the Municipality. Essentially, this refers to a broad overview of the demographic, social economic trends, opportunities and challenges. Umtshezi Municipality population is estimated at 83154 individuals. This marks an increase from the situation in 2001.The majority of the population is African constituting 83.7% of the total population. The minority racial groups constitute 16.28% of the total. Population growth is expected to continue to grow albeit at a much slower rate compared to the last census decade. Areas such as Wembezi and Estcourt are likely to attract most of the population growth due to their strategic location.

### Wards and Traditional Authority

Umtshezi municipality is the ward participative executive type. The municipality is made out of nine wards, and it is one of the five (5) category B local municipalities comprising Uthukela District municipality. Although Umtshezi Municipality is predominantly rural in character, the majority of the population resides in urban areas and per-urban settlements. Development intensity in terms of the nuc Mamber of households is acute in the urban areas of Estcourt and Wembezi. While each of these areas has experienced limited development over the last few years, expansive peri-urban settlements have developed in the outskirts of each of these areas. Some of these have been formalized as part of the housing delivery programme of the municipality. Umtshezi Municipality is one of the Municipality which is also govern by Amakhosi. We have a representative of Amakhosi in our council. Amakhosi also form part in development structures within the municipality.

### Economic Profile

A review of the socio-economic profile as presented in the IDP indicates the following as key characteristics of Umtshezi population:

The majority of the population can be considered functionally illiterate as 70.5% of the population has a primary education and 18.8% have not been to school;

Of the 13 961 households 3 777, representing 27% of households have no income. This correlates with the high levels of unemployment that stands at 33%.

Very few individuals have an income above R3 500 to enable them to provide their own shelter. Clearly, the majority of the municipal population will depend on state support for shelter and other basic services. Statistics reveal that 27% of the households are surviving on less than R12 a day;

Approximately 10% of the total working force in the Municipality is skilled. Only 18.3% of the workforce is professional. Trade and craft constitute 10% of the workforce. Wholesale and retail trade employs 1 857 (4.9%) while electricity, gas and water supply employ 4.2% of the population. While agriculture is considered a key economic sector, Statistics reveal that the sector employs 2.4% of the economically active population; and

Using household income, employment profile and employment by sector, it is strikingly clear that Umtshezi Municipality has a relatively high rate of unemployment, is dominated by low income households and the majority of those who are employed are involved in elementary sectors. Agriculture, which is essentially a dominant land use accounts for a small number of existing jobs. It follows that the majority of the unemployed are in areas with high population concentration.

## LONG TERM VISION

“By 2016 Umtshezi Municipality will be the champion of a sustainable growth with an aim of building better communities”

## DEVELOPMENT OF THE IDP

A detailed Process Plan was prepared and developed towards the end of July 2012, which in essence served as the guide for preparing the IDP 2013-14.  The Process Plan includes the following:

Policy and Legislative requirements for preparing IDP‘s;

A programme specifying the time frames for the different steps in preparation;

Appropriate mechanisms, processes and procedures for consultation and participation of local communities, organs of state, traditional authorities, and other role players in the IDP drafting process;

An indication of the organisational arrangements for the IDP process; and

Mechanisms and procedures for vertical and horizontal alignment of the IDP

This Process Plan set out the main activities to be undertaken in the development of the IDP 2013/14 in order to meet the legislative and submission requirements before the start of the 2013/14 financial year on 01 July 2013.  The following table provides an overview of the activities undertaken during the IDP preparation:-

Table 1: Process Plan Activity Schedule

Table 2: Process Plan Activity Schedule

PHASE 1: ADOPTION AND SUBMISSION OF 2014/2015 IPD PROCESS PLAN

| Activity No | Activity | Completion Date | Output | Responsible |
| --- | --- | --- | --- | --- |
| 1 | Prepare draft 2014/15 IDP/Budget Process Plan | 31 July 2013 | Draft IDP/Budget Process Plans | ULM |
| 2 | Submit Draft Process Plan | 31 July 2013 | Submission | COGTA |
| 3 | Present final Process Plan to Council for adoption | September 2013 | Approved IDP/ Budget Process Plan | ULM/COUNCIL |
| 4 | Present SDBIP & Performance Agreements to Council | September 2013 | Approved SDBIP & Performance Agreements | ULM/COUNCIL |
| 5 | Advertise the Final Process Plan | 07 August 2013 | Advertisement | ULM |
| 6 | Closing date for comments of Final IDP Process Plan | 29 November 2013 | Public Participation | ULM/COGTA |
| 7 | Submission of final IDP Process Plan 2014/15 to COGTA | 28 March 2014 | Submission | ULM/COGTA |
| 8 | Draft Annual Report 2013/14 | 31 January 2014 | Submission | ULM/AG |
| 9 | Advertise Draft Annual Report 2014/15 | 05 February 2014 | Public Comments | ULM |

PHASE 2: PREPARE STATUS QUO

| 10 | Planning Indaba/MEC Panel Feedback | 27 September 2013 | Feedback Session | ULM/COGTA |
| --- | --- | --- | --- | --- |
| 11 | Collect Data to Review Status Quo of Municipality | 30 September 2013 | Data for Status Quo | ULM/UDM |
| 12 | Meeting at UDM | 14 November 2013 | Meeting with UDM | ULM/UDM |

PHASE 3: REVIEW STRATEGIES

| 13 | Review Municipal Strategies | January 2014 | Strategies | ULM |
| --- | --- | --- | --- | --- |
| 14 | Community Satisfaction Survey | March 2014 | Consultation | ULM |
| 15 | IDP Ward Committee Meetings | March 2014 | Consultation | ULM/WARD COM |
| 16 | Meeting with CBOs (Community Based Organisations) | March 2014 | Consultation | ULM/CBOs |
| 17 | Review Sector Plans | 21 November 2013 | Revised Sector Plans | ULM |
| 18 | Review Policies | 28 November 2013 | Revised Policies | ULM |
| 19 | IDP Task team to discuss progress | 30 November 2013 | Progress | ULM |
| 20 | Compile Projects | January 2014 | Projects | ULM |
| 21 | Oversight Committee for Annual Report 2013/14 | February 2014 | Incorporate comments in Annual Report 2013/14 | ULM,WARD COMM |

PHASE 4: ADOPTION & SUBMISSION OF DRAFT 2014/2015 IDP TO COGTA

| 22 | IDP Representative Forum | May 2014 | IDP Rep Forum | ULM |
| --- | --- | --- | --- | --- |
| 23 | Alignment of Budget & IDP | March 2014 | Aligned IDP & Budget | ULM |
| 24 | Meeting COGTA and municipalities on IDP assessment process 2014/2015 | 14 February 2014 | Meeting | ULM/COGTA |
| 25 | IDP Task team to discuss progress on draft IDP | February 2014 | Progress | ULM |
| 26 | Service Providers Forum(Sector Departments) | March 2014 | Forum | ULM,UDM,COGTA, Sector Depts. |
| 27 | Adoption of Draft IDP by Council | Sept 2014 | Adopted Draft IDP | ULM |
| 28 | Submission of Draft IDP 2014/2015 | 15 July 2014 | Submission | ULM/COGTA |
| 29 | Advertise Draft IDP for Public Comments | 1 April 2014 | Advertisement | ULM |
| 30 | Final Annual Report 2013/14 | 31 March 2014 | Submission | ULM/AG |
| 31 | Advertise Final Annual Report 2013/14 | 01 April 2014 | Public Comments | ULM |

PHASE 5: ASSESSMENT OF DRAFT 2014/2015 IDP’S

| 32 | Assessment briefing & Orientation | 31 March 2014 | Briefing | ULM,COGTA,SECTOR DEPTS |
| --- | --- | --- | --- | --- |
| 33 | Assessment Week | 1 April 2014 | Assessment | ULM,COGTA,SECTOR DEPTS |
| 34 | Present Draft IDP/Budget to the Community | April 2014 | Izimbizo | ULM |
| 35 | Feedback Session | 21 April 2014 | Sessions | ULM,COGTA,SECTOR DEPTS |

PHASE 6: ADOPTION & SUBMISSION OF 2014/15 IDP TO COGTA

| 36 | Incorporate Public Comments into IDP | May 2014 | Comments | ULM |
| --- | --- | --- | --- | --- |
| 37 | Incorporate Comments from Assessment panel from COGTA | May 2014 | Comments | ULM/COGTA |
| 38 | Address Comments from Auditor General on the Annual Report of the previous year | 09 May 2014 | Comments | ULM,AG |
| 39 | IDP Task team to discuss progress | 13 June 2014 | Progress | ULM |
| 40 | Adoption of 2014/2015 IDP/Budget by Council | 20 June 2014 | Final IDP 2013/14 | ULM |
| 41 | Advertisement of Adoption | 02 July 2014 | Advertisement | ULM |
| 42 | Submission of adopted IDP/Budget to COGTA | 10 July 2014 | Submission | ULM |
| 43 | Submit SDBIP | July 2014 | Submission | ULM |
| 44 | Submit Performance Agreements for Municipal Manager & Managers directly accountable to the Municipal Manager | July 2014 | Submission | ULM,COGTA |

## KEY CHALLENGES FACING THE MUNICIPALITY

### Municipal Transformation and Institutional Development

Umtshezi Municipality does not have major challenges since there is a collective executive system combined with a ward participatory system. The Political structure of the municipality consists of the Mayor, the Deputy Mayor and the Speaker as full-time office bearers. In total there are 17 councillors (inclusive of office bearers), which constitutes the municipal Council. Out of 17 councillors, 9 councillors are ward councillors, and the other 8 are PR councillors. After the May 2011 Local Government Elections, Umtshezi was constituted by nine wards.

The municipality has an Executive Committee that comprises of 3 members, as per the political quota representation. There are also four sub – committees in which councilors serve and deliberate on matters to be submitted to EXCO and Council thereof. The committees are as follows:

- Infrastructure, Housing and Town Planning Committee, Rural development, Agrarian;

- IDP, Finance, Local Economic Development and Tourism Committee;

- Sports, Gender and Vulnerable Groups Committee, Health, Youth, Education, local Labour;

- Human Resources, Transformation and Safety / Security Committee;

- Peace and stability; and

- Local labour forum.

The Speaker and the Municipal Manager participate in functional IGR structures of the district. Frequent Sector Department meetings are held during the IDP Process.

### Service Delivery and Infrastructure

Umtshezi Municipality has identified the following Service Delivery and Infrastructure challenges:

- Lack of funding to address the existing backlogs (Roads Infrastructure, Community Facilities, Recreational Facilities and electricity.);

- Vandalism of infrastructure (breakages and theft);

- Ageing Infrastructure e.g. Landfill site, water pipes situated underneath our Roads Infrastructure causing a serious damage to the roads during leakages and Roads Infrastructure that have reached design capacity in terms of Life Span;

- Lack of Revenue Income to fund projects due to Non-payment of services, largely by indigents or very low debt collection rate due to unemployment;

- Insufficient funding of Operation and maintenance; and

- A large percentage of the employable population is unemployed resulting in indigents. This has a serious negative impact on the revenue income of the municipality.

Intervention:

The following Plant and Equipment were procured during the 2013/14 Financial in an attempt to address the above challenges:

- 1 x TLB-Bell Equipment

- 2 x   pedestrian Rollers

- 1 x sit on Roller

- 1 x 6x4 truck tractor

- 1 x   40t low bed tri axle trailer

- 2  x   6 cube Tippers

- 1 x Excavator

- 1 x 10 cube Tippers

- 1 x  10 000liter Water Tanker

- 1 x   6x6 Grader

- 1 x 15 Ton Roller

- Twenty  4X2 vans

- ten 4x4 vans

    - Local Economic Development

The following are some of the municipal local economic development key challenges:

The municipality has not yet fully tapped into the strategic location on the N3 development corridor, this can provide more opportunities in the area;

The municipality has not yet ensured optimum utilization of natural, cultural and historical assets for further economic growth;

Vast space of Agricultural Land has not yet been fully utilised for primary and secondary production;

Economic growth in terms of transport, storage and communication sectors have not been fully explored;

There is still a need to improve recreational, medical, housing and schooling facilities;

Major specific interventions to stimulate economic growth must be developed;

Opportunity for further growth of the tourism, and manufacturing sectors

### Municipal Financial Viability and Management

The municipality does not have major challenges in terms of Municipal Viability and Management as per the plan contained in Section 3 of this document.

### Good Governance and Public Participation

The municipality does not have major challenges in terms of Good Governance and Public Participation as per the plan contained in Section 3 of this document.

### Spatial AND EnvironmentAL

The following are some of the spatial and environmental key challenges:

Spatial integration intended to address spatial fragmentation which separated the town into up-town and down-town;

Land use integration as a means to address the course grain-land use pattern;

Urban renewal programme, which may include infrastructure upgrade, redevelopment and refurbishment of buildings

CBD expansion including gateway developments at strategic points.

Strengthening spatial linkages with the neighbouring settlements such as Wembezi.

## MUNICIPAL STRATEGY to Unlock the Key Challenges

The DC23 (Uthukela District Municipality) has formulated the following Inter Governmental Forums to ensure that the challenges are addressed:

| Forum | Role |
| --- | --- |
| Finance Forum | The role of the forum is to provide a platform for the Five (5) Local Municipalities within the district to address challenges relating to Financial Management and other related matters. |
| General and Social Services Forum | The role of the forum is to provide a platform for the Five (5) Local Municipalities within the district to address challenges relating to Social Needs, e.g. Disaster Management, Sports, Gender, Youth and any other Social Services. |
| Technical and Infrastructure Forum | The role of the forum is to provide a platform for the Five (5) Local Municipalities within the district to address challenges relating to Technical and Infrastructure projects implementation. |
| Planning and Development Forum | The role of the forum is to provide a platform for the Five (5) Local Municipalities within the district to address challenges relating to Planning and Development challenges and to share expertise since this is a scars skill. |
| Corporate Services Forum | The role of the forum is to provide a platform for the Five (5) Local Municipalities within the district to address challenges relating to Legal, Administration and Corporate matters. |
| Municipal Manager’s Forum | The role of the forum is to provide a platform for the Municipal Managers of the Five (5) Local Municipalities within the district to address challenges and share experiences. |
| Speaker’s Forum | The role of the forum is to provide a platform for the Speakers of the Five (5) Local Municipalities within the district to address challenges and share experiences. |
| Mayor’s Forum | The role of the forum is to provide a platform for the Mayors of the Five (5) Local Municipalities within the district to address challenges and share experiences. |

Our municipality fully participate in these IGR Forums.

## our expectations From The District (dc23), In Terms Outputs, Outcomes And Deliverables, Over The Next (5) Five Years

The Municipality has pledged to the local community that it would endeavour to respond to their service delivery and infrastructure needs as far as possible bearing in mind the Municipality‘s limited financial and other resources.  In collaboration with the public, the following capital projects have been prioritized over the next financial year and aligned to a 3-5 year Capital Investment Plan.

| WARD NO | PROJECT 1 | PROJECT 2 | PROJECT 3 | PROJECT 4 | PROJECT 5 | PROJECT 6 | RESPONSIBILITY PERSON / SECTOR DPT. |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Upgrade of Wagendrift Dam water pump station |  |  |  |  |  | Uthukela District Municipality |
| 2 | Wembezi D Water and Sanitation | Upgrading of the Bulk Infrastructure for the Wembezi C Phase 3 Housing Development | Sewer reticulation for Wembezi C Phase One and Wembezi B. |  |  |  | Uthukela District Municipality |
| 3 | Sanitation Project confirmed by UDM | Mimosadale Phase Two Water and Sanitation | Brynmbella Water and Sanitation | Kwamatshesi Water and Sanitation | Engavuza Water and Sanitation | Intunda and Lowlands Water and Sanitation | Uthukela District Municipality |
| 4 | Sanitation Project – Thembalihle/ confirmed by UDM | Emthweni Water and Sanitation | Haviland Water and Sanitation | Haviland Electricity - ESKOM | Esigodlweni Water and Sanitation | Esigodlweni Electricity - ESKOM | Uthukela District Municipality |
| 5 | Sanitation Project - Weenen confirmed by UDM | Ezitendeni Sanitation | Engodini, Vumbu and Gomba Water and Sanitation | Nhlawe and Madondo Water and Sanitation | Nontethe Water and Sanitation | Nkaseni and Nomoya Water and Sanitation | Uthukela District Municipality |
| 8 | Chievely, Frere and Rama Water and Sanitation | Cornfield Water and Sanitation |  |  |  |  | Uthukela District Municipality |
| 7 | Sanitation Project confirmed by UDM | Ephofini Water and Sanitation | Mbabane Water and Sanitation | Mgwamama, Ezibindini and Mankonka Water and Sanitation | Madulaneni Water and Sanitation | Mhlumba and Kwanhliwe Water and Sanitation | Uthukela District Municipality |

## monitoring and evaluation

The Umtshezi Municipality has a Performance Management System (PMS) in place. Each of the Departmental Heads to signs a Performance Contract which is linked to the objectives of the IDP and meeting the service delivery needs of the community.  Our Organisational Scorecard is aligned to the functions and responsibilities of each Department.

We have been nominated as one of the few municipalities to pilot the PMS System and initiative is funded by the KZN COGTA. We are doing very well, targets are being met and we see tangible improvement.

# SECTION B: PLANNING & DEVELOPMENT PRINCIPLES & GOVERNMENT POLICIES & IMPERATIVES

## PLANNING AND DEVELOPMENT PRINCIPLES

In developing our IDP, the follwing Key Planning and Development principles were taken into consideration:

Table 3: Planning and Development Principles

|  | PLANNING AND DEVELOPMENT PRINCPLES | APPLICATION OF PRINCIPLES |
| --- | --- | --- |
| NSDP SLUMB | Development / investment must only happen in locations that are sustainable. | The principle is being implemented accordingly. |
| DFA | Balance between urban and rural land development in support of each other | The principle is being implemented accordingly. |
| DFA | Discouragement of urban sprawl by encouraging settlement at existing and proposed nodes and settlement corridors, whilst promoting densification. Future settlement and economic development opportunities should be channelled into activity corridors and nodes that are adjacent to or that link the main growth centres | The principle is being implemented accordingly. |
| DFA | The direction of new development towards logical infill areas | The principle is being implemented accordingly. |
| DFA | Compact urban form is desirable | The principle is being implemented accordingly. |
| DFA CRDP NSSD | Development should be within limited resources (financial, institutional and physical). Development must optimise the use of existing resources and infrastructure in a sustainable manner. | The SDF identifies areas with potential for development. |
| NSDP | Basic services (water, sanitation, access and energy) must be provided to all households | The SDF investigates issues of water resources in the municipality. |
| NSDP | Development / investment should be focused on localities of economic growth and/or economic potential | The LED Strategy as developed in partnership with the district covers the matter at hand. |
| NSDP | In localities with low demonstrated economic potential, development / investment must concentrate primarily on human capital development by providing education and training, social transfers such as grants and poverty-relief programmes | The LED Strategy as developed in partnership with the district covers the matter at hand. |
| CRDP | Land development procedures must include provisions that accommodate access to secure tenure | The municipality is currently disposing land suitable for development by way of secure tenure. |
|  | Prime and unique agricultural land, the environment and other protected lands must be protected and land must be safely utilised | The protected areas are identified accordingly in the Town Planning Scheme. |
|  | Engagement with stakeholder representatives on policy, planning and implementation at national, sectoral and local levels is central to achieving coherent and effective planning and development. | The municipality ensures engagement with all stakeholders to ensure that all Planning Legislation and Policies are implemented accordingly. |
| Housing Policy-Breaking New Ground | If there is a need to low-income housing, it must be provided in close proximity to areas of opportunity | The municipality has adopted an Integrated Human Settlements Plan that is in line with the provisions of the IDP. |
| National Strategy on Sustainable Development) | During planning processes and subsequent development, the reduction of resource use, as well as the carbon intensity of the economy, must be promoted | The municipality subscribes to the call of Sustainable Development and ensures Integrated Human Settlements where all Human Settlements projects are implemented. |
| KZN PGDS National Strategy on Sustainable Development | Environmentally responsible behaviour must be promoted through incentives and | The municipality subscribes to the Seven (7) Strategic Goals of the Provincial Growth Development Strategy. |
| KZN PGDS | The principle of self-sufficiency must be promoted. Development must be located in a way that reduces the need to travel, especially by car and enables people as far as possible to meet their need locally. Furthermore, the principle is underpinned by an assessment of each areas unique competencies towards its own self-reliance and need to consider the environment, human skills, infrastructure and capital available to a specific area and how it could contribute to increase its self-sufficiency | The municipality subscribes to the Seven (7) Strategic Goals of the Provincial Growth Development Strategy. |
| KZN PGDS | Planning and subsequent development must strive to provide the highest level of accessibility to resources, services and opportunities | The municipality subscribes to the Seven (7) Strategic Goals of the Provincial Growth Development Strategy. |

## GOVERNMENT POLICIES AND IMPERATIVES

The National Development Plan (NDP) introduces the long-term vision for the future development of South Africa. As such, the National Planning Commission (NPC) has formulated a National Development Plan (NDP) - ‘vision 2030’ as a strategic plan to guide development at a national level over the short to medium term. The plan is based on a detailed diagnosis of issues facing the country and strategic engagement with all key sectors. It identifies unemployment, poverty and inequality as some of the key challenges facing South Africa, and outlines a number of strategic interventions to address these issues. Among these are the following:

Economic development and job creation.

Improving infrastructure.

Transitioning to a low carbon economy.

Building an inclusive and integrated rural economy.

Reversing the spatial effects of apartheid.

Improving education, innovation and training.

Quality health care for all.

Social protection

Reforming the public service

Fighting corruption

Transforming society and uniting the country

Positioning South Africa to seize opportunities of globalisation.

The 5 National priorities include Job creation (Decent work and Economic growth); Education; Health; Rural development, food security and land reform; Fighting crime and corruption; Nation-Building and Good Governance. We fully subscribe to the provissions of the NDP and our policies are aligned to the NDP to contribute to the National Targets.

### The Millennium Development Goals 2015

The Millennium Development Goals summarize the development goals agreed on at international conferences and world summits during the 1990s. At the end of the decade, world leaders distilled the key goals and targets in the Millennium Declaration (September 2000). The Millennium Development Goals, to be achieved between 1990 and 2015, are:

Halving extreme poverty and hunger;

Achieving universal primary education;

Promoting gender equality;

Reducing under-five mortality by two-thirds;

Reducing maternal mortality by three-quarters;

Reversing the spread of HIV/AIDS, malaria and TB;

Ensuring environmental sustainability; and

Developing a global partnership for development, with targets for aid, trade and debt relief.

In addressing the above millennium goals, the municipality has initiated poverty eradication programmes that are part of the plan for the financial year. These programmes include assisting the local community to plant vegetables for sustenance of the families. The municipality is in the process of reviewing its Local Economic Development Plan. The review of the LED will provide the current and a true reflection of the economy thereby assist in the identification of economic opportunities within Umtshezi that can unlocked to create economic growth and  job opportunities. We are fully aligned indeed.

### Provincial Growth & Development Strategy (PGDS)

The Provincial Growth and Development Strategy (PGDS) is a vehicle to address the legacies of the apartheid space economy, to promote sustainable development and to ensure poverty eradication and employment creation.

The PGDS offers a tool through which national government can direct and articulate its strategy and similarly for local government to reflect the necessary human, financial and fiscal support it needs to achieve these outcomes. It facilitates proper coordination between different spheres of government and aims to prevent provincial departments from acting out of concert with local municipalities. It enables intergovernmental alignment and guides activities of various role players and agencies (provincial sector departments, parastatals, district and municipalities). The PGDS will enhance service delivery.

It is a framework for public and private sector investment, indicating areas of opportunities and development priorities. It addresses key issues of implementation blockages whilst providing strategic direction.

Umtshezi Municipality is in full support of the KZN, PGDS and has ensured alignment of the Goals and Objectives with the KZN234 IDP in terms of the following:

Job Creation:

The municipality has ensured alignment by implementing the following programmes:

Recruitment of more than 150 participants under the Extended Public Works Programme as funded by the National Department of Public Works and further ensures that Infrastructure Projects are Labour Intensive;

The recruitment of more than 1200 participants for the implementation of the Community Works Programme as funded by the Department of Corporative Governance and Traditional Affairs;

The municipality has recruited more than 100 participants for the implementation of the Keep Umtshezi Clean Programme which aims at providing Job Opportunities to locals and at the same time provide assistance to the municipality with Service Delivery; and

The municipality is currently working hand in hand with the KZN Department of Economic Development for the Training of SMMEs and has also allocated a Budget to attend to the needs of the SMMEs;

Human Resource Development: The municipality is currently implementing the following programmes to assist the Local Youth with Skills Development:

Skills Development Programme of 100 Local Youth in partnership with the National Youth Development Agency;

Skills Development Programme of 50 Local Youth in partnership with the Office of the KZN Premier;

Annual Financial Assistance to 100 successful Grade 12 students with Registration Fees in Tertiary Institutions; and

The municipality ensures the distribution of Skills Development Information from other departments to all wards via the Youth Centre.

Human and Community Development:

The municipality is currently implementing Human Settlements Projects in the following areas to ensure Sustainable Human Settlement:

Cornfield, Paapkuilsfontein, Frere, 	Msobotsheni, Owl and Elephant, Wembezi, Thembalihle, Mimosadale and Rensbergdrift.

The municipality is also supporting the elderly, development of Women, People living with disability and matters pertaining to gender programmes.

Strategic Infrastructure:

The municipality has developed and submitted a Business Plan for the development of Dry Port / Industrial Area to the KZN COGTA for approval and is currently awaiting outcome. The development seeks to be a central point for delivery of goods between Durban and Johannesburg due to the strategic location of the town of Estcourt and the site.

Responses to climate change:

Umtshezi Municipality hosted a huge event / community outreach programme in year 2012 in the town of Weenen in partnership with the relevant Sector Departments. The event was aimed at equipping the community at large with the following:

Increased productive use of land;

Alternative energy generation and usage; and

Disaster Management.

Governance and Policy:

The municipality has a Prevention of Fraud and Corruption Policy adopted by council; and

The municipality has developed and adopted Government Policies to ensure compliance.

Spatial Equity: The municipality subscribes to the following pieces of legislation:

Spatial Planning and Land Use Management Act No 16 of 2013; and

Planning and Development Act No 6 of 2008.

### The 12 National Outcomes

Government introduced the outcome based approached and adopted twelve outcome areas. The objective is to improve service delivery across all spheres of government and to introduce a systematic planning, monitoring and evaluation process. Outcome nine specifically relates to local government and calls for ‘Responsive, accountable, effective and efficient local government system’. Umtshezi has to respond to the outputs set out in Outcome 9 and deal with issues facing the municipal area and providing efficient and effective services to its communities. The municipality is committed to implemented the respective outputs through focussing on improved service delivery, economic, environmental and social development.The seven outputs of outcome 9, are indicated below:

Output 1: Implement a differentiated approach to municipal financing, planning and support.

Output 2: Improving access to basic services.

Output 3: Implementation of the Community Work Programme.

Output 4: Actions supportive of the human settlement outcome.

Output 5: Deepen democracy through a refined Ward Committee Model.

Output 6: Administrative and financial capability.

Output 7: Single window of coordination.

### STATE OF THE NATION ADDRESS

Umtshezi Municipality acordingly subscribes to the content of the State of the Nation Address as delivered by the President of the Republic of South Africa, His Excellency: President Jacob G. Zuma.

### State of the Province of KZN Address

Umtshezi Municipality acordingly subscribes to the content of the State of the Province Address as delivered by the Premier of the Kwa Zulu Natal, Honorable: Senzo Mchunu.

### OPERATION CLEAN AUDIT

In the 2010/2011 and 2011/2012 financial year we have received two clean audit opinions. In order for us to obtain these two clean audit opinions, Strigent controls were put in place.

In the 2012/2013 financial year, however we have regressed to a qualified opinion. We are addressing the basis of receiving the qualified audit opinion i.e. accruals; commitments; irregular expenditure and all other queries raised by the Auditor General.

# Section c: situational analysis

## Spatial, environmental and disaster analysis

### Spatial Analysis

#### 3.1.1.1 Regional Context

Umtshezi Municipality is located approximately 165km northwest of Durban and 400km southeast of Johannesburg.  The National Road N3 also traverses the Municipality on its western portion linking these two major cities i.e. Durban and Johannesburg within Uthukela District Municipality (DC23).  Estcourt Town is the main urban center for the Municipality.  Umtshezi Municipality is bordered on its southeastern portion by the Mooi Mpofana Municipality, Msinga Municipality on its eastern portion, Indaka Municipality on its northeastern portion, both by Emnambithi/Ladysmith and Okhahlamba Municipalities on its northwestern portion and Imbabazane Municipality on its southwestern portion. (See the map of Umtshezi below)

Figure 1: Locality

#### 3.1.1.2 Administrative Entities

The Umtshezi municipality consists of nine (9) wards and includes two Traditional Authority Areas, namely the Nkwanyana and the Machunwini areas.

Figure 2: Administrative entities

#### 3.1.1.3 Structuring Elements

N3 national route, which links Durban and Johannesburg. It is approximately 80km from Pietermaritzburg and about 40km from Ladysmith. As such, it is highly accessible both local and regional level

P12 from Weenen and beyond and the P29 from Wembezi and beyond (major tourist route to Giants Castle and the Ukhahlamba Drakensberg Park World Heritage Site that passes through Imbabazane Local Municipality to Estcourt and a secondary tourism corridor in the district SDF).

Wagendrift dam

#### 3.1.1.4 Existing Nodes and Corridors (Including Urban Edges)

#### Nodes

The Primary Node is Estcourt since it is the main commercial, industrial and administrative centre within Umtshezi Municipality. It forms of part of the district spatial systems and is identified in the district SDF as a secondary node. This is despite Estcourt being recognised as a third order centre at a provincial level alongside Ladysmith. As a sub-regional node, the following activities should be strengthened in Estcourt;

Secondary Activity Nodes/Urban Community Centres: Weenen, and Wembezi Town Centre; and

Tertiary Nodes/Rural Community Centre: Thembalihle and Cornfields, Frere, Chively, Rensbergdrift, Nhlawe.

#### CORRIDORS

The N3 National Corridor;

Primary Development Corridors: Main access and mobility routes have been identified as primary development (regional) corridors, namely the Giant Castle to Weenen Nature Reserve Corridor (north–south axis); Regional road from Colenso in the west through Weenen to Greytown and beyond (east-west axis); and R103 which runs parallel to and north of the N3. For the purposes of the SDF, R103 is seen as part of the broader N3 corridor.

Secondary Corridors: (Road from Winterton to Colenso running along the western boundary of Umtshezi Municipality and P170-D385 corridor from Wagendrift dam through Estcourt town to Weenen running along the eastern boundary of the municipal area.

Tertiary Corridors:  Tertiary corridors are also known as local corridors because they serve mainly a local function including the following: (D489 – D721 (Cornfields-Thembalihle Corridor), P179 from Loskop road through Wembezi to Wagendrift Dam and the surrounding proposed conservation areas and the Wembezi-Estcourt Mixed Land Use Corridor.

##### Sub-regional Activity Node - Estcourt

Estcourt is the main commercial, industrial and administrative centre within Umtshezi Municipality. It forms of part of the district spatial systems and is identified in the district SDF as a secondary node. This is despite Estcourt being recognised as a third order centre at a provincial level alongside Ladysmith. As a sub-regional node, the following activities should be strengthened in Estcourt:

Development of commercial activities serving the whole municipal area and the surrounding areas (sub-region).

Location of district and sub-district offices of various government departments and serve delivery agencies.

Location of facilities and services for an effective administration and local governance of Umtshezi Municipality.

Industrial development, focusing mainly on the processing of raw materials produced within the sub-region and the neighbouring areas – agri-processing centre.

Location of public facilities serving the whole sub-region and beyond. These may include sports and transportation facilities.

##### Secondary Activity Nodes/Urban Community Centres

Two secondary activity nodes have been identified in Umtshezi Municipality, namely:

Weenen, and

Wembezi Town Centre.

Weenen which was previously a thriving rural town has experienced decline in both character and function. It is characterised by derelict and poorly maintained buildings, deteriorating quality of infrastructure and the associated services, and lack of investment. With the majority of the land around this town being subject to land restitution and labour tenant claims, it is critically important to repackage Weenen as a centre of activity and an anchor point for the integration and coordination of support services to the various land reform projects. It has potential for the activities:

Administrative offices for the decentralisation of services to the communities located around Weenen.

Limited commercial activities targeting the surrounding communities.

Processing of raw materials produced in the area given its potential for intensive crop and citrus production.

Wembezi on the other hand was developed as a residential township or a dormitory suburb for black people working in Estcourt. A small area was set aside for the development of a town centre. Today, this area is poorly developed with a community hall and two small local convenient shops. However, a small agglomeration of commercial facilities has occurred at the northern entrance to the township. Plans to develop a neighbourhood shopping centre in the area have reached and advanced stage with implementation due to start at the beginning of 2009. The area is also being considered for a range of projects that would be funded through the Neighbourhood Development Partnership Grant (NDPG).

In addition, middle income housing is being developed to the west of the Wembezi Township. In fact, there is potential to expand this to cover the vacant land located to the west of B-section and may yield about 500 units. Other issues that require attention in the area include:

Upgrading of informal settlements.

Upgrading of the existing cemetery.

Upgrading and maintenance of roads.

##### Tertiary Nodes/Rural Community Centre

The vision for the future spatial development of Umtshezi Municipality makes provision for the development of community centres within a cluster of settlements, as follows:

Thembalihle and Cornfields

Frere

Cheverly

Rensbergdrift

Nhlawe

None of these is currently developed. The primary aim of these centres is to accommodate land uses that provide services to the local communities. These include the following:

Educational facilities such as schools.

Community centres including a community hall

Health facilities such as a clinic or mobile clinic

Sports facilities

Limited commercial facilities

Pension pay point.

##### URBAN EDGE

With the pressure of population growth in cities and towns, especially in the still developing countries, an increase in human activity and human needs causes a build-up of development intensification and human needs. Urban containment and urban sprawl is thus global occurrences with local manifestations. Containment strives to prohibit commercial or residential over-development in and around large cities and towns so that the natural environment can be sustainable and continue whilst being protected. As with most human action certain social, political and governance issues also accompanies these processes.

The urban edge demarcation policy system is a South African approach to limit urban development from expanding to rapidly to the outskirts of an urban region. Hence, this system provides containment in the form of restriction. The urban fringe, or more plainly the zone were the urban ends and the rural starts, is a determinant for compiling the edge. However, the reality of modern urbanism and development is that large towns eventually formed metro poles, suburbs and neighborhoods (Daniels: 1999). This made the fringe vast and determination thereof difficult to place.

The pressure of residential development like golf course low-density development is at this moment extremely high. Farm and vacant land contributes to the very character of Paarl and the availability of these sites, either small or large, remains a problem especially when only so many restrictions can prohibit development from escalating to rapidly. Damage to the environment is the ultimate consequence if urban sprawl is to continue so fast for this region.

Most of the current farms and vacant urban land is zoned as agricultural, commercial, residential or undetermined and changing these sites can become difficult under the Heritage Resources Act of 2005. To comprehend the justification of policy adaptation in order to extend the Paarl urban edge is an immense predicament and is something that may never be fully understood or even proven. The fact remains that this is the case for many abutting local governments, not only in South Africa, but across the world.

For the purposes of Development Control, Umtshezi Municipality is currently implementing the Planning pieces of Legislation below and ensured inclusion of Urban Sprawl Prevention in the following Policy Documents:

| Legislation / Policy Document | Comments |
| --- | --- |
| KZN Planning and Development Act No 6 of 2008. | Currently being implemented. |
| Spatial Planning and Land Use Management Act No 16 of 2013 | The Act was Gazetted on the 5 August 2013 but practical effectiveness of the Act will depend on the advice of KZN COGTA. |
| Estcourt / Wembezi Town Planning Scheme | The municipality is currently utilising the scheme to ensure development control in the areas of Wembezi and Estcourt. |
| Spatial Development Framework | The municipality is currently utilising the SDF to ensure proper planning of development. |

#### 3.1.1.5 CORRIDORS

##### The N3 National Corridor

The N3 is identified in the NSDP as a national corridor, and is recognised as such (existing corridor) in the PSEDS. It runs in an east-west direction almost dividing Umtshezi Municipality in two halves. The southern portion is dominated by high potential agricultural land and portions of conservation worthy areas, while areas to the north could be described as moderate to low in production potential and generally suitable for livestock and game farming. It is a high speed limited access road providing access and inter-nodal connections at a national and provincial level. It carries traffic between Johannesburg and Durban.

At a local regional and local level, it presents an opportunity for the integration of Estcourt Town to the national and provincial trade routes.  It is a tourist route to the major tourist destinations in KwaZulu-Natal (KZN), particularly the Drakensburg and the Battle-fields Route.

Development along this route should occur as follows:

Facilitate the establishment of mixed land use activity nodes at the intersection of the N3 and the regional or provincial routes. Activities that may locate in these areas include logistics, warehousing, light industry and commercial facilities.

In the short to medium term, high value agricultural land located along the corridor should be protected, but in the long term, strategically located areas abutting onto the mixed land use nodes should be opened for development as mixed land use precincts.

Compliance with the policies and regulations introduced by the South African National Roads Agency (SANRAL).

Development of Wembezi Interchange as a mean facilitate access to the “Berg”.

##### Primary Development Corridors

Two main access and mobility routes have been identified as primary development (regional) corridors, namely:

Giant Castle to Weenen Nature Reserve Corridor (north–south axis);

Regional road from Colenso in the west through Weenen to Greytown and beyond (east-west axis); and

R103 which runs parallel to and north of the N3. For the purposes of the SDF, R103 is seen as part of the broader N3 corridor.

The former has potential to develop into a tourism route linking the Drakensberg with the proposed Big Five Game Reserve centred on Weenen Nature Reserve. There are also opportunities for intensive agricultural activities or leisure type of developments linked to the game reserve along the river hence the river is identified as a green corridor. It is also a major link between Estcourt and Weenen. As such, it carries local traffic between the two centres and creates a link between a largely agricultural centre in Weenen and an agri-processing centre in Estcourt.

The eastern axis on the other hand serves as a major link to the areas beyond Umtshezi Municipality, and is an alternative tourist route to the north-coast from areas such as Gauteng and the Free State. It runs through the proposed Big Five Game Reserve and has potential for the development of a range of tourism facilities including private game farms (mainly for hunting and/or conservation purposes). In the medium to long term, a need may arise for some land to be released for settlement purposes to accommodate land restitution claimants, labour tenant and farm dwellers using a cluster approach.

Development along these corridors should conform to the following guidelines:

Both corridors are located on provincial roads and thus should adhere to the regulations as implemented by the Department of Transport.

Development of viewing and picnic sites in appropriate areas.

Development of a tourism node at the intersection of the two corridors.

Limit the number and location of settlements located along this route to carefully selected areas.

##### Secondary Corridors

A number of existing roads have potential to develop as secondary or sub-regional development corridors, but there are opportunities to unlock new development areas through the use of a network of secondary corridors. The key existing secondary corridors include the following:

Road from Winterton to Colenso running along the western boundary of Umtshezi Municipality. This corridor links Winterton with Colenso and beyond. It runs mainly along agricultural land. As such, development along this corridor should focus on intensive and extensive agriculture including livestock farming. Settlement should be limited to the consolidation of the existing Chieverlery, its expansion to accommodate land reform beneficiaries and provision of the necessary public facilities so as to establish the area as a sustainable human settlement.

P170-D385 corridor from Wagendrift dam through Estcourt town to Weenen running along the eastern boundary of the municipal area.

The road from Winterton to Colenso serves as a major link at a district level knitting together small towns from Bergville through Winterton to Ladysmith, Weenen and beyond. It runs mainly along agricultural land. As such, development along this corridor should focus on intensive and extensive agriculture including livestock farming. Settlement should be limited to the consolidation of the existing Chieverlery, its expansion to accommodate land reform beneficiaries using a cluster approach and provision of the necessary public facilities so as to establish the area as a sustainable human settlement.

P170-D385 corridor is a proposed corridor linking the eco-tourism and leisure node of Wagendrift Dam through Estcourt town with the proposed Big Five Game Reserve but running along the eastern boundary of the municipal area. It is essentially a tourism corridor, but its future development should provide for a strategic mix of agricultural and eco-tourism activities. From Weenen, this corridor runs northwards into Indaka Municipality where it links with the proposed Cannibal Route.

##### Tertiary Corridors

Tertiary corridors are also known as local corridors because they serve mainly a local function including the following:

D489 – D721 (Cornfields-Thembalihle Corridor).

P179 from Loskop road through Wembezi to Wagendrift Dam and the surrounding proposed conservation areas.

Cornfields-Thembalihle Corridor serves as a major link between the two parallel secondary corridors and has potential to improve access to Thembalihle and Cornfields which area both isolated expansive rural settlements located on commercial farmlands. It has potential to link with Chieverley as well. To all intents and purposes, this corridor has limited economic opportunities.

P179 from Loskop road through Wembezi to Wagendrift Dam and the surrounding proposed conservation areas is also an emerging corridor intended to reinforce linkages and integrate Wembezi and the surrounding settlements to the agricultural and the proposed eco-tourism areas in the vicinity of the Wagendrift Dam. It has potential to serve as an alternative access to the Wagendrift eco-tourism node from the Loskop road.  It has potential to serve as an alternative access to the Wagendrift eco-tourism node from the Loskop road. It also provides access to settlements such as Wembezi and C- section.

##### Wembezi-Estcourt Mixed Land Use Corridor

Spatial integration between Wembezi and Estcourt is one of the main spatial development challenges facing Umtshezi Municipality. It is thus recommended that the portion of the main road between the two areas be developed as a low impact mixed land use corridor in the short to medium term. This will ensure protection of the existing agricultural land while also opening opportunities for tourism, leisure, housing and commercial development. The proposed N3 off-ramp gives further impetus to the development of a mixed land use node which accords well with the proposed corridor.

#### 3.1.1.6 LAND COVER AND BROADER LAND USES

Current land use pattern has evolved in response to the settlement pattern, the natural environment and regional access routes.

Figure 3: Land cover

The following broad land use categories are found in Umtshezi Municipality:

Urban nodes are Estcourt, Wembezi and Weenen. Each of these plays a different role in the space economy. While Estcourt is the major commercial node, Wembezi is essentially a dormitory suburb. Weenen is a declining rural town.

A sizeable portion of the municipal area comprises commercial agricultural areas.  There are extensive and intensive farming activities throughout this area. They include crop production (primarily in irrigated areas), game farming, limited forestry and livestock farming.

While there are no proclaimed Traditional Authority Areas within Umtshezi, there are several areas of dense rural settlement.  They include settlements such as Frere, Cheverly, Cornfields and Thembalihle.  The latter is settled by members of Mabaso traditional council.

Conservation areas include nature reserves (namely the Weenen, Wagendrift and Moor Park Nature Reserves), game farms and heritage sites.

A number of farms which were previously used for livestock farming have now been converted into game farms and are developed with tourism infrastructure.

#### 3.1.1.7 Land Ownership

Land ownership in the municipal area can be categorized as follows:

There are numerous parcels of state land located throughout the municipal area.  They include the land parcels upon which various facilities have been constructed, for example, government and municipal offices, police stations, schools, clinics and utilities (such as water works and sewerage treatment works).  Small portions of agricultural stateland are found near Ennersdale.

The predominant form of land ownership in the municipal area is privately-owned land. However, this is likely to change as more land is increasing registered in the name of groups as a result of the land reform program. Huge tracks of land will fall under communal land as defined in the Communal land Rights Act (CLaRA).

Major servitudes relating, inter alia, to uThukela Water’s bulk water supply pipelines and Eskom powerlines.

#### 3.1.1.8 Land Claims / Reform

The following table summarizes the current extent of the land reform programmes in Umtshezi.

Table 4l Land reform projects

| Programme | Extent |
| --- | --- |
| Restitution | 72 claims |
| Redistribution | 23 projects |
| Land Redistribution for Agricultural Development (LRAD) | 3 projects |
| Labour Tenant | 14 projects |

The LED aspects of the land reform projects are generally poorly developed. The Framework for Land Reform in KwaZulu Natal (2005) notes that: “Very few land reform projects, except those initiated by the private sector or in partnership with the private sector, facilitate the integration of beneficiary groups into commercial agricultural markets or provide opportunities for rural households to generate small amounts of income from their agricultural produce or natural resource products” (71). Land reform projects require not only the same kinds of support that other emerging farmers do; but additional support in the enterprise transformation process and resettlement process. This is termed ‘post- transfer support’ and requires enterprise, livelihood, infrastructure and social support interventions.

#### 3.1.1.9 Land Capability

The agricultural potential of Umtshezi varies with the different rainfall, soil, climate and topographical condition in the area. The five distinct Bioresource identified by the Department of Agriculture and Environmental Affairs have a major impact on agricultural practices and potential. The area of Umtshezi is of marginal value for crops, unless irrigated. The good water resources in the area create a high potential for irrigation.

Agricultural potential within Umtshezi Municipality falls into six of the eight potential ratings namely: good, relatively good, moderate, restricted, low, poor, and very poor agricultural potential areas. These are described as follows:

Good agricultural potential areas: Areas of agricultural potential within Umtshezi Municipality which are classified as good are limited of the six agricultural potential zones. These areas occur at the southern part of municipality. Good agricultural land occupies an estimated 2% of the municipality.

Relatively good agricultural potential areas: Land of relatively good agricultural potential is quite extensive in municipality. Areas of relatively good agricultural potential occur along the western boundary of the municipality and also at the northern tip of the municipality. Relatively good agricultural land occupies an estimated 16% of the municipality.

Moderately good agricultural potential: Land that is of moderate agricultural potential is located in the central parts of the municipality between the areas encompassed by southwest of Estcourt, east of Frere, northeast of Colenso and west of Weenen. A very small area of this land type also occurs along the western boundary of the municipality. Moderately good agricultural land occupies an estimated 25% of the municipality. Jane

Low and poor agricultural potential: The rest of the area which covers an estimated 56% of the municipality is covered by land considered to be low to poor agricultural potential land. These areas occur mainly at the western half of the municipality.

Agricultural Potential for Planning Purposes: The quantity and distribution of water resources in Umtshezi Municipality is very good although rainfall is erratic and soils are poor. It is estimated that close to 60% of land in the municipality has limited agricultural productivity. Thus in terms of economic land use, agriculture is not a suitable development option for economic development in the Municipality. Since majority of the people in this municipality depend on crop cultivation an area of focus for the municipality is to strengthen subsistence farming at the household level.

The best areas for irrigation are in the valleys of the Bushmans and Little Bushmans Rivers and the area of the Wagendrift Dam. Agricultural potential is greatest in the eastern sections along the Little Tugela River, declining to the west. Commercial farming is taking place in the eastern sections and non-commercial farming occurs in the vicinity of Weenen. The irrigated small holdings located almost around Weenen town accounts for the relatively good potential land in this area. High potential agricultural land is located to the south west of the area along Bushmans River.

Figure 4: Agriculture potential

#### 3.1.1.10 Private Sector Development

As Umtshezi Municipality, we are trying very hard to unlock in terms of shopping malls and at present, we are developing the Municipality with two Taxi Ranks i.e. in Wembezi and Estcourt town, expansion of Nestle industry.

### Environmental Analysis

The natural environmental resources and endowments are the pivots around which development revolves. Human intervention plays a critical role in the sustainability or depletion of these resources. Thus the ability of the natural environment to supply raw materials for production on a sustainable basis depends on the management principles and the instruments available for the management of these resources.

#### 3.1.2.1 Biodiversity (Including Protected Areas)

The Umtshezi Municipality is rich in biodiversity. The western and southern portions of the municipality are particularly high in species diversity and habitats. The eastern parts in particular and portions of the central areas of the municipality have intermediate sensitivity to species diversity. In the central parts and areas centrally placed towards the north, species diversity and communities tend to be irregular with some areas having intermediate sensitivity and others having low sensitivity.

South Africa has ratified the International Convention on Biological Diversity, which commits the country, including KwaZulu-Natal, to develop and implement a strategy for the conservation, sustainable use and equitable sharing of the benefits of biodiversity. In the Province of KwaZulu Natal, Ezemvelo KZN Wildlife is the authority responsible for planning and management of biodiversity conservation. As a means of complying with the requirements of the Convention on Biological Diversity, KZN Wildlife has developed management tools to manage the biodiversity resources in the province.

One of the tools of the conservation planning analysis (C-Plan) is an irreplaceability map of the province of KwaZulu-Natal.  This map is divided into 2 by 2 km grid cells called ‘planning units’.  Each cell has associated with it an ‘Irreplaceability Value’ which is one reflection of the cells importance with respect to the conservation of biodiversity.  Irreplaceability reflects the planning units ability to meet set ‘targets’ for selected biodiversity ‘features’.  The irreplaceability value is scaled between 0 and 1.

Irreplaceability value – 0.  Where a planning unit has an irreplaceability value of 0, all biodiversity features recorded here are conserved to the target amount, and there is unlikely to be a biodiversity concern with the development of the site.

Irreplaceability value – 1.  These planning units are referred to as totally irreplaceable and the conservation of the features within them are critical to meet conservation targets.  (Developments in these areas definitely require EIA for which, and depending on the nature of the proposal, an authorisation is unlikely to be granted).

Irreplaceability value > 0 but < 1.  Some of these planning units are required to meet biodiversity conservation targets.  If the value is high (e.g. 0.9) then most units are required (few options available for alternative choices).  If the value is low, then many options are available for meeting the biodiversity targets.  (EIA required and depending on the nature of the proposed development, permission could be granted).

The C-Plan is used to develop a minimum sets of biodiversity required (Minset) to meet biodiversity conservation targets. Mindset output map shows areas that are already protected, ‘Mandatory Reserves’ and ‘Negotiable Reserves’.  Mandatory reserves are those areas that appear as totally irreplaceable on the irreplaceability map, since there are no other alternatives for achieving the conservation targets.  Areas identified as negotiated reserves are the areas that the Minset function returns as the most efficient for achieving targets and constraints.  However there are alternatives to achieving the targets and constraints but with less efficiency, and hence the designation of this area is still negotiable.

Majority of the municipality is accorded very low irriplaceability values. Areas considered as initially excluded correspond with those areas of low irriplaceability values. This implies that development planning in these areas is not likely to infringe significantly on biodiversity conservation issues. However, care needs to be taken in planning infrastructure in particular and developments that are likely to take up large extends of land in areas that are labelled as negotiated reserves especially in areas around Weenen and north east of Colenso. Development in such areas should involve low key developments and planning processes should involve KZN Wildlife at the conception stage of the planning process.

Areas labelled as Mandatory Reserve located at the southern tip of the municipality is considered as important for biodiversity conservation. These areas would definitely be expected to be conserved by KZN Wildlife. It is recommended that areas labelled as Mandatory Reserved by included as part of passive open spaces in the municipality.  There is a centrally located protected area west of Weenen town. This area is a legally protected area which is not available for development or any land use changes except by consent from the relevant authorities. It is recommended that protected areas and mandatory reserves should be included in passive open systems. Negotiated reserves should be zoned as limited development areas where all developments involving new open spaces should be undertaken under the guidance of an EIA.

#### 3.1.2.2 Hydrology

Umtshezi Municipality is a major contributor to the provinces water supply and play a major role in the agricultural and industrial sectors of the economy in KZN.  Three of the rivers in the province flow through the municipality area, namely (refer to Map 8):

Boesman River,

Bloukrans River,

Sikhehlenga River, and

UThukela River

Figure 5: Rivers and catchments

The quality and quantity of water emerging from the municipality largely depends on land use and land management practices in the municipality. Since impacts on natural river systems at any given point is propagated over long distances beyond the point of impact, care needs to be taken to protect the rivers and wetlands in the municipality from undue pollution.

Thus in order to protect rivers, there is the need to investigate and establish the 1:100 year floodline for all major rivers in the municipality. It is also necessary to investigate and delineate suitable buffers for the wetlands in the municipality.

#### 3.1.2.3 Air Quality

Domestic energy or fuel use depending on the type of fuel used, is a significant source of indoor and outdoor air pollution. Air pollution comprises e.g. outdoor (ambient) pollution:- fossil fuel burning (e.g.) power generation, (cars) industrial non- fossil fuel emissions, natural emissions, pesticides etc.  Indoor pollution includes burning coal, wood, paraffin for heating, cooking and lighting.The Nestle SA in Estcourt and Masonite SA are the two industries which pollute the air at Umtshezi Municipality.The Umtshezi Municipality is situated near Drankesburg mountains filled with cold,dense air,this dense air brings pollutants from the local coffee industry into the town which causes the town to smell burnt coffee every morning and evening as a result the Municipality suffers a short term peaks in pollution.Reported trends in air quality are as follows:

there is an increase in air pollution from Nestles as they are expanding the plant; and

Increase of air pollution from Masonite has been noted.

An increase in vehicle volumes and traffic congestions in peak hours, particularly in the CBD and many of the arterial routes; and

Formal and informal settlements that use coal and firewood for heating and cooking.

#### 3.1.2.4 Climate Change

This is ongoing trend of changes in the earth’s general weather conditions because of an average rise in the temperature of the earth’s surface often referred to as global warming. While weather changes on a daily basis, climate represents the statistical distribution of weather patterns over time. In this regard, a policy needs to be developed with a strategic approach that is:

Needs-driven and Customized - Employing a wide range of different types of adaptation and mitigation approaches, policies, measures, programmes, interventions and actions that meet the special needs and circumstances of those most vulnerable;

Developmental - Prioritizing climate change responses that have both significant mitigation and adaptation benefits and that also have significant economic growth, job creation, public health, risk management and poverty alleviation benefits;

Transformational, empowering and participatory - Implementing policies and measures to address climate change at a “scale of economy” that enables and supports the required level of innovation, sector and skills development, finance and investment flows needed to reap the full benefit of a transition to a lower-carbon, efficient, job-creating, equitable and competitive economy.

Balanced and cost effective - Implementing a balanced approach to both climate change mitigation and adaptation responses in terms of cost-benefit, prioritization, focus, action and resource allocation.

Umtshezi is characterized by dry winters and wet summers, with thunderstorms being very common in summer

Environmental Management and Sector Plans:

Umtshezi LM is committed to adhere to sustainable development principles in its municipality for the benefit of present and future generation. This is achieved through proper environmental planning which includes environmental sector plans, which supposed to be considered in integrated development planning of Umtshezi LM to avoid environmental degradation.

Environmental Planning concerns itself with the decision-making processes where they are required for managing relationships that exist within and between natural systems and human systems.

The municipality has not undertaken a SEA; although the district has developed, an Environmental Planning endeavors to manage these processes in an effective, orderly, transparent and equitable manner for the benefit of all constituents within such systems for the present and for the future. Present day Environmental Planning practices are the result of continuous refinement and expansion of the scope of such decision-making processes. Environmental sector plans can be used to manage environment in the area of municipal jurisdiction. The following are the existing Environmental sector plans for Umtshezi LM:

Integrated Waste Management Plan

This plan covers the following key aspects Status quo analysis of Waste Management Goals and objectives of Waste Management, Gaps and needs and needs assessment of Waste Management, Evaluation of alternatives for Waste Management, Framework for an Implementation Strategy. Umtshezi manage environment in the area of municipal jurisdiction.

Identified Environmental Challenges

- Illegal dumping

- Air Pollution

- Loss of Biodiversity

- Environmental Degradation

- Lack of environmental management by-laws and policies

- Lack of law enforcement

- Lack of environmental education and awareness

- Flooding

General Strategies / Intervention

The municipality has identified the following key interventions/strategies that can be explored to address the above-mentioned environmental challenges and assist in job creation for local economic development:

Adaptation and Mitigation Measures:

The use of Sustainable Energy as a means of intervention on reducing greenhouse gas emissions from energy use. Additional areas that will be covered in this theme include creation of local economic opportunities through the development of the sustainable energy use projects, building capacity and knowledge of municipal citizens in the climate impact of energy use, and ensuring the adaptation of energy systems to future climate change.

Transport:

- The intervention is on moving towards less carbon intensive forms of transport. Additional areas that will be covered in this theme include the creation of local economic opportunities in the provision of low carbon transport, building capacity and knowledge of municipal citizens on the climate impact of transport, and ensuring the adaptation of the transport system to future climate change.

Biodiversity:

- The intervention is on protecting ecological infrastructure. Additional areas that will be covered in this theme include the creation of local economic opportunities in biodiversity protection, building the capacity and knowledge of municipal citizens on the importance that Biodiversity plays in providing ecosystem services, and the role biodiversity can play in mitigation strategies.

Water:

- The intervention is on preparing for the impacts of a change in rainfall patterns. Additional areas that will be covered in this theme include the creation of local economic opportunities in water and sanitation, and building the capacity and knowledge of Umtshezi citizens on the value of conserving water.

Food Security:

- The intervention is on preparing for the impacts of a change in climate on food production and security. Additional areas that will be covered in this theme include the creation of local economic opportunities in agriculture, building the capacity and knowledge of municipal citizens to grow their own food, and ensuring that greenhouse gases from agricultural processes are reduced.

Health:

- The intervention is on preparing for the impacts of a change in climate on human health. An additional area that will be covered in this theme is building the capacity and knowledge of municipal citizens on the risks of climate related disease.

Waste Management and Pollution:

- The intervention is on minimizing the amount of waste that goes to landfill and reducing pollution from industry. Additional areas that will be covered in this theme include the creation of local economic opportunities in waste management and recycling, building capacity and knowledge of the municipal citizens on the value of managing waste and pollution, and reducing emissions from waste and industries.

SWOT ANALYSIS OF THE Umtshezi LM (ENVIRONMENTAL MANAGEMENT)

The Environmental SWOT Analysis (Strengths, Weaknesses, Opportunities and Threats) is presented in the Table below:

| MUNICIPALITY | STRENGTHS |  | WEAKNESSES | OPPORTUNITIES | TREATS |  |
| --- | --- | --- | --- | --- | --- | --- |
| Umtshezi Local Municipality | Large biodiversity that inhabits an ecosystem landscape that has retained ecological functionality; There are wetlands, important water yield areas and streamlined rivers The presence of Priority Floral Species that prevents ecological degradation and further loss of vegetation The municipality also contains the basis of the Tugela-Vaal water scheme and good water resources. Indigenous planted at Wembezi Area as a response to reduction of Carbon Footprint Municipal Participation in Greenest Municipality Competition (GMC) Partnerships with other sector departments | Limited benefits derived from international assets situated in the municipality Lack of environmental compliance and enforcement; this weakens management of the natural environment Lack of environmental management strategies and key interventions to monitor & manage biodiversity as well as ecological footprint Lack of common planning between development planning and environmental planning Lack of environmental education & awareness in municipal communities |  | Improvement of biodiversity and hydrological integrity of aquatic systems There is an opportunity for contributions to rural livelihood through employment opportunities in alien eradication operations as well as beneficiation of some species as they provide materials for the production of various household and saleable items such as building materials, crafts and furniture and fuel wood Stakeholder alliance on environmental protection Revenue generation through conservation of biodiversity Mapping environmental sensitive areas |  | On-going environmental degradation affecting the ecotourism, leading to a reduction of resources available for conservation aspects. Low economic growth and increasing rate of unemployment in major economic sectors Alien infestation may lead in marked declines in stream flow, transformation of vegetation composition & structure; alteration of patterns nutrient cycle & fire regime; also impact on Tourism & Agricultural production Poor environmental management due to lack of environmental awareness Industrialisation and overpopulation Illegal Dumping which pollutes wetlands High potential agricultural land, potential forestry areas and areas likely to experience settlement expansion this poses greatest threats to identified Critical Biodiversity Areas (CBAs) Limited benefits derived from international and national assets situated in the district. |

### Disaster Management

#### 3.1.4.1 Risk Assessment

To establish a uniform approach to assess and monitor disaster risks that will inform disaster risk management planning and disaster risk reduction undertaken by organs of State and other role players.

Disaster risk assessment is the first step in planning an effective disaster risk reduction programme. It examines the likelihood and outcomes of expected disaster events. This would include investigating related hazards and conditions of vulnerability that increase the chances of loss. Disaster risk assessment planning also requires identification of key stakeholders, as well as consultation with them about the design and/or implementation of the assessment and the interpretation of the findings.

Disaster risk assessments must be undertaken to:

Anticipate and plan for known hazards or disasters to prevent losses and limit endangering impacts.

Ensure that development initiatives maximize their vulnerability reduction outcomes.

##### Risk Profile of the Umtshezi Municipality

This section presents the findings of the disaster risk analysis and assessment of the Umtshezi Municipality. The chapter begins by presenting the key findings of the disaster risk analysis & Assessments on the prevalent disasters, followed by the impact these hazards have as well as the hazards that have the potential to cause catalyst disasters. The Umtshezi Municipality’s vulnerability analysis and adjustment is also presented and finally the section concludes with the overall analysis of capacity and resources for the Umtshezi Municipality. It should be noted that that these assessments distinguishes between the disaster risks faced by the rural dwelling households as well as the urban dwelling households did.

##### Risks Requiring Preparedness Plan

Based on the desktop disaster risk review, analysis and assessments conducted on the prevalent disasters within the Umtshezi Municipality ,the following hazards have been identified and classified as key hazards prevalent the  within the municipality .The key prevalent hazards and disasters include but not limited to the following :

Rural & Urban Fires

Thunderstorms and Lightening

Floods

Droughts

Tornado

Soil Erosion

Environmental Degradation

Snow

Technological Hazards

It is common knowledge that these hazardous events not only destroy and slow down years of hard work and development but also will result in severe social and economic losses both at the local, provincial and national level where these various structures of government and emergency & disaster management organisations are required to provide emergency relief for the victims. These findings will be later followed by a detailed account of the impacts that can be sustained in the event that measures are not in place to prevent, mitigate or reduce the risk of the hazards happening in the near future.

It is generally acknowledged that there are a host of risks and hazards, which result in disasters; it is however for a number of reasons not the intention of this exercise to discuss each hazard in this framework. Therefore given there is substantial evidence from the findings of the data review assessment and analysis suggesting that fire, flooding, thunderstorm and drought appears to be the most prevalent disasters, it has been deemed appropriate to discuss these prevalent hazards in much more detail

#### 3.1.4.2 Risk Reduction Plan

The Disaster management framework and disaster risk management plan are the strategic mechanisms through which disaster risk management action is co-coordinated and integrated across all spheres. Umtshezi Local Municipality currently has an adopted Disaster Management Framework. Our District Municipality Framework is currently under review.

Level 1: Disaster Risk Management Plan: A Level 1 The disaster Risk Management Plan focuses primarily on establishing institutional arrangements for disaster risk management.

Level 2: Disaster Risk Management Plan: A Level 2 Disaster Risk Management Plan applies to national, provincial and municipal organs of State that have established the institutional arrangements, and are building the essential supportive capabilities needed to carry out comprehensive disaster risk management activities.

Level 3: Disaster Risk Management Plan: A Level 3 Disaster Risk Management Plan applies to national, provincial and municipal organs of States that have established both the level 1 and level 2 disaster risk management plans. The level 3 plan must specify clear institutional arrangements for co-coordinating and aligning the plan with other governmental initiatives and plans of institutional role players. It must also show evidence of informed disaster risk assessment and ongoing disaster risk monitoring capabilities, as well as relevant developmental measures that reduce the vulnerability of disaster prone areas, communities and households.

#### 3.1.4.3 Disasters and possible interventions

To complete the plan it was deemed necessary to include a pro forma. Further research on this topic will be done in conjunction with Municipal Disaster Committee as well as Academics in the field of disaster risk management during the second phase.

#### 3.1.4.4 Principles governing disaster risk management in the Municipal sector

The principles applied in managing municipal disasters are guided by the disaster risk management cycle model described in the National Disaster Risk Management Framework and seeks to do the following:

Address important human needs;

Be driven at all tiers of government;

Be transparent and inclusive;

Ensure community involvement;

Accommodate local conditions;

Have legitimacy;

Be flexible and adaptable;

Be efficient and effective;

Be affordable and sustainable;

Be needs oriented and prioritized;

Involve other actors;

Have a multi-disciplinary and integrated approach;

Focus on key issues;

Be practical.

#### 3.1.4.5 Response and Recovery

To ensure effective and appropriate disaster response and recovery by:

Implementing a uniform approach to the dissemination of early warnings.

Averting or reducing the potential impact in respect of personal injury, health, loss of life, property, infrastructure, environments and government services.

Implementing immediate integrated and appropriate response and relief measures when significant events or disasters occur or are threatening to occur.

Implementing all rehabilitation and reconstruction strategies following a disaster in an integrated and developmental manner.

Early warnings

Early warnings are designed to alert areas, communities, households and individuals to an impending or imminent significant event or disaster so that they can take the necessary steps to avoid or reduce the risk and prepare for an effective response.

Assessment, classification, declaration and review of a disaster

When significant events or disasters occur or are threatening to occur, clear guidelines for the measures that have to be taken need to be established. Organs of State are in terms of section 25 of the Disaster Management Act, 2002, tasked with primary responsibility for dealing with disasters because of a particular hazard or significant event. To ensure immediate and appropriate response and relief actions the municipality will prepare operational guidelines for initial assessments, the extent of the area affected and the damage to critical infrastructure, lifeline facilities, property and the environment.

Disaster reviews and reports

Comprehensive reviews will be conducted routinely after all significant events and events classified as disasters. The findings will directly influence the review and updating of disaster risk management plans and will serve as valuable training aids.

#### 3.1.4.6 Training & Awareness

To support the education, training, public awareness and research enabler, the following functionalities are required:

Education and training programmes pertaining to disaster risk management in all spheres of the education system need to be recorded and monitored.

The content of education and training programmes as well as records of participants (professionals, volunteers, communities, learners), and the education and training programmes they attended must be recorded.

A register and records need to be kept of all accredited service providers as well as accredited facilitators to ensure that minimum standards set by Sector Education and Training Authorities (SETA's) are met.

Research programmes and projects need to be registered and monitored and the information disseminated to relevant stakeholders.

Initiatives related to an integrated awareness programme by all spheres of government need to be recorded to minimize duplication and to ensure synergy among stakeholders.

#### 3.1.4.7 Disaster Management SWOT Analysis

Table 5: Disaster Management SWOT Analysis

| Strengths | Opportunities |
| --- | --- |
| - Community outreach; - Quick response; - Enabling mechanisms in place including policy, structure, capacity building and resources; and - We have the Disaster Management Forum which uncludes local NGOs / NPOs (Alimdaad Foundation and Meals on Wheels) and etc. | - Community education on disaster risk management; - More robust land use management; - Environmental management through land degradation and unsustainable agricultural practices; and - Encourage pre-disaster, vulnerability and reduction and mitigation measures. |
| Weaknesses | Threats |
| - Environmental degradation; - Soil Erosion; - Technological Hazards; - Rapid and poorly controlled urbanization and underdevelopment in the rural areas; - Inactive public policy; - Increasing construction of municipal and infrastructure production in hazard prone areas; and - Dense population in flood plains and settlement below potential hazard areas. | - Rural and Urban fires; - Thunderstorms and Lightning; - Floods; - Droughts; and - Tornado. |

## DEMOGRAPHIC CHARACTERISTICS

### POPULATION SIZE AND STRUCTURE

The 2011 Census data estimated that the total population of Umtshezi Municipality at 83 907 individuals.  It has the smallest population within the uThukela District and experienced a population growth rate of  3.25% between 2001 and 2011. The uMtshezi population size in 2011 accounts for approximately 12.4% of the overall districts population of 668 848 people. The increasing population  could be attributed by amongst others inward migration of people moving into  uMtshezi from other neighbouring municipalities perhaps in search of better living standards and greener pastures.

Table 6: Population growth

| Municipality | Wards | Population |  | Population Growth (% p.a.) |
| --- | --- | --- | --- | --- |
|  |  | 2001 | 2011 | 2001-2011 |
| DC23: UThukela | 73 | 657 736 | 668 848 | 0.17 |
| KZN234: Umtshezi | 9 | 60 087 | 83 153 | 3.25 |
| KZN236: Imbabazane | 13 | 120 622 | 113 073 | -0.65 |
| KZN 233: Indaka | 10 | 113 644 | 101 557 | -0.97 |
| KZN 232: Emnambithi | 27 | 225 459 | 237 437 | 0.52 |
| KZN 235: Okhahlamba | 14 | 137 525 | 151 441 | -0.43 |

Source: Census 2011

Figure 6: Population by ward

The Municipality has 19 252 households, spread unevenly over nine (9) municipal wards.  The majority of the people are concentrated in urban areas (±29 934 – wards 3 and 4) and in farming areas (±19 950), but there are a few patches of high-density settlements within informal areas, hence, there have been Housing projects running to date in different wards of the municipality and this has contributed to the growth rate. And the total number of new households is 1688 households and are distributed as follows: Colita (301 households); Wembezi A (515 households); Wembezi D (800 households); Kwanobamba Phase 2 (72 households).

The composition of the population is dominated by black females, while the fmeale population also dominates the population numbers on average.

Table 7: Population group by gender

|  | Male | Female | Total | Percentage |
| --- | --- | --- | --- | --- |
| Black | 34575 | 40451 | 75026 | 90.23% |
| Coloured | 569 | 568 | 1137 | 1.37% |
| Indian or Asian | 2386 | 2449 | 4835 | 5.80% |
| White | 949 | 959 | 1908 | 2.30% |
| Other | 136 | 111 | 247 | 0.30% |
| Total | 38 615 | 44 538 | 83 153 | 100% |

Source: Census 2011

### AGE BREAKDOWN

The age breakdown determines the kind of economic activities required within the varying wards.  Different age groups have different economic needs and different spending patterns.  Approximately 71% of the total population in Umtshezi Municipality area is below the age of 35.  Children, below the pre-school enrolment age (that is, 0-4 years of age), constitute 12% of the population, with those who are at school-going age, including pre-school constitute 24% of the entire Municipal population.  Approximately 3% of the total population is over the age of 65 years.  This scenario indicates the high dependency ratio incident within the municipal area, an event that might have a negative impact on the overall socio-economic development of the area as it impedes on the ability of the individuals to save and invest.

Table 8: Population by Age

| AGE | Population |  | Percentage % |  |
| --- | --- | --- | --- | --- |
|  | Male | Female | Male | Female |
| 0 – 4 | 5109 | 5014 | 13 % | 11% |
| 5 – 9 | 4.625 | 4.624 | 12% | 10% |
| 10-14 | 4.519 | 4.679 | 11% | 10% |
| 15-19 | 4.217 | 4.466 | 11% | 10% |
| 20-24 | 4.053 | 4.142 | 11% | 9% |
| 25-29 | 3.564 | 4.072 | 9% | 9% |
| 30-34 | 2.600 | 3.061 | 6% | 7% |
| 35-39 | 2.221 | 2.828 | 6% | 6% |
| 40-44 | 1.829 | 2.412 | 5% | 5% |
| 45-49 | 1.594 | 2.330 | 4% | 5% |
| 50-54 | 1.210 | 1.662 | 3% | 3% |
| 55-59 | 1.057 | 1.504 | 3% | 3% |
| 60-64 | 876 | 1.407 | 3% | 3% |
| 65-69 | 466 | 801 | 2% | 2% |
| 70-74 | 336 | 613 | 1% | 1% |
| 75-79 | 150 | 360 | 0% | 1% |
| 80-84 | 102 | 312 | 0% | 0% |
| 85+ | 87 | 251 | 0% | 0% |
| TOTAL | 38615 | 44538 | 100% | 100% |

The table above (age breakdown) indicates that the largest age group in the municipality is between the ages of 15-34 constituting 37% of the entire population.  This is followed by ages 35-64 (25%) and by 5-14 age group (23%).  This trend obliges the provincial and national government (implementation) and the local municipality (planning) to allocate a large percentage of their budget to social development facilities such as schools, child grant, pension and clinics. However, capital facilities such as roads, water and electricity infrastructure and municipal marketing activities require the municipal attention.

#### 3.2.2.1 Dependency Ratio

Umtshezi Municipality has 83% dependency ratio which causes serious problems for a town if a large proportion of a government's expenditure is on health, social security & education, which are most used by the youngest and the oldest in a population. The fewer people of working age, the fewer the people who can support schools, retirement pensions, disability pensions and other assistances to the youngest and oldest members of a population, often considered the most vulnerable members of society.Nevertheless, the dependency ratio ignores the fact that the 65+ are not necessarily dependent (an increasing proportion of them is working) and that many of those of 'working age' are actually not working.

### Mortality Rate

Perinatal Mortality Rate for Umtshezi Municipality for January-December 2013 is 51.1%.

Maternal Mortality Rate for Umtshezi Municipality for January-December 2013 is 25%.

There are majors taken by the local hospital and the clinics in trying to deal with how to reduce the mortality rate, lessons on health education together with Sukuma Sakhe has been conducted.

#### 3.2.3.1 Crude Death Rate

Crude death rate indicates the number of deaths occurring during the year, per 1,000 he provides the rate of natural increase, which is equal to the rate of population change in the absence of migration.

#### 3.2.3.2 Leading Causes of Death

The most recent death statistics in South Africa have revealed a mortality rate of roughly 570 000 people annually. In 2009 - the latest available complete death statistics - this figure was at 572 673, or 1.7%. The majority of these deaths can be attributed to illness, but other contributing factors include road accidents, acts of violence and accidental injury.

In South Africa, the leading causes of death are natural causes, and are usually the result of parasitic or infectious diseases. Figures released in 2011 by Statistics South Africa revealed that the leading known cause of death among South Africans in 2009 was tuberculosis. In 2009, 12.6% of deaths were officially attributed to TB - more than 69 000. The second-highest known cause of death in South Africa was influenza and pneumonia, which attributed to 45 602 death in 2009, or 7.7% of recorded deaths. Intestinal infectious diseases were the third-highest known cause of death in SA in 2009, and include illnesses such as gastroenteritis and diarrhoea, which can lead to death because of dehydration. 39 351 were attributed to intestinal infectious diseases in 2009 - 6.6% of recorded deaths.

The statistics also revealed that thousands of men and women continue to succumb to heart disease, hypertension and other cerebrovascular illnesses in South Africa each year. In 2009, these illnesses contributed to more than 78 900 deaths in South Africa. Other larger causes of death among South Africans are malignant neoplasms (cancer), respiratory ailments and kidney disease.

#### 3.2.3.3 HIV Prevalence

There is still a great deal of ignorance about the spread of HIV/AIDS. The HIV Prevalence in Umtshezi Municipality for the Period April 2009 to October 2009 is 36.4%. The District is at 30.9%. Access to social welfare services still poses another challenge on the access to social services.  The Department of Welfare and population Development is working together with the Municipality in ensuring that such services are rendered to the local communities.  This is one of the priority areas for the Municipality.

The scourge of AIDS affects all the citizens of this country, mostly the youth. Umtshezi Local Municipality has realized that HIV/AIDS pandemic will have a devastating impact on its socio-economic development programs and formulated the HIV/AIDS council that was launched in 2007. This has led to the formation of HIV/AIDS development plan, which seeks to ensure that HIV/AIDS infection rates are lowered and that those who are affected and infected with the pandemic are given a necessary support.  The Municipality will embark on HIV/Aids programs during the 2012/17 financial years that would contribute to the mitigation of this pandemic and a permanent fulltime HIV/AIDS Co-coordinator has been appointed in 2013.

## MUNICPAL TRANSFORMATION AND INSTITUTIONAL DEVELOPMENT

### Municipal Transformation and ORGANIZATIONAL DEVELOPMENT

The Political structure of the Municipality consist of the Mayor, the Deputy Mayor and the Speaker as full-time office bearers. In total there are 17 councillors (inclusive of office bearers), which constitutes the Municipal Council. Out of 17 councillors, nine councillors are ward councillors, and the other eight are PR councillors after May 2011 Local Government Election, Umtshezi was constituted by nine wards.

### Institutional Arrangements

On the political institutional arrangement, Umtshezi Municipality has a collective executive system combined with a ward participatory system. The Political structure of the municipality consists of the Mayor, the Deputy Mayor and the Speaker as full-time office bearers. In total there are 17 councillors (inclusive of office bearers), which constitutes the municipal Council. Out of 17 councillors, 9 councillors are ward councillors, and the other 8 are PR councillors. After the May 2011 Local Government Elections, Umtshezi was constituted by nine wards.

The municipality has an Executive Committee that comprises of 3 members, as per the political quota representation. There are also four sub – committees in which councilors serve and deliberate on matters to be submitted to EXCO and Council thereof. The committees are as follows:

Infrastructure, Housing and Town Planning Committee, Rural development, Agrarian;

IDP, Finance, Local Economic Development and Tourism Committee;

Sports, Gender and Vulnerable Groups Committee, Health, Youth, Education, local Labour;

Human Resources, Transformation and Safety / Security Committee;

Peace and stability; and

Local labour forum (LLF).

The Speaker and the Municipal Manager participate in functional IGR structures of the district. Frequent Sector Department meetings are held during the IDP Process.

Of importance also is the involvement of the both internal and external stakeholders in the decision making processes on Umtshezi.  The Municipality has devised clear roles and responsibilities for each structure.  For example, the internal role players include the councilors, officials, IDP steering committee and the representative forum (RF).  The external role-players include the District Municipality, the ward committees as well as the sector departments.  The RF provides a platform for all role players to take part in the decision making process to ensure the effectiveness of the IDP Development.

#### Powers And Functions Of Municipality

In realizing its Strategic Objectives, National and Provincial Priorities, uMtshezi Municipality will thrive to provide the following powers and functions as enshrined in the constitution and the Municipal Systems Act of 2000.

The following are the powers and functions of our municipality:

| - Development planning and Local economic development; - Solid waste disposal; - Firefighting services; and - The establishment, conduct and control of cemetery and crematoria. | - Promotion of local tourism; - Air pollution; - Building regulations; - Storm water management; - Street trading; and - Control of undertakings that sell liquor and food to the public. | - Street lighting; - Traffic and parking; - Electricity; - Local sports facilities; - Noise pollution; - Pounds; and - Municipal roads. |
| --- | --- | --- |

The Umtshezi Municipality does not have sufficient capacity, both human and financial capacity, to perform these powers and functions effectively and efficiently. To improve its capacity, the municipality as entered into an “ Agreement with the Department of Co-operative Governance and Traditional affairs.”

Business Plans have been developed to source funds from financial institutions and Donors, etc.

### Organizational Structure / ORGANOGRAM

The organogram has been developed so as to accommodate the HR needs of the Municipality.

Table 9: Organogram

### Municipal Institutional Capacity and Status Of Critical Posts

On the administration institutional arrangement all Section 57 positions are filled. All section 57- Managers have performance agreements and charters. The diagram below presents the first page organogram of the municipality and division of powers and functions to different portfolios within the Umtshezi Municipality establishment to ensure the effective implementation of the IDP.

### HUMAN RESOURCE STRATEGY

The Municipality has a Human Resource Strategy Document which responds to the long-term development plans which reflect on recruitment, retention, succession plan, scarce skills, skills development plan, etc, and an adopted organogram, with 380 current posts, 142 vacant posts and 2 frozen posts.

There is a budget allocated for the review of the Performance Management System for the Municipality. The current Performance Management System (2012/2013) is fully functional, however there is a need to appoint a full time Performance Officer/Manager. The Municipality has established a Special Programmes Units that will ensure there is effective implementation of the Equity Plan in order to address the issues relating to HIV / AIDS, youth, gender, pensioners and people with disabilities. Policies to address the foregoing Special Programmes have been developed.

Comments on Skills Development and related expenditure and on the Financial Competency Regulations

Adequacy of training plans

Trainings planned for personnel development are line with the departmental needs concerned and training do equip personnel with required skills to effectively perform their duties. Training costs have become so expensive from service providers in such an extent that training budgets is exhausted before all training are finalised.

Training funding is expected to increase due to the increases by service providers.

#### 3.3.5.1 Employment Equity Plan

The uMtshezi Local Municipality embarked on drafting the Employment Equity Plan, which reflects the primary areas of the course of action to follow. This Plan is for all intent and purposes binding and should balance considerations of strategic business and with a justifiable equity rationale. The intention is that the policy be tabled at the Employment Equity Committee, since it is an integral part of the committee’s objective to gain acceptance of the policy throughout the Municipality at all levels. This is compliance to the Employment Equity Act of 1998.The Municipality have constructively taken cognisance of the results of an in-depth strategic analysis and preliminary information gathering process, as well as the need identified during the process.

This Employment Equity Plan presents proposals that will ensure that the workforce of the UMtshezi Local Municipality will be more reflective of the demographics of the Municipality with five (5) years. After five (5) years, the progress of the plan shall be reviewed. In designing this Plan, great care has been taken to consult all stakeholders and to reach consensus with them, to ensure that this plan enjoys wide support throughout the Municipality.

The targets set in terms of employment levels are more primarily aimed at top management and middle management, operative and supportive transformation. Other elements cover wide field and will, by their nature, affect all employees within the UMtshezi Local Municipality.

#### 3.3.5.2 Work Skills Plan

The Municipality has approved the Skills Development Plan, which also includes the Workplace Skills plan.  This plan promotes education and training in the Municipality and to empower all employees as per the Skills Development Act, Employment Equity Act and the Basic Conditions of Employment Act.

The Workplace Skills Plan has enabled the acquisition of specialist skills required by legislation, specialist technical training, project management and planning, social/community/economic development and training, apprenticeships and administration skills. With the receipt of discretionary grants the critical and scarce skills training will be a priority in the development of a succession plan and staff retention strategy.

#### 3.3.5.3 Recruitment and Selection Policy

Recruitment is aimed at attracting, obtaining and retaining people with required competencies (knowledge, skills, and behaviour) and attitude. Recruitment also involves marketing Council careers in order to supply a sufficient number of potential employees for selection. In addition, recruitment actions will ensure that a continuous supply of high quality human material is available to meet the Council’s immediate and future human resource needs. Recruitment is also attuned to establish a positive image of the Council as an employer in the labour market.

#### 3.3.5.4 Retention and Exit Policy

It is generally agreed that the achievement of the Umtshezi Municipality’s strategic objectives is largely dependent on its ability to attract and attain high caliber individuals. This is particularly important with regard to defined critical occupations, strategically critical individuals and ensuring adequate succession.

Attraction and Retention rest on the following key principles:

Managing people well to ensure directed and motivated employees;

Paying people competitively and rewarding superior performance;

Developing people and retaining the by providing perpetual learning and challenge;

Establishing a work-life culture and climate that is attractive and supportive; and

Each of our four principles has to be weighed and balanced within a practical attraction and retention strategy.

## SERVICE DELIVERY AND INFRASTRUCTURE ANALYSIS

### Water and Sanitation

Access to water within 200m of one’s home is an acceptable minimum standard irrespective of whether the water comes from a hand pump, borehole and a reticulation system supplied from a high yielding borehole or a reticulation system from a bulk line or reservoir. In the Umtshezi Municipality the water services backlog is at 7% (UTDM IDP 2009/2010) while the sanitation backlog is estimated at 8%. The planned housing projects are guaranteed access to water through CMIP funding. Thus housing development provides opportunities for households to access water and sanitation. This is a district competency and therefore housing projects have to be aligned to the district infrastructure plan to ensure that they the bulk infrastructure component of the development is supplied employment, housing and land, with people able to exercise control over their society, community and personal lives, and to invest in the future.

Figure 7: Sanitation

Source: Census 2011

In Umtshezi Local Municipality, the majority of the population have access to flush toilet connected to a sewerage system.  The above is a clear indication of lower levels of services in Imbabazane Local Municipality.

The continued consumption of un-purified water exposes the community to water borne diseases and poses a major health risk.  In Umtshezi Local Municipality, the majority of people receive piped water from the local water scheme and very little people use boreholes, rivers and water vendors.

Figure 8: Water supply

Source: Census 2011

### Solid Waste Management

There is no municipal wide waste disposal site with the result that dumping is uncontrolled and litter bears testimony to this.  Only Estcourt, Weenen and Wembezi experience some measure of waste management although there is a need for the identification of a new waste disposal site. The majority of people, especially in the farming areas, dispose of their waste on-site and diseases emerge because they do not have information on how to manage the situation.  As a result, diseases are spread and animals are also exposed to hazardous conditions because of plastics.  Awareness campaigns on the importance of proper waste management in attracting investment.  Currently, funds are inadequate to provide formal waste disposal sites, hence, a Waste Management Plan is underway.

Figure 9: Waste removal

Source: Census 2011

#### Integrated Waste Management Plan (IWMP)

In overall terms, Waste management is the collection, transportation, processing, recycling and/or disposal of waste materials. The term usually relates to materials produced by human activity, and is generally undertaken to reduce their effect on health, the environment or aesthetics. Waste management is also carried out to recover resources from it. Waste management can involve solid, liquid, gaseous or radioactive substances, with different methods and fields of expertise for each.

Waste management practices differ from one place to another, e.g. from urban to rural areas, and from residential to industrial producers. Management for non-hazardous residential and institutional waste in municipal areas is usually the responsibility of the local council authorities. Concurrently the management for non-hazardous commercial and industrial waste is usually the responsibility of its generator.

The primary objective of the IWMP is to optimize waste management through the waste tandem by maximizing efficiency and minimizing associated environmental impacts and financial costs and to enhance the quality of life within Umtshezi Local Municipality. The Waste Management Plan must also be integrated with the objectives of the municipal Integrated Development Plan (IDP) in the following ways:

Waste Minimization and Recycling (explore business/employment opportunities)

Waste Collection

Waste Treatment and Disposal (including medical and hazardous waste)

Waste Management Capacity Building and Awareness

Waste Management Costs and Recovery

Environmental Management (only limited to waste management)

The preparation of the IWMP is a requirement of the National Waste Management Strategy, as it requires that all Local Authorities develop and submit such plans to be incorporated into the wide provincial plan to improve the waste management scenarios at the local municipal levels.

Umtshezi municipality is currently developing an Integrated Waste Management Plan.

### Transportation Infrastructure

The Municipality relies heavily on MIG funding for infrastructure development.  The Municipality is working closely with the Department of Transport, through the Rural Transport Forums, in identifying roads that need funding and upgrading within the Municipality.

A Transport Plan has also been developed which stipulates clearly their plans for the building of new roads and maintaining in the next five years.  The O&M of old roads is funded to a total of R1.2 million budgeted for the next financial year; these projects are included in the Project Schedule: Infrastructure and Services.

TRANSPORTATION INFRASTRUCTURE

| PROJECT DESCRIPTION | WARD | INKOSI | AREA | 2013/2014 | 2014/2015 |
| --- | --- | --- | --- | --- | --- |
| Re-gravel: D 1244 | 7 | Mkhize | Hlathikhulu | R2 000 000-00 |  |
| Re-gravel: D 52 | 8 | Private Land Owners | Frere | R1 800 000-00 |  |
| Re-gravel: D 500 | 9 | Private Land Owners | Estcourt | R1 500 000-00 |  |
| Re-gravel: D 1246 | 1 | Ndaba | Goodhome |  | R3 000 000-00 |
| Re-gravel: P 170 | 9 | Private Land Owners | Midway – lowlands |  | R3 600 000-00 |
| Re-gravel: P 176 | 5 | Mthembu | Weenen |  | R2 400 000-00 |
| Causeway: P 176B | 5 | Mthembu | Weenen |  | R3 500 000-00 |
| SIP2 Durban – Free |  |  | N3 |  |  |

### Energy

The Umtshezi Municipality is divided into Eskom Licensed Area of Supply and the Umtshezi Municipality licensed area of supply. Currently all households within the Umtshezi Municipality Licensed area of supply are all electrified. The Municipality is currently doing in fills as well as electrifying the low income housing schemes that are being built. Therefore there are no electrification backlogs within Umtshezi Municipality Licensed area of supply.

Within Eskom Licensed Area of Supply but within Umtshezi Jurisdiction, there are households without electricity. The table below indicates the backlogs as well the progress to-date in addressing those backlogs.

All households that reside within the Municipal Boundary are within the electricity national grid; therefore it will be cost effective to provide the grid energy than the use of the renewable energy sources. The current plan is to connect all the people to the national grid as soon as the funds are made available. However, whilst plans are being made to connect everyone to the grid, there are areas that will have to be identified to be provided with the renewable energy i.e. Solar System.

The Municipality has signed the cooperative agreement with EDI Holdings and currently awaiting funding from the EDI Holdings to Ring Fence the Electricity Department as well as to establish the Separated Operated Entity (SOE). Also the Municipality in partnership with EDI Holdings will need to conduct workshops to ensure that the decision makers are refreshed on the matter. The Municipality signed the cooperative agreement with EDI Holdings and applied for funds to conduct the ring fencing as well as the MSA Section 78 Assessment. The EDI Holdings has programmes that Umtshezi Municipality will have their ring fencing as well as MSA Section 78 will be done in due course.

The Municipality conducted an assessment into its tariffs and it was found to be above the NERSA benchmarks, however financial shortfalls still exists. IBT’s is currently being modeled and is being prepared as per NERSA regulations and will be ready for submission shortly. Budgeted maintenance has grossly affected the functioning of the Electricity Department, and this has resulted in the Municipality being strained financially in terms of resources to keep the electricity department going.

The Municipality is currently doing Skills assessment on its electricity staff to identify the skills gap as well capacity. This will inform the organizational structure review, the skills development as well as the optimum capacity required.

The Municipality does have an Electricity Master Plan, but it is has not been updated. This Master Plan also deals with the electricity issues within the Umtshezi Municipality licensed area of supply.  The Municipality will endeavor to review its Master Plan during the 2012/2017 Financial year.

The municipality tried unsuccessfully to fill the more technical vacant positions due to shortage of skills, technical pool available around Umtshezi. Those residing far could not accept the salary package noting that it is too low. Consultants were used to  build internal capacity and to handle work, currently these employees are being empowered to take over the responsibilities.

Due to high Eskom tariff increases that will be passed on to Municipalities and the limit that NERSA has set on Municipal tariff increases, which is far below Eskom tariff increases, aggravated by the fact that the Municipal tariffs are far below NERSA bench marks, it is making it very difficult for the municipality to efficiently operate the electrical network and to find adequate finances, to maintain and upgrade the electrical infrastructure.

### Access to Community Facilities

Equitable access to social facilities such as to schools, clinics and police stations is an important indicator of the quality of life. Although, the majority part of Umtshezi Municipality fell within the former Natal, the area has suffered from decades of neglect in terms of the delivery of social facilities. As such, the need to address this issue is identified in the IDP as one of the key challenges facing the municipality.

#### 3.4.5.1 Education

Spatial distribution of education facilities in relation to the population density reveals that some areas are not well provided with education facilities. This is based on the application of a standard of 1200 households per secondary school and 600 households per primary school. Areas that require urgent attention include Frere, Rensburg Drift, Cornfields and Thembalihle. In some instances, the settlement does not have sufficient threshold to warrant a school. This situation accounts for a high rate of school drop out and the associated functional illiteracy. This affects mainly the farm dweller households that are located in deep commercial farmlands.

#### 3.4.5.2 Health

An analysis of the spatial distribution of health facilities reveals the same pattern as that of education facilities. Areas such as Wembezi, and Weenen each have one clinic yet they provide service to large areas with households in excess of the norm of 6000 households per clinic or a clinic within a 5km radius from each household. Thembalihle, Rensburg Drift and Frere do not have stationery clinics. The rate of population growth in these areas emphasises a need for these facilities in these areas.

Health facilities in Umtshezi are as follows:

Estcourt Hospital which is a district hospital servicing areas beyond the municipal boundaries.

6 clinics located in Wembezi, Estcourt (2), Weenen, Cornfields, Sahlumbe.

Emergency rescue services (EMRS) found in Estcourt.

As with education facilities, an increase in density in some settlements increases service backlogs and forces people to walk travel long distances so as to access health facilities.

#### 3.4.5.3 POLICE STATIONS

Umtshezi Municipality is generally well provided with police stations as each of the three major population concentration areas is developed with a police station. Information pertaining to the location of crime scenes could not be obtained. Therefore it is difficult to establish the spatial pattern of crime in the area.

### Human Settlements

The majority of the population resides in urban settlements of Weenen, Estcourt and Wembezi. This is informed by the historic growth pattern of the municipality.  The two main nodes of Weenen and Estcourt evolved as agricultural service centres. While Wembezi complex on the other hand served the residential area of Wembezi, The municipal population of 83 153 residents distributed across seven municipal wards   represents a range of predominantly urban, farming communities and rural settlements. Development intensity and housing need particularly is in the urban areas of Estcourt and Weenen and Wembezi with a population of 29 934 residents (49%) of municipal population. These settlements are located on the major activity routes.

The second largest population density with a population of 19 950 (33%) of municipal residents is located on privately owned commercial farmlands. The tribal areas make up 10 038 (16%) of the residents of the municipality.

Taking into account the composition of settlements, that is, urban population (49.9%), farmlands and tribal settlements that comprise 33% and 16 % respectively, it is evident that the 35% of traditional huts are in farmlands and communal areas. The municipal IDP (2008/2009) states that the houses in these areas are in a bad state of repair. They are subjected to periodic collapse during the rainy season or windy times. In terms of Section 9 (1) of the National Housing Act the municipality through its planning takes all reasonable and necessary steps to ensure that, conditions that are not conducive to health and safety of its residents are prevented and removed.

It is therefore without doubt that the greatest areas of housing need in the Umtshezi Municipality are the farmlands and tribal areas. This correlates to the housing development projects planned by the municipality as the majority of them are in rural settlements (see Table 5). The lack of housing development in the rural areas and farm areas can be ascribed to a number of factors, the most important of these being security of tenure on Ingonyama Land and lack of land ownership by farm dwellers.

The project linked subsidy which requires beneficiaries to have outright ownership of the site to which the subsidy relates has been until recently the preferred Housing subsidy Scheme. As a result thereof, housing development has taken place in urban areas as all the current housing developments are in urban settlements. The foreseen challenge in the housing development in farmlands is access to tenure, as this land is privately owned.

Consequently, there has been no development on Ingonyama Land and farmlands resulting in less than adequate housing standards. Almost half of the municipal population resides in these areas. The introduction of the Institutional subsidy now provides a mechanism for development on Ingonyama Land, which provides the beneficiary with a long term-lease.  For farm dwellers access to housing opportunities is reliant on tenure reform.

Table 10: Housing projects

| PROJECT NAME | FUNDER | VALUE | STATUS |
| --- | --- | --- | --- |
| Rensbergdrift | Dept. of Human Settlements | R77 868 000.00 | Awaiting Tranche 1 approval |
| Mimosadale | Dept. of Human Settlements | R77 868 000.00 | Tranche 1 approved. Busy with Tranche 2 – end June 2013 |
| Owl and Elephant | Dept. of Human settlements | R41 114 000,00 | Implementing agent appointed – Tranche 1 end April 2013 |
| Msobotsheni | Dept. of Human settlements | R41 114 000,00 | Implementing agent appointed – Tranche 1 April 2013 |
| Cornfields | Dept. of Human settlements | R164 456 000,00 | IA appointed – Conditional approval – end March 2013 |
| Paapkuilsfontein | Dept. of Human settlements | No budget yet | Awaiting for acquisition of land to be sorted out by DoH |
| Mshayazafe | Dept. of Human settlements | No budget yet | Waiting for authority to advertise project |
| Wembezi A Section | Dept. of Human settlements | R75m | Project enrolled for rectification – proposed budget R75m |
| Kwanobamba 1&2 | Dept. of Human settlements | No budget yet | Project enrolled for rectification – waiting for NHBRC report |
| Nhlawe | Dept. of Human settlements | No budget yet |  |

We have adopted our housing Sector Plan, which has been reviewed accordingly.  We have incorporated our Reviewed Housing Sector Plan within our IDP with proper integration of housing programmes and projects.

### Telecommunications

The Umtshezi Municipality give cell phone allowances to certain staff members depending on their ranks, the Directors and Senior managers receive R1 000 and middle management receive R500.All management staff receive R200 telephone allowance, when a staff member excided what is allocated then he or she pays the difference.

## LOCAL ECONOMIC DEVELOPMENT AND SOCIAL DEVELOPMENT ANALYSIS

### Local Economic Development Analysis

#### 3.5.1.1 COMPETETIVE AND COMPARATIVE ADVANTAGES

The national LED strategy noted that state expenditure (at all levels) is having a limited impact on development goals. This strategy intervention is based on the use of the municipal procurement system to undertake targeted and preferential procurement. This should be undertaken as a specific study within the corporate services section. The intervention should not end at this point – but also the Municipality should monitor that any other state agencies are ensuring that maximum benefits are accruing to local enterprises and local labour. This would include infrastructure development such as water systems and road construction.

LED has been now well institutionalised within KZN234. All staff, councillors and residences of this municipality are fully aware of the importance of LED and are indeed aware of our LED Strategy. We have reviewed and reflected more details of our LED strategy and associated projects within our reviewed IDP. We have placed more emphasis on the implementation actions and progress with regard to the LED in our current IDP. Proper alignment has been ensured of our LED Strategy and realistically practicability in line with the PSEDS and ASGI-SA.  Further, our LED Plan is fully aligned to our SDF and are spatial reflected.

#### 3.5.1.2 Main Economic Contributors in Umtshezi

The economy experienced a negative growth rate until 1999 – 2000, and even since then has exhibited a fluctuating growth rate in spite of the national positive growth. In terms of sectors the area has had mixed success. The three most positive private sectors remain agriculture, manufacturing and trade. These are also the three most important sectors historically. The three sectors differ in their forecast in terms of potential growth, challenges, and the future of employment demand.

The manufacturing and agri-processing sectors remain important, but have experienced a decline. The Estcourt area has been a key center for the processing of agricultural products (60% of manufacturing was previously in food processing) – mostly meat and dairy products. There are obvious important backward and forward linkages between agriculture and food processing, which can be exploited. The manufacturing sector was well established in the past but has experienced a steady decline with a number of large firms closing down. The decline was partly a result of the national slow down in the sector, but also as a result of industries moving to larger centers. The remaining industries are exhibiting growth as the sector as been growing in terms of GDP/GVA, but not in employment. The upturn in manufacturing will not necessarily lead to industries coming back.

The agricultural sector is well established and indicates a level of stability in terms of employment1. There are two key challenges in the sector. The first is that there is a dependency on traditional crops and products with very little innovation or value addition. The second is that the sector appears to be struggling with the possible impacts of land reform. There have been some positive signs as the Estcourt Farmers Association has been investigating the local solution developed at Besters near Ladysmith. At the same time there is also an area proposed for the Gongolo Game Reserve which has been unable to develop a common vision.

The decline in manufacturing employment is notable and a cause for concern. The decline is probably associated with the closure of some firms, the sensitive nature of the sector to broader trends (foreign exchange, cost of raw material, transport etc) and an increase in mechanization. The sector has been growing in terms of GDP/GVA, but not in terms of employment. The increase in employment in community services is largely linked to the establishment of wall-to-wall local government and the expansion of the public sector. This trend will tend to slow as new government structures have been established. The stability in employment in the agricultural sector is positive as this sector is a large employer and has experienced a general down turn in employment at a national level. The construction sector should be showing an improved growth n employment, as should trade. There may have been additional capacity in these sectors, which meant growth could take place without additional employment. Additional capacity may also have been taken on as ‘casuals’ without permanent employment being created. Finance has remained stable, although the sector is growing.

#### 3.5.1.3 Employment AND INCOME LEVELS

The economic analysis undertaken in the Status Quo report indicates that the poverty and unemployment rates in Umtshezi have increased, with employment opportunities not being created quickly enough for the number of people entering the labour force. The Development Bank (2005) has clearly indicated that employment (a job or an income generating activity) is the best protection against poverty. This means that any strategy must protect and build formal employment and assist the poor and second economy participants to access opportunities.

The balance between the two approaches and the use of available resources is also important.

The most disturbing trend is that unemployment and poverty levels will continue to increase unless a new approach is developed. This is despite a growing economy (see Table 1 below). The point is that the economy will not create as many formal sector opportunities as there are job seekers. Future opportunities need to be generated in more creative ways.

Figure 10: Labour market

Source: Census 2011

Umtshezi Local Municipality: 8.6% are discouraged work seekers, while 27.4% are not economically active.

Figure 11: Employment status in Umtshezi

Source: Census 2011

Table 11: Household income

| ANNUAL HOUSEHOLD INCOME | PERCENTAGE ( % ) |
| --- | --- |
| No income | 27 % |
| R 1 – R 4 800 | 10 % |
| R 4 801 – R 9 600 | 20 % |
| R 9 601 – R 19 200 | 13 % |
| R 19 201 – R 38 400 | 11 % |
| R 38 401 – R 76 800 | 9 % |
| R 76 801 – R 153 600 | 7 % |
| R 153 601 – R 307 200 | 2 % |
| R 307 201 – R 614 400 | 0.7 % |
| R 614 401 – R 1228 800 | 0.1 % |
| R 1228 801 – R 2457 600 | 0.2 % |
| TOTAL: | 100 % |

The above figures indicate that on average 27% of the households are surviving on less than R12 per day.  This indicates high dependency ratios in that most of the households may be surviving on government grants ranging from old-age pension grants, disability grants etc.  Even if households employ informal or illegal survival strategies it is unlikely that they generate substantial income given the general lack of viable economic base within rural areas.  This situation indicates a need for development of local economic development activities that will ensure that households do manage to have access to the bare minimum of household’s amenities.

Figure 12: Umtshezi Local Municipality - monthly income

Source: Census 2011

#### 3.5.1.4 Agriculture Sector

#### 3.5.1.5 Tourism

It is difficult to obtain local statistics for tourism in the Umtshezi municipality. However, tourism is one of the sectors that have contributed to the economy of Umtshezi both directly and indirectly. There are surrounding tourism activities that have major influence on the tourism sector of Umtshezi.  The main tourist destinations in the area include:

The Midlands meander, which is an arts and crafts route around the Pietermaritzburg, Hilton and Howick and Mooi River;

Drakensberg Resorts that is a National Heritage Site. The Drakensberg Mountain Range is a well-established holiday destination for local tourists.;

Thukela Biosphere Reserve and Weenen Nature Reserve. These areas focus on eco-tourism;

Battlefields Route – This route encompasses a number of towns in the region in which historic battles took place. Along the route, events are planned which include re-enactments of battles; and

Bushmans Experience– This route starts in Estcourt/ Wembezi and is designed to capture tourists visiting the above destinations, as well as to create a local Umtshezi tourist destination.

There is an existing Tourism Association in Umtshezi, which has a membership of 85% of the Bed and Breakfast establishment in the area (KZN Tourism Brochure).

#### 3.5.1.6 Small Medium and Micro Enterprise (SMME)

The municipality is currently supporting the SMMEs in the following activities:

Skills Development and Training, in partnership with the KZN Department of Economic Development; and

The municipality has also made a budget available for attending to the requests or needs of the SMMEs as and when required.

#### 3.5.1.7 Informal Sector

The most disturbing trend is that unemployment and poverty levels will continue to increase unless a new approach is developed. This is despite a growing economy (see Table 1 below). The point is that the economy will not create, as many formal sector opportunities as there are job seekers. Future opportunities need to be generated in ways that are more creative.

| Unemployment Rate: |  |  |  |
| --- | --- | --- | --- |
|  | Male | Female | Total |
| 1996 | 43.6% | 57.5% | 50.0% |
| 2004 | 53.1% | 73.7% | 62.7% |
| 2011 | 40.0% | 60% | 29% |

#### 3.5.1.8 Manufacturing

The following industries were identified within the municipality:

Eskort Bacon Factory (Meat Processing);

Masonite (Manufacturing of Masonite Board);

Narrow Tex (Manufacturing of Safety / Seat Belts for vehicles);

Clover (Dairy processing e.g. Milk and cream);

Nestle South Africa (Food Processing, e.g. Skimmed Milk, Hot Chocolate, Chocolate and other products);

ECO Plant (Processing of food for animals);

Cabortech (Manufacturing of Charcoal);

Glamosa PTY LTD (Manufacturing of Glass and related items);

Midlands Beer Distribution (Distribution of Beer and related items to the customers of the South Africa Breweries); and

Other light industry.

#### 3.5.1.9 Mining

Umtshezi Municipality is currently having the following Mining activities within its area of jurisdiction:

| Company Name | Description of Company Activities |
| --- | --- |
| Blue Chip Quarry (PTY) LTD | The company specialises in the mining of aggregate and supply of the following: - Concrete Stones; and - Other stone-type material required for General Building or Civil Work. |
| Buckus Sands (PTY) LTD | The company specialises in Sand Mining and supply of the following: - Concrete Sand; - Plaster Sand; and - Building Sand. |

#### 3.5.1.10 services

Umtshezi Municipality offer many services i.e. cleaning and cleansing services, Waste Management services with a huge number of employees, we also have the electricity services who works day and night so as push service delivery, the water services are controlled at UThukela district Municipality.

#### 3.5.1.11 LED SWOT Analysis

| STRENGTHS | OPPORTUNITIES |
| --- | --- |
| - Strategic Location of Umtshezi Municipality - Drakensberg World - Heritage Sites available within the area - Environmental and Cultural Sites available within the area - Good Agricultural Land - High Development Indicators for Umtshezi Municipality - Strong Manufacturing base within the area - Key Industrial Area in the town of Estcourt Significance Index for Agriculture increase for Umtshezi | - Inadequate basic Infrastructure provision and Unstable water supply - Our failure to optimise the tourism opportunities - Dependency ratio is too high - HIV prevalence is high - Lack of support skills in Tourism Industry - Decline in formal employment and Increase in informal employment but no policy to support it - LED strategy is outdated and lacks implementation plan Umtshezi Municipality has not yet created an enabling environment for LED |
| OPPORTUNITIES | TREATS |
| - Location on the N3 development corridor, this can provide more opportunities in the area - Optimum utilization of natural, cultural and historical assets for further economic growth - Vast space of Agricultural Land to be used for primary and secondary production - Explore growth of transport, storage and communication sectors - Need to improve recreational, medical, housing and schooling facilities - Specific interventions to stimulate economic growth - Potential to develop retail facilities Opportunity for further growth of the tourism, and manufacturing sectors | - Unsustainable development practices - Development along the N3 corridor could threaten CBD - HIV prevalence - No employment opportunities and skills development opportunities created, social challenges can escalate to further marginalization - Failed Land Reform Programme - Relocation of Industries - Poor Global Economy - Decline in manufacturing and agricultural sectors - Lack of sound business incentives - High tariffs - Political instability - Disjointed planning Lack of resources, communication and partnerships |

### Social Development

The municipality aims to improve access to social development services and information with this chapter. Core to this chapter is the need for social needs analysis and programmes to facilitate interfaces between different spheres of government charged with social development role.

#### 3.5.2.1 Broad Based Community Needs (3 Priority Projects Per Ward)

Cllrs to submit

#### 3.5.2.2 Education

There is great concern over the distribution of crèche’s, primary and secondary school facilities in the municipality. The quality of education in schools is also not satisfactory because of the shortage of teachers and location of schooling facilities in private land (farms). In some clusters high school learners have to travel long distances because of uneven distribution of schools. The planning of education facilities is complicated by the fact that some parents may choose to support schools in other areas because they are perceived as offering a better service.

Table 12: Population group by Educational Institution

|  | Pre-school | Primary | Sec- School | College | University/ Univ. of Technology | Adult basic Edu. | Other | Not App. | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Blk | 1.462.8 | 5.916.87 | 5.314.09 | 311.363 | 377.430 | 377.430 | 101.954 | 24.768.931 | 38.255.167 |
| Col. | 112.34 | 561.299 | 410.765 | 28.564 | 34.739 | 34.739 | 8.530 | 3.219.235 | 4.375.527 |
| Indian | 26.380 | 125.597 | 105.351 | 12.564 | 45.007 | 45.007 | 3.957 | 925.777 | 1.244.634 |
| White | 108.54 | 349.659 | 339.155 | 45.423 | 155.283 | 155.283 | 11.853 | 3.616.820 | 4.626.733 |
| Total | 1.710.066 | 6.953.426 | 6.169.361 | 397.914 | 612.459 | 612.459 | 126.294 | 32.530.764 | 48.502.06 |

#### 3.5.2.3 Health Sector Analysis

Furthermore, the distribution of clinics and other primary health care facilities within the municipality is uneven with the result that some clusters are left out. There is one hospital in the municipality, which provides for emergency services and hospital care. The Primary Health Care facilities vary in size and they cater for prams and wheelchairs, i.e. the facilities are user friendly. The impact of HIV / AIDS enhances the need for hospitals and clinics.

##### 3.5.2.3.1 HIV / AIDS

There is still a great deal of ignorance about the spread of HIV/AIDS. The HIV Prevalence in Umtshezi Municipality for the Period April 2009 to October 2009 is 36.4%. The District is at 30.9%. Access to social welfare services still poses another challenge on the access to social services.  The Department of Welfare and population Development is working together with the Municipality in ensuring that such services are rendered to the local communities.  This is one of the priority areas for the Municipality.

The scourge of AIDS affects all the citizens of this country, mostly the youth. Umtshezi Local Municipality has realized that HIV/AIDS pandemic will have a devastating impact on its socio-economic development programs and formulated the HIV/AIDS council that was launched in 2007. This has led to the formation of HIV/AIDS development plan, which seeks to ensure that HIV/AIDS infection rates are lowered and that those who are affected and infected with the pandemic are given a necessary support.  The Municipality will embark on HIV/Aids programmes during the 2012/17 financial years that would contribute to the mitigation of this pandemic.

##### 3.5.2.3.3 SPORTS COUNCIL

The absence of sport and recreation facilities in the municipality has a direct relationship with crime and prevalence of HIV/AIDS among the youth. The facilities that exist are located only in urban settlements making them unreachable for the rural communities. There is a huge bias towards soccer and other sporting codes are not catered for.  The provision of facilities is a matter of urgency so as to keep the youth engaged and thus reduce crime incidents.  The youth need extra mural activities to keep them busy.  The youth can develop their talent and get to professional level.  The Departments of Education and Sports and Recreation are part of the IDP Forum as well as the service provider’s forum where these priority areas are debated at length and addressed to a certain extent by the relevant sector department.

##### 3.5.2.3.3 CEMETERIES

Some communities within the Municipality are still practicing on site burials as a cultural phenomenon and there is a general shortage of burial sites in the municipal area. There are negative environmental implications because of contamination of ground water. The land that has been used for cemetery purposes and it cannot be used for any other purposes. There needs to be intensive awareness campaigns so as to sensitize people about the importance of using clearly demarcated cemeteries as per National Water Act, Act No.36 of 1998 and KwaZulu – Natal Cemeteries and Crematoria Act, Act No.12 of 1996 require that suitable buffers be put in place as determined by a qualified professional. Uthukela District Municipality conducted the Cemetery Crematorium Identification Study and the findings are yet to be implemented.

Figure 13: Facilities

#### 3.5.2.4. Safety and Security

##### 3.5.2.4.1 Policing / Community Forums

There are Community Policing Forums in all nine wards, working together with the Chairperson of Safety and Security in the Municipality Councilor B. Sulleman we do observe changes at Umtshezi Municipality, our municipality has been identified as one of the municipalities where there is a lot political intolerance as per MEC Willies Mchunu’s (KZN Safety and Security) report,the forums are working closely with the SAPS in the affected areas.

##### Fire Protection

Annexure F

##### Traffic Management

There six fulltime traffic officers in the Municipality as a whole, there are four in the College who will complete by June 2014.We only have three examiners, four clerks and one Supervisor.

The daily duties of the traffic department is to concentrate and manage scholar patrols during school working days, control on CBD parking, attend to crashes, obstructions, deviation through town. The examiners concentrate in learners’ testing and vehicle testing. The management is also responsible for submission of fines.

##### National Building and Social Cohesion

Social Cohesion and Nation-Building.

Defining social cohesion

The department of Arts and Culture defines social cohesion as the degree of social integration and inclusion in communities and society, and the extent to which mutual solidarity finds representation among individuals and communities.

In terms of this definition, a community or society is cohesive to the extent that the inequalities, exclusions and disparities based on ethnicity, gender, class, nationality, age, disability or any form of distinctions that engender divisions distrust and conflict are reduced or eliminated in a planned and sustained manner. This, with community members and citizens as active participants, working together for the attainment of shared goals, designed and agreed upon to improve the living conditions for all. Hence the IDP plays this vital role in our proximities together with the people of uMtshezi across all cardinal points to plan as to how their budget should be utilized according to their needs.

Defining Nation-Building

Nation-building is the process whereby a society with diverse origins, histories, languages, cultures and religions come together within the boundaries of a sovereign state with a unified constitutional and legal dispensation, a national public education system, an integrated national economy, shared symbols and values, as equals, to work towards eradicating the divisions and injustices of the past; to foster unity; and promote a countrywide conscious sense of being proudly South African, committed to the country and open to the continent and the world.

Nation building in this sense, and in the context of South Africa, cannot be the perpetuation of hierarchies of the past, based on pre-given or ethnically engineered and imposed divisions of people rooted in prejudice, discrimination and exclusion. It calls for something else; that is a rethinking, in South African terms, of what social cohesion, linked to nation building, should be. It should, no doubt and in essence, be directed towards the practical actualisation of democracy in South Africa.

Accordingly, a nation is conceived as a social formation based on the unity and equality of its members consisting of the following shared and recognised attributes:

- Shared Origin and history

- An internationally recognised territory

- A unitary sovereign state

- A single judicial system

- Single public education system

- National recognised languages

- National recognised cultures

- National recognised religions

- Shared values

- Shared Symbols

- A shared national consciousness

In South Africa, the diverse cultures, languages and religions should not be seen as impediments to national unity given the statutory equality accorded to all citizens.

SOCIAL COHESION PROJECTS

- Community conversations/dialogues;

- Comments from these communities’ conversations are incorporated into the National Social Cohesion strategy and informed discussions in the National Social Cohesion Summit;

- The community conversations are an on-going project.

#### 3.5.2.5 Community Development with Special Focus on Vulnerable Groups

##### 3.5.2.5.1 Youth Development

Umtshezi Municipality has a current project for the Youth to equip them with skills in Carpentry, Plumbing, Masonary and Bricklaying. We have also involved the youth in sports where we conducted a successful 2013 Mayoral Cup event and currently we are working on introducing more sports code e.g Volleyball and Rugby. An Internship program for the graduates’ students is also on the way with Phelonong where the Municipality will host so Interns in order to equip them with work experience.

##### 3.5.2.5.2Development of People with Disabilities

A disability forum that had existed since 2006 was obliterated in 2013 hence a new committee was launched on the 03 May 2013.Since the establishment of the new committees numerous meetings have been held which have proved to be very productive.

The Municipality is actively involved in the development of people with disabilities and a number of concerns have been raised by the forum on behalf of all disabled people within Umtshezi Municipality.

The Municipality is currently doing well in the area of disability although there are challenges such as appropriate access for disabled people. Progress is traceable.

##### 3.5.2.5.3 Development of the Elderly

Umtshezi municipality is one of the Municipalities that was vigorous in launching its senior citizen forum within Uthukela District. This subsequently resulted in luncheon clubs being established almost in all wards. The municipality is actively involved in the development of elderly group as we promote Golden Wednesday in partnership with Department of Sports and Recreation on monthly basis. The Municipality also adhere to Age in Action’s Event Calendar and where expedient implement some of the events.

Three citizens within Umtshezi municipality have participated in as far as Provincial golden games of which one was eliminated and two proceeded to National Golden Games.it is apparent that the Municipality is playing an active and supporting role to Uthukela Department of Sports and Recreation which is the overseeing department in Senior Citizens programmes.

The Municipality has shown great progress over the years in the field of Development of Senior Citizens. Although the Municipality has a task to prelaunch most luncheon clubs within its jurisdiction due to eternal sickness or death of senior members, the wing of senior citizens is both functional and effective.

##### Development of Women

Umtshezi Municipality has various projects to develop women in the Municipality, working together with the LED Manager all women of Umtshezi are motivated to form co-operatives and they receive free training by DTI. The Izwi Labafelokazi (Widow Fellowship) was introduced at Umtshezi council in 2013, the councilors are willing to work hand in hand with these women.

##### People Affected By HIV / AIDS, Crimes & Drug Abuse, Etc.

The HIV/AIDS Coordinator worked closely with the ward committees to form LACs (Local AIDS Committees) successfully they were formed, the statistics is collected every month from the local hospital which work the programme with all local clinics at Umtshezi and Imbabazane local Municipality, The ARVs are successfully roll out though the hospital covers two Municipalities and the clinics in them.

Working with Operation Sukuma Sakhe we are able to profile community members affected and infected,a number of learners in our municipality are from child headed families and they are so much involved in drugs.

#### 3.5.2.6 Social Development SWOT Analysis

| STRENGTHS | OPPORTUNITIES |  |
| --- | --- | --- |
| - Adequate Available and allocated budget - Available programmes will develop the youth in terms Skills Development |  | - Employment opportunities for the youth - New business venture from skills development programme |
| WEAKNESSES |  | THREATS |
| - Low moral from the local youth because of faults information made available by Non Designated Persons - Un-employable youth due to High School Drop outs - Un employed youth |  | - Unrest the local youth due to the canter not being operational - Lack of resources e.g. Internet and telecoms - People to take advantage of the youth by provision of wrong information |

## Municipal Financial Viability and Management Analysis

### Financial Viability and Management Analysis

Umtshezi Municipality has recognized that to be successful, the IDP must be linked to a workable financial plan. The purpose of the five-year financial plan is to create the medium and long-term strategic financial framework for allocating resources through the municipal budgeting process and to ensure the financial viability and sustainability of the Umtshezi Municipality’s investments and operations.

The table below shows the Financial Viability and Management Plan:

| M U N IC IP AL F IN AN C IAL VIAB ILITY AN D M AN AG EM EN T |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Performance Objective | Weight |  | Key Performance Indicator | Baseline | Annual Target | Budget | Quarterly Targets |  |  |  |
|  | PO | KPI |  |  |  |  | Q1 | Q2 | Q3 | Q4 |
| To ensure sound Financial anagement Services in line with legislation · Reporting · Budgeting · Accounting |  |  | SCM Policy approved | Policy currently in use | Reviewed annually | Internal budget |  |  |  |  |
|  |  |  | Number of SCM Reports submitted | 4 reports are required. | 4 | Internal budget | 1 | 1 | 1 | 1 |
|  |  |  | % Improvement on the quality of Section 71 Reports | Section 71 reports needs improvement | 10% | Internal budget | 2% | 2% | 3% | 3% |
|  |  |  | % Improvement on the quality of Section 72 Reports | Section 72 reports need to be improved | 10% | Internal budget | 2% | 2% | 3% | 3% |
|  |  |  | Timeous and correct statement | Statements not always correct | 12 (monthly) | Internal budget | 3 | 3 | 3 | 3 |
|  |  |  | % Increase in customers satisfied about statements | 15% of clients are unsatisfied about the statements | 5% | Internal budget | 2% | 1% | 1% | 1% |
|  |  |  | Updated Indigent Register | Indigent Register compiled and approved | Monthly | Internal budget | x |  |  |  |
|  |  |  | % Increase in debt collection | 70% debt is collected | 15% | Internal budget | 5% | 5% | 3% | 2% |
|  |  |  | % Debtors database cleansing | Debtors database has duplicate records and very old “non-moving” records | 90% | Internal budget | 20% | 60% | 5% | 5% |

| M U N IC IP AL F IN AN C IAL VIAB ILITY AN D M AN AG EM EN T |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Performance Objective | Weight |  | Key Performance Indicator | Baseline | Annual Target | Budget | Quarterly Targets |  |  |  |
|  | PO | KPI |  |  |  |  | Q1 | Q2 | Q3 | Q4 |
|  |  |  | Investment and loans | Manual Investment and Loan Registers not in Venus and linked with General Ledger | 12 (monthly) | Internal budget | 3 | 3 | 3 | 3 |
| Render Accounting Services |  |  | Number of risk reviews | Risk assessment conducted | 4 | Internal budget | 1 | 1 | 1 | 1 |
|  |  |  | % Reduction in the number of VAT audit queries | Monthly VAT Returns with audit queries | 5% | N/A |  |  | 5% |  |
|  |  |  | % Reduction in the number of 2012/13 audit queries | Previous year audit queries not resolved | 50% | N/A |  |  | 25% | 25% |

#### 3.6.1.1 Capability of the Municipality to execute Capital Projects

INTRODUCTION TO SPENDING AGAINST CAPITAL BUDGET

The spending in terms of the capital budget was slow during year.  This was mainly due to the fact that there were amendments to contracts for capital projects as was mentioned under the grant expenditure information above.

Below is a table that highlights the expenditure :

The municipality has the capacity to execute Capital Projects since there is a Project Management unit situated within the PECS and Technical Departments as follows:

Technical Services:

| Position | Technical Expertise required |
| --- | --- |
| Director: Technical Services | Relevant Qualification: Civil Engineering / Electrical Engineering |
| Senior Manager: Civil Engineering | Relevant Qualification: Civil Engineering / Project Management |
| Senior Technician: Civil Engineering | Relevant Qualification: Civil Engineering / Project Management |

| Position | Technical Expertise required |
| --- | --- |
| Senior Manager: Electrical Engineering (DEVELOPMENT) | Relevant Qualification: Electrical Engineering / Project Management |
| Senior Manager: Electrical Engineering (PLANNING) | Relevant Qualification: Electrical Engineering / Project Management |
| Senior Technician: Electrical Engineering | Relevant Qualification: Electrical Engineering / Project Management |

Planning, Economic and Community Services

| Position | Technical Expertise required |
| --- | --- |
| Director: Planning, Economic & Community Services | Relevant Qualification: Town and Regional Planning / Development Studies / Community Development |
| Development Manager | Relevant Qualification: Project Management |
| Human Settlements Manager | Relevant Qualification: Housing / Project Management |
| Building Control Officer | Relevant Qualification: Building |

#### 3.6.1.2 Indigent Support (including Free Basic Services)

The Municipality is also focusing on the provision of free basic services to the indigent.  The indigent policy is in place and the register is updated regularly for this purpose.  However, there are still some challenges that are experienced in this area due to lack of human resources that could focus entirely on this function.  Regarding free basic electricity, the Municipality has signed a service level agreement with ESKOM to provide free basic electricity to those areas listed in the agreement.  At the moment there are backlogs reported in those areas that need to be addressed by ESKOM.  The Municipality is also providing alternative sources of energy in those communities where there is no electricity.  On Free Basic Water, Uthukela District Municipality has also entered into an agreement with the Local Municipality on this function.  Regarding Free waste removal, there are no programmes in place for this service. There is a funding, which is provided by National Treasury to manage the Indigent policy.

#### 3.6.1.3 Revenue Enhancement and Protection Strategies

- Ensuring accurate implementation of the Municipal Property Rates Act (MPRA): Proper implementation will ensure that all properties are valued at market related values and would result in increased revenue for the Municipality

- Parking meters or payment for parking in CDB: Parking in the CDB is identified as a problem and by implementing a system of ensuring that motorists pay for parking in the CBD, will generate revenue and alleviate the problem of vehicles being parked in the CBD the entire day and thus reduce the parking problem.

- Investing surplus cash to obtain interest: If all surplus cash is invested, additional income will be generated without much effort.

- Tariff Modelling: In terms of Circulars issued by the National Treasury, it is stated that by 2015, the Municipality would need to implement cost reflective tariffs.  If cost-reflective tariffs were implemented, it would mean that the Municipality would be able to recover costs incurred in the delivery of services.  In order to determine cost-effective tariffs, tariff modelling would have to be done.

Promoting tourism: By promoting tourism, additional revenue will be brought into the area thus stimulating economic growth.

#### 3.6.1.4 Municipal Consumer Debt Position

OUTSTANDING DEBTORS / ARREAR ACCOUNTS

There had been a large increase in the amount of outstanding debt as at 30 June 2013.  This is mainly attributed to the fact that the economic climate in the Umtshezi area is that some of the major businesses in the area are retrenching staff.  One company is currently in the process of retrenching approximately 186 employees.In addition to the above, many of the receipts from some of the other businesses were only received after the financial year.  This resulted in an increase in the outstanding debt.

It has been subsequently reported that many of the debtors in one of the suburbs in the area, are indigent.  Many of the debtors that were employed at the beginning of the financial year were subsequently unemployed and fulfilled the criteria of been classified as indigent on the municipal database.  The debtors have been included in the provision for debt impairment of R34,913,137 in the annual financial statements.

Below is a summary of the outstanding debt as at 30 June 2013:

#### Grants & Subsidies

The Division of Revenue Act contains allocations from National and Provincial, which allocations are recognized as Government Grants and factored as follows under the Medium Term:

#### 3.6.1.6 Municipal Infrastructure Assets & Maintenance (Q&M)

The asset management unit was in the Finance Department of the municipality for the 2013 financial year.  It consisted of the Asset Manager supported by two interns and a service provider, I-Chain, who are asset management specialists.The implementation of the new Grap standard relating to heritage assets meant that additional work had to be performed to value these assets.  It was established that the heritage assets of the municipality were made up of the two museums, one based in Estcourt, namely Fort Durnford, and the second museum in Weenen.  The contents of the museum had to be established and the municipality had chosen to apply the transitional provisions of accounting for these contents.  There were included in the Statement of Financial Position in the Annual Financial Statements at provisional amounts.During the year all assets were verified and it was found that assets with a net book value of R39,000 could not be verified.  These assets were investigated and Council had finally resolved to write off the assets.

Below is a table that summarises the net book values of the property, plant and equipment of the 2013 financial year:

Repairs and maintenance is critical to ensuring that infrastructure and all other assets are maintained.  Failure to maintain infrastructure leads to derelict assets that negatively affect service delivery and income generation for the area. We will make sure with budget that the percentage allocated for repairs and maintenance over the MTREF exceeds the Treasury guideline of 8%.

#### 3.6.1.7 Current & Planned Borrowings

| Actual Borrowings: Year -2 to Year 0 |  |  |  |
| --- | --- | --- | --- |
| R' 000 |  |  |  |
| Instrument | Year -2 | Year -1 | Year 0 |
| Municipality |  |  |  |
| Long-Term Loans | 0 | 10538857 | 8727956 |
| Long-Term Loans Finance Lease Obligation |  | 1811239 | 1 246 257 |

#### 3.6.1.8 Employee Related Costs (including councillor allowances)

| Description (2012/13) | Amount |
| --- | --- |
| Employee related costs | R56, 390, 941 |
| Remuneration of councillors | R4, 359, 576 |
| TOTAL | R60, 750, 517 |

#### 3.6.1.9 Supply Chain Management (SCM)

The municipality has developed its supply chain management policy in line with supply chain regulations.  The policy meets all the requirements as stated in the Municipal Finance Management Act, No. 56 of 2003.  The unit is has a Supply Chain Manager, one vacant Supply Chain Officer post and two Supply Chain Clerks.  The department also is capacitated by two finance interns and is supported by the KwaZulu Natal Provincial Treasury.

MFMA Act, SCM Regulations, municipal policy, PPPFA, govern our SCM Unit. The following are things that are required by law:

That the supplier of goods & services to the municipality must registered in the municipal database. To register there is a form that is obtainable from the municipal building at reception area, SCM Unit offices & on the municipal website.

Retainable document with the form are as follows:

Registration document such as CK, Original Tax clearance certificate, BBBEE Certificate, certified I.D. copies of the directors of the company &letter from the bank confirming the business account.

The company get registered on municipal database then our buyers invite suppliers to quote, receive quotations, evaluate quotations based on the specification, PPPFA & BBBEE.

The order is printed & faxed to the supplier to deliver goods or service to the municipality. The supplier must issue the delivery note when delivering there after the invoice/tax invoice must be send to our creditors department for payment.

Suppliers are requested not to deliver any goods or services to the municipality without receiving official purchase order.

Suppliers are requested to take orders from supply chain officials who are dully authorised by the accounting officer.

The supplier may tender for goods & services advertised by the municipality even if they are not registered on municipal data base.

### Financial Viability & Management: SWOT Analysis

| Strengths | Weaknesses |
| --- | --- |
| • After a period of financial strain, decline, and distress, the Municipality is now entering a period of stabilisation and recovery; and • The implementation of the Long-term Financial Plan for the Municipality. | • A limited rates base and high levels of demand for services; • A growing number of debtors; and • Under-spending against operations and maintenance budgets. |
| Opportunities | Treats |
| • A limited rates base and high levels of demand for services; • A growing number of debtors; and • Under-spending against operations and maintenance budgets. | - The gradual increase of outstanding debt remains a potential risk to the Municipality’s working capital, hence the possibility of service delivery delays; - The growing number of indigent households and the financial strain these places on the municipal budget; - The lack of forward planning in terms of procurement for services in relation to the capital budget; and - Under-expenditure against some conditional grants. |

## Good Governance & Public Participation Analysis

### National and Provincial Programmes

#### 3.7.1.1 NATIONAL PRIORITIES

The Umtshezi municipality endeavours to include and implement the national priorities as soon as possible. We have successfully implemented EPWP (job creation) and have dedicated an official to focus on AIDS and other diseases. We receive statistics from the Department of Health on Child Mortality, Maternal Death, HIV/AIDS and other diseases for monitoring and awareness purposes. We also as the municipality ensure gender equality and Women empowerments in terms of our employment policy.

#### 3.7.1.2 PROVINCIAL PROGRAMMES

As with the National Government, the Provincial Government should prepare Sectorial Guidelines and funding for the preparation of Sectorial Plans. The preparation of the Sector Plans and programmes and district programmes also needs to be co-ordinated and aligned.

#### 3.7.1.3 Batho Pele Principles

Umtshezi Municipality subscribes to the following Batho Pele Principles and a number of training sessions have been conducted for employees:

Providing information; Umtshezi Municipality subscribes to the following Batho Pele Principles and a number of training sessions have been conducted for employees:

Consultation;

Setting service standards;

Increasing access;

Ensuring courtesy;

Providing information;

Openness and transparency;

Redress; and

Value for money.

#### 3.7.1.4 Operation Sukuma Sakhe

The Umtshezi Municipality notes that this is a Premier’s initiative and will endeavour to be present at all relevant District and Local co-ordinated meetings to ensure that it is prioritised in our IDP.The Umtshezi Municipality Opration Sukuma Sakhe teamwork closely with the local and the district team lead by Mrs Thandeka Zulu to push the premiers initiative of Sukuma Sakhe.

### 3.7.2 Intergovernmental Relations (IGR) Structures Operating in Umtshezi

The municipality participates in some of the District IGR forums, which are functional. The Umtshezi Municipality also participates and fully co-operates in the activities of other spheres of Government. IGR structures include:

The District Intergovernmental Forum (DIF) or the Mayors Forum.

The District Technical Support Forum (DTSF) or the Municipal Manager’s Forum.

The uThukela District Mayor is the chairperson of the District Intergovernmental Forum and attends the KZN Provincial Premier’s Forum meetings.  Other IGR structures in the district include the following forums:

Planning Forum,  chaired by the Municipal Manager of Umtshezi;

Finance Forum, chaired by the Municipal Manager of Okhahlamba;

Corporate Forum; and

Infrastructure Forum.

### Municipal Structures

#### 3.7.3.1 Ward Committees

Ward Committees have been established in all nine wards,though some committees have been functioning well with their chairpersons which are ward concillors we do have problems in other wards. Attempts have been made to train these committees and  this was successful.  A budget has been allocated to revive and reconstitute these ward committees.The key purpose of ward committee is to get a broader input from the community in order to advise the council.Also to make sure that there is more current interaction linking the council and the community and to help the ward councillor with meeting and in turn-liase with the community.

#### 3.7.3.2 IDP Representative Forum

The forum will represent all stakeholders and will be as inclusive as possible. Additional organizations will be encouraged to participate in the forum throughout the process.

Represents the interests of their constituents in the IDP Process;

Provide an organisational mechanism for discussion, negotiation and decision making between the stakeholders including the municipality;

Participate in the process of setting up and monitoring “key performance indicators” in line with the “Performance Management Manual”.

#### 3.7.3.3. Executive Committee (EXCO)

Chairperson:

#### 3.7.3.4 Council

Umtshezi Municipality is a Council that comprises of 17 Councillors. The total of 9 Councillors are Ward Councillors and 8 are PR Councillors.

| NAME OF COUNCILLOR | WARD |
| --- | --- |
| BS Dladla | 1 |
| BA Dlamini | 2 |
| BD Dlamini | 9 |
| TC Dubazane | 7 |
| TG Duma | Proportional |
| RP Gericke | Proportional |
| E Lite | Proportional |
| SD Magubane | 3 |
| EM Majola | Proportional |
| ME Mchunu | Proportional |
| SM Mlambo | 5 |
| SC Mlele | Proportional |
| CJS Nunes | Proportional |
| B Sulieman | 6 |
| U Chetty | 4 |
| KA Vilakazi | Proportional |
| Z Zwane | 8 |

POLITICAL OVERSIGHT AND DECISION MAKING

Our Council is run professionally and all decisions are taken on an informed system based on legal prescripts guarding the institution.

#### 3.7.3.5 IDP Steering Committee

As part of the IDP preparation process, Council resolves to establish an IDP Steering Committee, which comprises Senior Managers to act as a support structure to the IDP Representative Forum or Ward Committees, the Municipal Manager and the IDP Manager. These structures are to continue functioning throughout the IDP Review Phase and after.

#### 3.7.3.6 Municipal Public Accounts Committee (MPAC)

The MPAC was constituted and it fully functional as per the requirement.

#### 3.7.3.7 Municipal Bid Committees

Municipal Bid Committees are functional and includes the following:

| ROLES OF THE BID SPECIFICATION COMMITTEE |  |
| --- | --- |
| Committee role | Key consideration |
| - Compile Specifications | - Specifications are written in an unbiased manner - Guard against the use of tight specification to limit competition - References to brand names, catalogue numbers or similar classifications should be avoided |
| - Determine evaluation criteria | - The evaluation criteria are aligned with the specification. |
| - Determine procurement method - Determine special conditions of contract |  |

Members:

Mr. F Shaik		: Chairperson

Mr. B Lite		: Member

Mrs. C Obrien		: Member

Mr. Y Sewraj		: Member

| BID EVALUATION COMMITTEE |  |
| --- | --- |
| COMMITTEE ROLE | KEY CONSIDERATIONS |
| - Evaluate bids received in accordance with specifications and the points system (Preferential Procurement Regulations) | The BEC must assess: - Each bidder’s ability to execute the contract; - Whether municipal rates and taxes and municipal service charges are not in arrears; - Consult National Treasury’s Register for tender/bid defaulters before making any recommendations. - Check with NT’s database that the recommended bidder is not prohibited/ restricted from doing business with the public sector. |

| BID EVALUATION COMMITTEE |  |
| --- | --- |
| COMMITTEE ROLE | KEY CONSIDERATIONS |
| - Report and recommendation to the BAC - Ensure compliance to bid policies and procedures | - Submit a report with recommendations regarding the awarding of the bid or any other related matter to the Bid Adjudication Committee |

Members:

Mr. EH Dladla		: Chairperson

Mr. HS Hlongwane	: Member

Mr. S Sithole		: Member

Mr. E Desai		: Member

Mr. S Bhagoparsad	: Member

Mrs. R Mayibasi		: Member

Mr. DV Khumalo	: Member

| BID ADJUDICATION COMMITTEE |  |
| --- | --- |
| COMMITTEE ROLE | KEY CONSIDERATIONS |
| - Must consider the recommendations and reports from the Bid Evaluation Committee and either (depending on the official written delegations): - make the final award; - make a recommendation to the AO to make the final award; or - make another recommendation to the AO on how to proceed with the relevant procurement | The BAC must ensure that: - All necessary bid documentation has been submitted; - Disqualifications are justified and valid and accountable reasons/motivations were furnished for passing over of bids; - Scoring has been fair, consistent and correctly calculated and applied; - Bidders’ declarations of interest have been taken into account; - Any other relevant facts which could affect the awarding of a contract. |

Members:

Mr. M Zulu		: Chairperson

Mr. HB Chotoo 		: Member

Mr. C Moodley		: Member

#### 3.7.3.8 Municipal Portfolio Committee

Umtshezi Municipality has the following portfolio committees:

| NAME OF PORTFOLIO COMMITTEE | CHAIRPERSON | MEMBERS |
| --- | --- | --- |
| Infrastructure, Housing, Town planning, Rural Development and Agrarian reform Committee | E Lite | BD Dlamini TC Dubazane SC Mlele B Sulieman |
| IDP, Finance, LED and Tourism Committee | BD Dlamini | E Lite B Sulieman BA Dlamini SM Mlambo |
| Sport, Gender, Vulnerable Groups, Health, Youth and Education Committee | SD Magubane | Z Zwane BS Dladla E Lite TG Duma EM Majola |
| Human Resource and Transformation Committee | TC Dubazane | SD Magubane E Lite SC Mlele KA Vilakazi |
| Safety and Security Committee | B Sulieman | BA Dlamini RP Gericke SC Mlele BS Dladla |
| Rules Committee | CJS Nunes | SD Magubane RP Gericke SC Mlele |
| Municipal Public Accounts Committee | VACANT | TC Dubazane SD Magubane RP Gericke SC Mlele |
| Local Labour Forum | E Lite | BS Dladla SD Magubane TG Duma |
| Executive Committee | BD Dlamini | BA Dlamini EM Majola |

#### 3.7.3.9 MAYORAL IZIMBIZO / ROADSHOWS AND STAKEHOLDER FORUMS

The Mayor participates actively in Road Shows and Izimbizo to discuss and approve the IDP and the allocated budgets with the communities.  The Representatives Forum also includes external stakeholders to ensure that there is contribution made by all stakeholders before the Municipality adopts the final IDP.

The area of focus for the 2012/2017 financial years will be to ensure that all relevant sector Departments attend the planned forums and participate effectively.  The Municipality hosts the Service Providers Forum which is aimed at bringing together all service providers within the Municipality to share with other stakeholders and input on the IDP.  Attempts were made in the previous years but there are those Departments that never attended the scheduled meetings.  However, there is support from the Departments such as the Department of Agriculture, Social Welfare and Transport.

### Audit Committee

The Umtshezi Municipality audit committee consists of the members listed hereunder and are required to meet at least 4 times per year as per the approved terms of reference in its Audit Committee Charter. Six meetings were held relating to the 2012/13 financial year wherein both Financial and Performance matters were discussed (a combined audit committee)

NAME OF MEMBER                                                    No. OF MEETINGS ATTENDED

Mr LB Van Der Merwe (Chairperson)                            6

Mr C Rautenbach                                                              6

Mr Z Zulu                                                                            5

AUDIT COMMITTEE RESPONSIBILITY

The audit committee reports that it has complied with its responsibilities arising from section 166(2) of the MFMA.

The audit committee reports that it has adopted appropriate formal terms of reference as its audit committee charter, has regulated its affairs in compliance with this charter and has discharged its responsibilities as contained therein.

THE EFFCTIVENESS OF INTERNAL CONTROL

The system of internal controls applied by the municipality over financial and risk management is generally effective, efficient and transparent. In line with the MFMA and the King III Report on Corporate Governance requirements, Internal Audit provides the audit committee and management with assurance that the internal controls are appropriate and identification of corrective actions and suggested enhancements to the controls and financial statements, and the management report of the Auditor-General, The control and deviations therefrom. Accordingly, we report that these matters require urgent attention of Management and Council, all of which will be included in our Action Plan for follow up by 31 January 2014 and monthly thereafter.

### Status of Municipal Policies

| HR Policies and Plans |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Name of Policy | Completed | Reviewed | Date adopted by council or comment on failure to adopt |
|  |  | % | % |  |
| 1 | Affirmative Action |  |  |  |
| 2 | Attraction and Retention |  |  |  |
| 3 | Code of Conduct for employees | 100 | 100 | Not yet adopted |
| 4 | Delegations, Authorisation & Responsibility | 100 | 100 | 23/07/2008 |
| 5 | Disciplinary Code and Procedures | 100 | 100 | Not yet adopted |
| 6 | Essential Services | 100 | 100 |  |
| 7 | Employee Assistance / Wellness | 100 | 100 |  |
| 8 | Employment Equity | 100 | 100 | 06/10/2005 |
| 9 | Exit Management |  |  |  |
| 10 | Grievance Procedures | 100 | 100 | 23/07/2008 |
| 11 | HIV/Aids |  |  |  |
| 12 | Human Resource and Development |  |  |  |
| 13 | Information Technology |  |  |  |
| 14 | Job Evaluation |  |  |  |
| 15 | Leave | 100 | 100 | 23/07/2008 |
| 16 | Occupational Health and Safety | 100 | 100 | 23/07/2008 |
| 17 | Official Housing |  |  |  |
| 18 | Official Journeys |  |  |  |
| 19 | Official transport to attend Funerals |  |  |  |
| 20 | Official Working Hours and Overtime | 100 | 100 | 23/07/2008 |
| 21 | Organisational Rights |  |  |  |
| 22 | Payroll Deductions |  |  |  |
| 23 | Performance Management and Development |  |  |  |
| 24 | Recruitment, Selection and Appointments | 100 | 100 | 23/07/2008 |
| 25 | Remuneration Scales and Allowances | 100 | 100 | 23/07/2008 |
| 26 | Resettlement |  |  |  |
| 27 | Sexual Harassment | 100 | 100 | 23/07/2008 |
| 28 | Skills Development | 100 | 100 | 13/06/2007 |
| 29 | Smoking | 100 | 100 | 13/06/2007 |
| 30 | Special Skills |  |  |  |
| 31 | Work Organisation |  |  |  |
| 32 | Uniforms and Protective Clothing |  |  |  |
| 33 | Other: |  |  |  |

Table 13: Status of Council Adopted Municipal Policies

### Municipal Bylaws

The workshop to present and workshop the Council on the new updated by-laws relating to Public Libraries, Public Roads, Property Encroachment, Storm Water Management, Cemeteries, Keeping of Birds and Animals, Pollution Control. Public Amenities, Parking, Pounds, Fire Safety and Nuisances were finally held on 20 June 2013 following two previous postponements. Council accepted the new by-laws at its meeting held on 26 June 2013.

The Street trading By-Laws were updated and accepted by the Council at its meeting held on 26 June 2013. The notice informing the public and calling for objections/submissions were placed in the local paper on 26 June 2013. The by-laws were also circulated to libraries and appear on the website. Presentations well be made to Ward Committee members at the IDP cluster meetings:

| By-laws Introduced |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Newly Developed | Revised | Public Participation Conducted Prior to Adoption of By-Laws) | Dates of Public Participation |  |  |
| PUBLIC LIBRARIES |  | IN PROGRESS | ADVERTS (10/07/2012) |  |  |
| PUBLIC ROAD | STREET TRADING | IN PROGRESS |  |  |  |
| PROPERTY ENCROACHMENT |  |  |  |  |  |
| STORMWATER MANAGEMENT |  |  |  |  |  |
| CEMETERY & CREMATORIA |  |  |  |  |  |
| KEEPING OF BIRDS & ANIMALS |  |  |  |  |  |
| POLLUTION CONTROL |  |  |  |  |  |
| PUBLIC AMENITIES |  |  |  |  |  |
| PARKING |  |  |  |  |  |
| POUND |  |  |  |  |  |
| FIRE SAFETY |  |  |  |  |  |
| NUISANCES |  |  |  |  |  |

# Combined SWOT Analysis

Prior sections of this report highlighted SWOT Analysis on each KPA. Following is a combined SWOT Analysis.

| Strengths | Opportunities |
| --- | --- |
| - Large biodiversity that inhabits an ecosystem landscape that has retained ecological functionality; - There are wetlands, important water yield areas and streamlined rivers - The presence of Priority Floral Species that prevents ecological degradation and further loss of vegetation - The municipality also contains the basis of the Tugela-Vaal water scheme and good water resources. - Indigenous planted at Wembezi Area as a response to reduction of Carbon Footprint - Municipal Participation in Greenest* - Municipality Competition (GMC) - Partnerships with other sector departments | - Limited benefits derived from international assets situated in the municipality - Lack of environmental compliance and enforcement; this weakens management of the natural environment - Lack of environmental management strategies and key interventions to monitor & manage biodiversity as well as ecological footprint - Lack of common planning between development planning and environmental planning - Lack of environmental education & awareness in municipal communities |
| - Opportunities | - Threats |
| - Improvement of biodiversity and hydrological integrity of aquatic systems - There is an opportunity for contributions to rural livelihood through employment opportunities in alien eradication operations as well as beneficiation of some species as they provide materials for the production of various household and saleable items such as building materials, crafts and furniture and fuel wood - Stakeholder alliance on environmental protection - Revenue generation through conservation of biodiversity - Mapping environmental sensitive areas | - On-going environmental degradation affecting the ecotourism, leading to a reduction of resources available for conservation aspects. - Low economic growth and increasing rate of unemployment in major economic sectors - Alien infestation may lead in marked declines in stream flow, transformation of vegetation composition & structure; alteration of patterns nutrient cycle & fire regime; also impact on Tourism & Agricultural production - Poor environmental management due to lack of environmental awareness - Industrialization and overpopulation - Illegal Dumping which pollutes wetlands - High potential agricultural land, potential forestry areas and areas likely to experience settlement expansion this poses greatest threats to identified Critical Biodiversity Areas (CBAs) - Limited benefits derived from international and national assets situated in the district. |

# VISION, GOALS, OBJECTIVES AND STRATEGIES

## UMTSHEZI VISION

BY 2016, UMTSHEZI MUNICIPALITY WILL BE A CHAMPION OF SUSTAINALBE GROWTH WITH AN AIM OF BUILDING BETTER COMMUNITIES.

### STRATEGIC OBJECTIVES

Following the stakeholder meetings and presentation of their needs, the municipal management and councillors held a series of strategic planning workshops where it was agreed that there are a set of challenges that faces the municipality.

In response to these challenges, the following Strategic Objectives were developed: taking into consideration the National Key Performance Areas, national and Provincial Priorities.

To run a functional Organisational Performance Management System

To improve institutional and organisational capacity

To improve municipal image

To facilitate  communication

To advance access to Basic Services

To promote  economic growth and development

To advance effective Public Participation

To improve the Municipal Audit opinion and Accountability

To improved budget implementation in the municipality

To promote efficient and credible strategic and spatial municipal planning

To promote sustainable protection and  development of the environment

To  improve response to Disasters

| STRATEGIC FRAMEWORK |  |  |
| --- | --- | --- |
| KPA | STRATEGIC OBJECTIVE/ OUTPUT | STRATEGIES |
| Municipal Transformation and Organisational Development | To improve institutional and organisational capacity | Develop and implement and effective organogram |
|  |  | Employ staff in terms of Umtshezi Municipality’s Equity Plan |
|  |  | Women employed by the municipality |
|  |  | Youth employed by the municipality |
|  |  | Disabled staff employed by the municipality |
|  |  | Develop a workplace skills plan |
|  |  | Budget spent on Workplace Skills Plan |
|  |  | Implement Batho Pele principles |
|  | To run a functional Organisational Performance Management System | Develop and implement and effective OPMS |
|  |  | Develop S57 Performance Agreements |
|  |  | Compilation of Annual Performance Report |
| Basic Service Delivery and Infrastructure | To advance access to Basic Services | Ensure access to Electricity |
|  |  | Providing access to solid Waste Disposal Services |
|  |  | Provision of Free basic services |
|  |  | Facilitate an improved road network |
|  |  | Provision and maintenance of community and public facilities |
|  |  | Facilitate the development of sustainable human settlements |
|  |  | Manage health facilities |
| Local Economic and Social Development | To promote economic growth and development | Facilitate a Safe and Secure environment |
|  |  | Identify and implement special programmes |
|  |  | Develop and capacitate SMMEs |
|  |  | Create jobs through LED initiatives |
| Good Governance and Public Participation | To advance effective Public Participation | Develop and implement effective public participation strategy |
|  |  | Create community awareness |
|  |  | Effective Stakeholder liaison |
|  | To improve the Municipal Audit opinion and Accountability | Improve Internal Auditing Function |
|  |  | Develop and implement anti-fraud strategy |
| Financial Viability and Financial Management | To improve budget implementation in the municipality | Revenue Enhancement |
|  |  | Financial Management |
|  |  | Budgeting and Reporting |
|  |  | Expenditure Control |
| Spatial Planning and Environment (cross cutting issues) | To promote efficient and credible strategic and spatial municipal planning | Review SDF |
|  | To promote sustainable protection and development of the environment | Review environmental management plan |
|  | To improve response to Disasters | Review Disaster management Plan |

# STRATEGIC MAPPING

Umtshezi municipality developed and adopted an SDF in terms of Section 26(e) of the Municipal Systems Act (32 of 2000).  The SDF is however outdated and are currently under review.

The primary aim of the SDF is to guide the spatial form and location of future developments within the municipality area of jurisdiction. Its objectives are as follows:

- Giving a spatial expression of the development vision and strategy as outlined in the IDP;

- Identifying areas where development should or should not go;

- Guiding the municipality in the coordination of development within its area of jurisdiction;

- Giving spatial effect to multi-sectoral projects identified in the IDP; and

- Promoting sustainable utilisation of natural resources.

  - Spatial Planning Principles

Umtshezi Municipality SDF is underpinned by normative principles reflected in various policy documents and pieces of legislation. The objective of the principles and norms is to influence directly the substantive outcomes of planning decisions, whether they relate to spatial development frameworks or decisions on land use change or development applications. The overall aim of the principles and norms is to achieve planning outcomes that:

- Restructure spatially inefficient settlements;

- Promote the sustainable use of the land;

- Channel resources to areas of greatest need and development potential, thereby redressing the inequitable historical treatment of marginalized areas;

- Take into account the fiscal, institutional and administrative capacities of role players, the needs of communities and the environment;

- Stimulate economic development opportunities in rural and urban areas; and

- Support an equitable protection of rights to and in land.

- In addition they promote:

- Accountable spatial planning, land use management and land development decision-making by organs of state;

- Channel resources to areas of greatest need and development potential, thereby redressing the inequitable historical treatment of marginalized areas;

- Take into account the fiscal, institutional and administrative capacities of role players, the needs of communities and the environment;

- Stimulate economic development opportunities in rural and urban areas; and

- Support an equitable protection of rights to and in land.

In addition they promote:

- Accountable spatial planning, land use management and land development decision-making by organs of state;

- Cooperative governance and wider information sharing in plan-making and implementation; and

- Maximum openness and transparency in decision-making.

The normative principles are focused on and correlated to the field of spatial planning, land use management and land development, but, as is the case with all principles and norms, need further actualization in specific, concrete contexts. Thus, in the practical implementation of the principles spatial planning, land use management and land development in Umtshezi will be guided by the following overarching concerns:

Integrated development, which is a key concern in legislation and policies dealing with Integrated Development Plans (Municipal Systems Act) and Land Development.

Sustainability, which emanates from Local Agenda 21 and in South African is, enforced through the National Environmental Management Act (NEMA) amongst others.

Equity, which implies equitable distribution of development, resources and opportunities.

Participation. The Municipal Systems Act is dedicated to the subject matter of public participation in municipal affairs. This principle promotes accountability and transparency in decision-making.

Order and amenity, which focuses mainly on the creation of safe and healthy environments suitable for human habitation. Current land use legislation (Natal Town Planning Ordinance) puts a greater emphasis on this concern.

Redress, which is mainly addressed in the Land Reform Program and various, associated pieces of legislation.  The main focus in this regard is top correct the wrongs of the past.

Efficiency, which deals mainly with, the creation of efficiently functioning environments scaled to the needs of the local people and role-players.

Good governance.

The principles and norms collectively form a vision for land use and planning in Umtshezi. They constitute a single point of reference, and an overarching coherent set of policy guides to direct and steer land development, planning and decision-making in land use so that outcomes thereof are consistent with the development objectives as outlined in the IDP.

  - ENVIRONMENTAL MANAGEMENT

    - Areas Suitable for Planning & Development

The areas considered suitable for development fall outside the environmentally sensitive areas, the areas with agricultural potential and the archaeologically sensitive areas. However, there may be other issues that may hamper planning and development in these areas, hence these are given as guides only and more detailed investigation will be needed at the planning/development stage to confirm the findings of this desktop study. Other factors such as geological/geotechnical, economic, social etc., may prevent planning and development.

Map 1: Environmental sensitive areas

Umtshezi Local Municipality is characterised by generally three topographical regions:

Areas above the escarpment located mainly to the west of Estcourt town, are generally flat and suitable for crop production and extensive grazing.

Areas with undulating terrain are located mainly along the southern and northern boundaries. They are dominated by thorn bush and characterised by erodible soils.

Areas such as Weenen valley are located within low-lying regions.

In Umtshezi Local Municipality, there are three conservation areas, including the Weenen Nature reserve, the New Formosa Nature Reserve and the Weenen Nature Reserve.  Some of the issues that may impact on the planning and development of the Umtshezi Municipality are given below.

Map 2: Conservation areas

    - Issues Impacting on Planning and Development

#### Low Cost Housing

Low cost housing problems, such as subsidence, sewage problems, collapsing of houses, (all issues especially evident within low cost housing developments), may occur because of:

Inappropriately located sites;

Impatient and environmentally insensitive developers;

Lack of understanding from developers regarding the role of environmental impact assessments in the site selection and application process (EIAs are often the last thought once all other studies have already been undertaken, developers are often not open to alternatives in terms of site selection or housing / development design or type);

Disregard for wetlands and endangered species;

Poor quality housing;

Health conditions (in wet areas – compromises sewage systems and cemeteries) and costs.

Because low cost housing sometimes merely Tran-locates the poor from a rural area to urban areas – where the housing is provided on smaller lots (preventing homeowners from growing food or keeping livestock), and where employment is not available to compensate, the poverty cycle, impact on the environment and crime may in fact increase as a result. More suitable housing sites (not in wet areas) with larger plots per home should instead be considered.

Increased development of informal housing hinders the development potential and aesthetic appeal of the region. Rural areas should be formalised and provided with sanitation and water.

Residents should be encouraged to remain in these areas where there is sufficient space to establish large gardens and keep livestock.

#### 6.2.2.1 Management of Water Resources

Incorrect citing of high-impact developments (such as low cost housing with poor sewage, wastewater and storm water management) in close proximity to wetlands, drainage lines, rivers and dams is resulting in water pollution. There is a need to protect water resources as a means to prevent waterborne diseases and ensure adequate supply of quality water for household consumption.

The sustainable use of ground water must be guaranteed, in order to ensure the quality and quantity of water for consumption and other uses in future. Siting of unsuitable developments in close proximity to known water sources and in sites of high ground water must be prevented.

#### 6.2.2.2 Veld Fires

Veld burning is recognised as an important veld management tool but should be applied according to strict scientific methods, considering factors such as veld type, carrying capacity (number of animals of a given type which the veld type can support), seasonal, climatic, soil and veld conditions.

Veld areas should only be burnt after full ecological consideration and evaluation, to provide informed decision making regarding hot or cold burns to control excess woody material.  Fire-breaks should be burnt in early to mid winter, depending on environmental conditions as broad strips allowing for effective fire management.

#### 6.2.2.3 Requirement for a Municipal Open Space System

A clearly defined municipal open space system (for the entire municipal area, but especially in the ‘urban’ areas of Estcourt, Weenen, and later in the more rural areas but still built up) is required for the:

Protection of wetlands, associated rivers, streams and catchments and areas of natural beauty.

These Open Space Plans should take into consideration the local EMPs and SEAs and the LUMS for the local and district municipalities.

#### 6.2.2.4 Rehabilitation of Damaged and Degraded Areas

Rehabilitation of damaged and degraded areas is now legislated and the municipality could begin to enforce this legislation by developing a whole new environmental branch: Very few new developments institute or apply rehabilitation plans, often where blatantly necessary.

Begin to enforce this legislation by developing a whole new environmental branch: Very few new developments institute or apply rehabilitation plans, often where blatantly necessary.

    - Protection and Conservation of Agricultural Land

As a general aim, the municipality together with the Department of Agriculture has a responsibility to protect agricultural land from development that leads to its alienation from its primary purpose or to diminished productivity. Any proposal for non-agricultural development on agricultural land is subject to an application made to, and assessed by, the Department of Agriculture in terms of the Sub-division of Agricultural Land Act, (Act No. 70 of 1970).  On the other hand, the municipality has a responsibility to implement wall-to-wall land use management system within its area of jurisdiction. This includes setting land aside for agricultural development purposes.

The traditional and widespread view that land is an almost limitless resource is a myth. Both availability and condition are under threat. Poor resource (veld) management such asresponsibility to protect agricultural land from development that leads to its alienation from its primary purpose or to diminished productivity. Any proposal for non-agricultural development on agricultural land is subject to an application made to, and assessed by, the Department of Agriculture in terms of the Sub-division of Agricultural Land Act, (Act No. 70 of 1970).  On the other hand, the municipality has a responsibility to implement wall-to-wall land use management system within its area of jurisdiction. This includes setting land aside for agricultural development purposes.

The traditional and widespread view that land is an almost limitless resource is a myth. Both availability and condition are under threat. Poor resource (veld) management such as overstocking, the development of land for settlement and other non-agricultural uses has led to the loss of significant areas of good agricultural land, and land degradation is now widely regarded as one of the greatest challenges facing rural Umtshezi.

Agricultural land in Umtshezi Municipality could broadly be divided into three main categories as follows:

Good agricultural land in located along the southern and western boundaries of the municipal area.  Patches of similar land are found along Umtshezi River and around Weenen.

- Moderate potential agricultural land is located generally in the area stretching from Estcourt in the south to Weenen in the north. Land with low agricultural potential is located in the low lying areas towards Indaka and Msinga Municipalities and falls largely within the Bloukrans River catchment area.

Protection of good agricultural land should be based on the following policy principles:

- Good quality agricultural land has a special importance and should not be built on unless there is an overriding need for the development in terms of public benefit and no other site is suitable for the particular purpose;

- When preparing, reviewing or amending planning schemes, the municipality will be expected to include provisions for protecting good quality agricultural land, regardless of the effect of market fluctuations on its viability;

- The preparation of planning schemes should include an evaluation of alternative forms of development, and significant weight should be given to those strategies which minimise the impacts on good quality agricultural land;

- The land Use Scheme should aim to minimise cases where incompatible uses are located adjacent to agricultural operations in a manner that inhibits normal farming practice. Where such instances do arise, measures to ameliorate potential conflicts should be devised;

- The land use scheme should provide for a hierarchy of agricultural zones based on the agricultural development potential and impact of non-agricultural activities on agricultural land. Non-agricultural activities such as agri-tourism, game farms with themed estates or lodges, resort developments, etc. should be located on land with moderate agricultural potential of development, and significant weight should be given to those strategies which minimise the impacts on good quality agricultural land;

- The land Use Scheme should aim to minimise cases where incompatible uses are located adjacent to agricultural operations in a manner that inhibits normal farming practice. Where such instances do arise, measures to ameliorate potential conflicts should be devised;

- The land use scheme should provide for a hierarchy of agricultural zones based on the agricultural development potential and impact of non-agricultural activities on agricultural land. Non-agricultural activities such as agri-tourism, game farms with themed estates or lodges, resort developments, etc should be located on land with moderate agricultural potential; and

- Agricultural potential should be used to establish agricultural zones in terms of the land use scheme, and provide for a continuum of agricultural zones from predominantly agriculture only zones to zones that allows for a mixture of agricultural and non-agricultural uses.

The following criteria may be used in this regard:

- High potential agricultural land should be used for mainly agricultural activities. However, limited non-agricultural uses may be permitted especially along the corridors and within the designated development nodes. Conservation should form part of a drive to protect and enhance the quality of agricultural land. Irrigated land along the river corridors should be protected equally;

Land with moderate agricultural potential provides an opportunity for the development of mixed agricultural, tourism and conservation uses. These include game farms, game reserves and feedlots.  As such, the proposed game reserve stretching from just outside Estcourt towards Weenen should be supported subject to the resolution of the land and social issues;

Low potential agricultural land should be subjected to conservation and low intensity agricultural uses. Most of it is degraded and prone to soil erosion; and

A detailed indication of agricultural activities undertaken in the area is indicated in the District Agricultural Development Strategy. It recommended that an agricultural development plan be prepared.

    - DESIRED DIRECTION OF GROWTH

The desired direction and nature of growth is indicated through the application of nodes and corridors. By using the system of nodes and corridors, and strategic areas for intervention, the SDF promotes functional integration between the N3 and the Estcourt Town, as well as Estcourt Town and Wembezi.

The following nodes and corridors have been identified:

Map 3: Nodes and corridors

## Desired spatial form and land use

The SDF clearly identifies areas where different land uses should be promoted. These include light industry and mixed use nodes at key road intersections, expansion of the residential areas along development corridors, commercial nodes in selected areas.

Areas that requires immediate attention in terms of infrastructure development are identified in the SDF in Wembezi Township, Estcourt Town and Weenen:

Wembezi where the main focus on the initiation and implementation of an urban renewal program.

Weenen where the main focus also on urban renewal and intensive urban agriculture.

Estcourt where the main focus is on land use integration and developing the town into

Areas that requires immediate attention in terms of infrastructure development are identified in the SDF in Wembezi Township, Estcourt Town and Weenen:

Wembezi where the main focus on the initiation and implementation of an urban renewal program.

Weenen where the main focus also on urban renewal and intensive urban agriculture.

Estcourt where the main focus is on land use integration and developing the town into an efficient sub-regional centre.

The SDF also identifies a number of settlements for upgrading and transformation into sustainable human settlements. These include Emabhanoyini, Thembalihle, etc.

An efficient sub-regional centre.

Map 4: SDF map

# IMPLEMENTATION PLAN

Stratplan session

| SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Key Challenge | Obj. Ref | Objective | Strategies | Performance Indicator |  | 5 Year Target |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Baseline | Yr 1 13/14 | Yr 2 14/15 | Yr 3 15/16 | Yr 4 16/17 | Yr 5 17/18 | Target & yr (if outside 5 yr period) | Budget (R) (‘000) | Source | Responsibility (In Municipality) |
| LOCAL ECONOMIC AND SOCIAL DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Key Challenge | Obj. Ref | Objective | Strategies | Performance Indicator | 5 Year Target |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Baseline | Yr 1 13/14 | Yr 2 14/15 | Yr 3 15/16 | Yr 4 16/17 | Yr 5 17/18 | Target & yr (if outside 5 yr period) | Budget (R) (‘000) | Source | Responsibility (In Municipality) |
| FINANCIAL VIABILITY AND SOCIAL MANAGEMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Key Challenge | Obj. Ref | Objective | Strategies |  |  | 5 Year Target |  |  |  |  |  |  |  |  |
|  |  |  |  | Performance Indicator | Baseline | Yr 1 13/14 | Yr 2 14/15 | Yr 3 15/16 | Yr 4 16/17 | Yr 5 17/18 | Target & yr (if outside 5 yr period) | Budget (R) (‘000) | Source | Responsibility (In Municipality) |
| COMMUNITY AND SOCIAL SERVICES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Key Challenge | Obj. Ref | Objective | Strategies | Performance Indicator | 5 Year Target |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Baseline | Yr 1 13/14 | Yr 2 14/15 | Yr 3 15/16 | Yr 4 16/17 | Yr 5 17/18 | Target & yr (if outside 5 yr period) | Budget (R) (‘000) | Source | Responsibility (In Municipality) |
| MUNICIPAL TRANSFORMATION & INSTITUTIONAL DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Key Challenge | Obj. Ref | Objective | Strategies | Performance Indicator | 5 Year Target |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Baseline | Yr 1 13/14 | Yr 2 14/15 | Yr 3 15/16 | Yr 4 16/17 | Yr 5 17/18 | Target & yr (if outside 5 yr period) | Budget (R) (‘000) | Source | Responsibility (In Municipality) |
|  |  | To improve institutional and organizational capacity | Develop and implement and effective organogram | Adopted Organogram |  |  |  |  |  |  |  |  |  |  |

# FINANCIAL PLAN

The application of sound financial management principles for the compilation of the Municipality’s financial plan is essential and critical to ensure that the Municipality remains financially viable and that municipal services are provided sustainably, economically and equitably to all communities.

The country is currently recovering from the downturn in the economy due to the recession in the last four years.  According to the National Treasury Budget Circular No 58, it states that the growth in the economy had slowed down from 4.5% to a revised 3.1% in 2011.  Unemployment has increased from 21.8% in 2008 to 25.7% in 2011.  As a result of this, a conservative approach needs to be adopted when forecasting future revenues and developing future financial plans.

Consumers who are the biggest contributor of the financial resources find themselves in a position where it is difficult for them to meet their daily needs.  It is therefore critical that in order to make the Integrated Development Plan (IDP) a credible document, that financial resources are obtained and allocated to prioritized projects in order to ensure that service delivery occurs.  By developing financial strategies and making use of the limited financial resources available, projects can be funded, service delivery would occur and consumer confidence and satisfaction would be achieved.

The municipality has put together a financial plan, in order to:

To ensure a close planning and budgeting link;

To inform municipal budgeting over tier;

To facilitate inter-governmental alignment with regard to capital requirements and sources of funding;

Assess financial management arrangement and financial strategy; and

To outline revenue and expenditure forecast.

The financial plan is an integral component of the IDP and addresses:

Establishing financial management systems and efficient, effective internal audit systems.

Funding availability over a 3- 5year planning period

The balancing of this limiting factor relating to income with objectives established in terms of the IDP.

## Municipal Budget Overview

The application of sound financial management principles for the compilation of the Municipality’s financial plan is essential and critical to ensure that the Municipality remains financially viable and that municipal services are provided sustainably, economically and equitably to all communities.

The Mayor is tasked with co-ordinating the processes for preparing the budget, reviewing the Integrated Development Plan (IDP) and budget related policies. The Accounting officer, as per S68 of the MFMA, is required to assist the mayor in developing and implementing the budgetary process.

| Financial Overview: Year 0 |  |  |  |  |
| --- | --- | --- | --- | --- |
|  |  |  |  | R' 000 |
| Details | Original budget | Adjustment Budget |  | Actual |
| Income: |  |  |  |  |
| Grants | 61028000 | 74508000 |  | 65408235 |
| Taxes, Levies and tariffs | 58140513 | 47140513 |  | 46236323 |
| Other | 179718871 | 178260036 |  | 173941400 |
| Sub Total | 298887384 | 299908549 |  | 285585958 |
| Less: Expenditure | 302260451 | 296351393 |  | 286303871 |
| Net Total* | -3373067 | 3557156 |  | -717913 |
| Operating Ratios |  |  |  |  |
| Detail |  |  | % |  |
| Employee Cost |  |  | 22% |  |
| Repairs & Maintenance |  |  | 3% |  |
| Finance Charges & Impairment |  |  | 1% |  |

## Three (3) Year Municipal Budget

Below is a table that shows the quarterly expenditure of each grant:

| Name of Grant | 1 Jul. 2011 to 30 Sep 2011 |  | 1 Oct. 2011 to 31 Dec. 2011 |  | 1 Jan. 2012 to 31 Mar. 2012 |  | 1 Apr. 2012 to 30 Jun. 2012 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Receipt | Expenditure | Receipt | Expenditure | Receipt | Expenditure | Receipt | Expenditure |
| Conditional |  |  |  |  |  |  |  |  |
| MIG | - 9,593,000 | 2,457,880 | 0.00 | 2,567,806 | -917,000 | 1,506,041 | R 0 | 2,772,182 |
| FMG | - 1,450,000 | 418,622 | 0.00 | 415,088 | 0,00 | 252,997 | R 0 | 363,292 |
| NDPG | 0.00 | 1,692,834 | 2,000,000 | 1,293,016 | -5,600,000 | 519,840 | R 0 | 1,024,299 |
| MAP | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0,00 |  | 0.00 |
| INEP | 0. 00 | 0.0 0 | 1,000,000 | 0.00 | 3,500,000 | 349,038 | R 0 | 0.00 |
| GOOD GOVERNANCE | 0. 00 | 0.0 0 | 0.00 | 0.00 | 0.00 | 0.00 | R 0 | 0.00 |
| STR | 0,00 | 0,00 | 6,220,000 | 0,00 | 1,000,000 | 392,554 | 0.00 | 1,235,930 |
| TOTAL | - 11,043,000 | 4,569,336 | -9,220,000 | 4,275,910 | -11,017,000 | 3,020,471 | R 0 | 5,395,703 |
| UNCONDITIONAL |  |  |  |  |  |  |  |  |
| HEALTH | R 0 | R 0 | R 0 | R 0 | -1,950,062 | 1,950,062 | R 0 | R 0 |
| EQUITABLE SHARE | -10,768,000 | 10,768,000 | -15,059,000 | 15,059,000 | 0,00 | 0.00 | R 0 | R 0 |
| MUSEUM | R 0 | R 0 | -250,000 | 250,000 | R 0 | R 0 | R 0 | R 0 |
| PROVINCIALISATION OF LIBRARIES | 851,597 | 851,597 | 0.00 | 0,00 | R 0 | R 0 | R 0 | R 0 |
| COMMUNITY LIBRARY SERVICE | 85,000 | 85,000 | 0.0 0 | 0.00 | R 0 | R 0 | R 0 | R 0 |
| MSIG | 790,000 | 790,000 | R 0 | R 0 | R 0 | R 0 | R 0 | R 0 |
| KWEZI DEV UPGRADING | R 0 | R 0 | R 0 | R 0 | R 0 | R 0 | R 0 | R 0 |
| TOTAL | -12,494,597 | 12,494,597 | -15,309,000 | 15,309,000 | -R 1,950,062 | 1,950,062 | R 0 | R 0 |
| GRAND TOTAL |  |  |  |  |  |  |  |  |

On receiving the audit opinion, annually, from the Auditor General, uMtshezi municipality council deliberates on the auditor’s report and provides the response to the Auditor General. Over and above this, mechanisms are put in place to prevent the same incidents recurring within the municipality.

The municipality has a functional Audit Committee, which also functions as a Performance Audit Committee. The Audit Committee deliberates on annual performance of the municipality and reports to Council. Thereafter Umtshezi full Council adopts the annual report.

The Umtshezi Municipality received an unqualified report for the Financial Year 2009/2010. The following is the full report of the auditor general together with the Umtshezi Manager’s responses.

ACTION PLAN FOR AUDIT QUERIES    UMTSHEZI MUNICIPALITY- 2011/2012

| Audit Report paragraph number/Finding | Action plan | Implementation / (Target) Date | Accountable Executive | Status |
| --- | --- | --- | --- | --- |
| 1. Commitments not completely disclosed in the annual financial statements | Training will be provided to all relevant Finance staff. A Contract Register will be compiled that will indicate all the commitments. Contracts and Work in Progress will be monitored monthly and updated on the Contract Register and the Venus system. | 15 February 2014 7 February 2014 | CFO, All directors CFO, All directors CFO, All directors | Commenced Commenced Commenced |
| 2. Accruals not completely disclosed in the annual financial statements. | Training will be provided to all relevant Finance staff. Retention creditor’s will be disclosed in the half-year and year-end financial statements; All monies received and not used will be accounted for as liability (Unexpended grants). All services rendered/goods received by the end of the reporting period will be accounted for. | 15 February 2014 10 February 2014 31 July 2014 31 December 2013 30 June 2014 | CFO CFO CFO CFO | Done for half year end |
| 3. Irregular expenditure of R12.8 million. | Council as per section 32 of the MFMA will investigate irregular expenditure of R12.8 million, as reported. Irregular expenditure of R12.8 million will be dealt as per the Council Resolution taken in this regard. KZN Provincial Treasury has seconded a resource to provide training and support to the SCM Unit, which will encompass ensuring inter alia that: We obtain three written quotations for all the goods or services purchased for less than R200 000; All goods or services procured above R200 000 and long-term are competitive bids; The preference point system is always applied in the procurement of goods and services above R30 000. Review all expenditure from 1 July 2013 to date, to identify other incidences of irregular expenditure to report to EXCO/Council to investigate and for them to be dealt with as per Council resolution. | 26 February 2014 1 December 2013 Ongoing | Council Municipal Manager (MM) MM CFO | To be done before year end Done |
| 4. Litigation in process against the municipality (Street vendor - R300,000) | This matter has been reported to Council and is currently followed up by management | Ongoing | MM | Ongoing |
| 5. Litigation in process against the municipality (Construction company – R2,76 m) | This matter has been reported to Council and is currently under investigation. | Ongoing | MM | Ongoing |
| 5. Material underspending of grants | A Procurement Plan has been compiled and will be monitored monthly and progress, delays reported to the MM/EXCO. All directors with projects will be required to motivate planning delays, and the CFO will report on SCM delays on project procurement/expenditure. A spending report will be submitted to the MM, CFO and EXCO monthly. | Immediate (30 June 2014) (Monthly by the 10th working day) | All directors | Done Done for July – December 2013 |
| 6. Material losses of electricity | A load monitoring system (SCADA) will be introduced; Metering system will be improved. Meter reading in June each year for consumer consumption will be aligned with the ESCOM reading as far as possible. Illegal connections will be monitored | 24 February 2014 8 December 2013 June 2014 Immediate (Ongoing) | Senior Manager: Electrical (Cyril Moodley) | Commenced |
| 7. Material impairment | Indigent management and debt collection process will be reviewed and improved, where possible. | Monthly | CFO | Done monthly |
| 8. Going concern Unspent grant monies not cash backed Material impairment of debtors | We will review our cash flow management and credit control processes to improve investments and debt collection. We will consider revenue enhancement strategies to maximize revenue opportunities. | Ongoing | CFO | Ongoing |
| 9. Achievement of planned targets: 10 out of 42 targets not achieved | Refer actions referred to in paragraph 14 above. Under-performance will be monitored on a quarterly basis and corrective measures will be implemented and monitored. | Refer to paragraph 14. Quarterly | Refer to paragraph 14. MM / All HOD’s Mayor PAC | Done Quarters 1 and 2 |
| Procurement and Contract Management |  |  |  |  |
| 10. Proc < R200k | Refer actions referred to in paragraph 8 above. | Refer Implementation/Target dates, Accountable Executive and Status in paragraph 8 above. |  |  |
| 11 Proc > R200k |  |  |  |  |
| 12. Awards to suppliers whose tax matters in order |  |  |  |  |
| 13. Preference points system not applied |  |  |  |  |
| Annual financial statements |  |  |  |  |
| 14. The financial statements submitted for auditing were not in all material respects in terms of section 122. (1) of the MFMA. Material misstatements identified by the auditors were not adequately corrected and were not supported by full and proper records, which resulted in the financial statements receiving a qualified opinion. | Interim financial statements for the six months ended 31/12/2013 will be compiled, which Internal Audit, will review, together with the supporting working papers. A financial statement preparation plan will be compiled. Internal Audit will also review the year-end draft financial statements together with the supporting working papers. Both the six-month and year-end financial statements will be submitted to the Audit Committee for review. | 2/01/2014 (28/02/2014 | CFO | Corrected in the interim financial statements |
| Expenditure management |  |  |  |  |
| 15. Reasonable steps not taken to prevent irregular expenditure as required by section 62.(1)(d) of the MFMA. | Refer actions referred to in paragraph 8 above. | Refer Implementation/Target dates, Accountable Executive and Status in paragraph 8 above. |  |  |
| Internal control |  |  |  |  |
| 16. Leadership: The MM did not exercise adequate oversight over financial reporting, compliance with procurement and expenditure management, and internal control. | Refer actions referred to in paragraphs 8 and 31 above. | Refer Implementation/Target dates, Accountable Executive and Status in paragraphs 8 and 31 above. |  |  |
| 17. Financial management: Management has not implemented adequate controls over the preparation of the financial statements to ensure that it complies with the accounting standards. Adequate review and monitoring was not exercised over supply chain management was not undertaken. | A checklist will be developed to monitor internal controls. | 28 February | CFO | Done |
| Investigations in progress |  |  |  |  |
| 18. Cheque fraud | This matter has been reported to Council and is currently under investigation | 28 February | CFO | Ongoing |
| 19. iKwezi Hostel | This matter has been reported to Council and is currently under investigation | 1 March | PECS Director | Ongoing |

## OTHER MUNICIPAL PROJECTS

### UMTSHEZI MUNICIPALITY MUNICIPAL CIVIL DEPARTMENT PROJECT REPORT 2013-2015

| DEPARTMENT | PROJECT NAME | DESCRIPTION | COMPLETION DATE | PROGRESS | WARD |
| --- | --- | --- | --- | --- | --- |
| CIVIL DEPARTMENT | Frere Hall | Construction of community hall | August 2013 | Completed | 08 |
|  | Frere Creche | Construction of crèche | September 2013 | Completed | 08 |
|  | Phofini Creche | Construction of crèche | August 2013 | Completed | 07 |
|  | Mshayazafe Hall | Construction of community Hall | November 2013 | Completed | 09 |
|  | Entunda Creche | Construction of crèche | 30 March 2014 | In Progress | 09 |
|  | Black Top Road rehabilitation (Wembezi) | Rehabilitation of roads | 30 June 2014 | In Progress | 03 & 04 |
|  | Black Top Rehabilitation (CBD) | Rehabilitation of roads | 30 June 2014 | In Progress | 04 |
|  | Black Top Rehabilitation (Collita) | Rehabilitation of roads | 30 June 2014 | In Progress | 04 |

### Umtshezi Municipality ELECTRICITY DEPARTMENT PROJECT REPORT – 2013 to 2015

| Component / Department | Project Name | Description | Completion Date | Progress | Ward |
| --- | --- | --- | --- | --- | --- |
| Electricity Bulk Infrastructure Upgrade Electricity Electrification Esigodlweni | Sub 57 Phase I | Upgrade of Main Substation including: 33 KV Cabling from O/H line to Sub 57 New 20MVA Transformer 33 KV switchyard including civil works and 33 KV equipment 11 KV panel extension etc | July 2013 | Transformer 20MVA completed ,expected delivery on Tuesday 18 February 2014 Civil Work completed | 3 |
|  | Sub 57 Phase II | Upgrade of Main Substation including: 33 KV Cabling from O/H line to Sub 57 New 20MVA Transformer 33 KV switchyard including civil works and 33 KV equipment 11 KV panel extension etc | Expected June 2014 | - 33 Kv Circuit Breakers delivered and installed - 33 Kv Cables delivered to site, to be installed by 28 March 2014 - VT Delivered and Installed - Claim for R 5,2 Million received | 3 |
|  | Wembezi Substation | Upgrade of Main Substation including: 15 MVA Transformer 33 KV switchyard including civil works and 33 KV equipment 11 KV panel extension etc | Expected September 2014 | Work in Progress |  |
|  | Esigodlweni Electrification Project Phase 1 | 751 Houses to be electrified | Date for completion 31 August 2012 316 Connections Completed in Phase 1 | Completed Phase 1 | 6 |
|  | Esigodlweni Electrification Project Phase 2 | 435 Houses to be electrified | 200 Connections to be Completed in Phase 2 Date for completion 31 July 2014 | ## Work in progress | 6 |
|  | Esigodlweni Electrification Project Phase 3 | 235 Houses to be electrified | 235 Connections to be Completed in Phase 3 Date for completion 31 July 2015 | ## Planning in progress | 6 |

OTHER ELECTRICITY PROJECTS ARE IN PROGRESS BY ESKOM IN THE FOLLOWING PLACES:

- Mthaniya

- Vumbu

- Msuluzi

- Ekuthuleni

- Clouston Farm

- Emantanjeni

- Phofini

- Embabani

HOUSING PROJECTS

| PROJECT NAME | FUNDER | VALUE | STATUS |
| --- | --- | --- | --- |
| Rensbergdrift | Dept of Human Settlements | R77 868 000.00 | Awaiting Tranche 1 approval |
| Mimosadale | Dept of Human Settlements | R77 868 000.00 | Tranche 1 approved. Busy with Tranche 2 – end August 2014 |
| Owl and Elephant | Dept of Human settlements | R41 114 000,00 | Implementing agent appointed – Tranche 1 approved |
| Msobetsheni | Dept of Human settlements | R41 114 000,00 | Implementing agent appointed – Tranche 1 approved |
| Cornfields | Dept of Human settlements | R165 000 000,00 | IA appointed – Conditional approval approved |
| Paapkuilsfontein | Dept of Human settlements | No budget yet | IA appointed. Busy with Stage 1. Awaiting for acquisition of land to be sorted out by DoHS |
| Mshayazafe | Dept of Human settlements | No budget yet | Waiting for authority to advertise project |
| Wembezi A Section | Dept of Human settlements | R75m | R75m approved in October 2013 waiting for Dohs to appoint IA. |
| Kwanobamba 1&2 | Dept of Human settlements | No budget yet | Project enrolled for rectification – waiting for NHBRC report |
| Nhlawe | Dept of Human settlements | No budget yet |  |
| Brewitt Park Phase 2 | Private/Dohs | FLISP |  |
| Thembalihle | Dept of Human settlements | No budget yet | IA busy with Stage 1. |

PROJECTS FROM PARKS

| PROJECT NAME AND AREA | FUNDER | COST | START & END DATE |
| --- | --- | --- | --- |
| Street Cleaning – Weenen, Estcourt and Wembezi | Department of Environmental Affairs | R 5 000 000 | 01 April 2014 – 31 December 2015 |
| Rehabilitation of existing parks 1.Wembezi park 1 and 2. Caravan park - Town | Department of Environmental Affairs | R 8 800 000 | 01 April 2014 – 31 December 2015 |

## SECTOR DEPARTMENT Projects

“To be confirmed after the sitting of the IDP Representative Forum”.

# ANNUAL OPERATIONAL PLAN (DRAFT SDBIP)

SUMMARY OF SDBIP

The Municipal Finance Management Act defines the SDBIP in Section 1 as follows: “a detailed plan approved by the Mayor of a Municipality in terms of section 53(1)(c)(ii) for implementing the Municipality’s delivery of services and the execution of its annual budget and which must include the following:

- projections of each month of-

- revenue to be collected by source; and

- operational and capital expenditure, by vote

- Service delivery targets and performance indicators for each quarter.”

In developing a good performance management tool for the Municipality, the IDP is drafted, the budget is drafted and the service delivery and budget implementation plan is developed in order to put into effect the budget.  The SDBIP is a monitoring and implementation tool that is the vital link between the Mayor, Council and Administration as it facilitates the process for holding management accountable for its performance.  The SDBIP quantifies the strategic objectives as highlighted in the budget to measurable outcomes.  It is then, that as a monitoring tool, the Mayor and Council are able to monitor the performance of the Municipal Manager.  The Municipal Manager can also monitor the performance of Senior Managers and the Community is able to monitor the Municipality.

The SDBIP is an important management tool as it allows for monitoring of performance and implementation of identified strategies and goals.  Adherence to this SDBIP will ensure that the objectives set out in the budget are achieved and hence the objectives and goals identified in the IDP will be realized, thus ensuring service delivery and that the Municipality meets the needs of the people.

The SDBIP is defined as a contract between the administration, council and community where the goals and objectives as set out by the Council are quantified and can be implemented by the administration of the Municipality.  National Treasury, MFMA Circular No. 13, diagrammatically depicts this relationship as follows:

IDP

Budgets

Monthly reports

Mid Year Performance Assessment

Annual Report

Employee Contracts and Annual Performance Agreements for the Municipal Manager and Senior Managers

SDBIP

Service delivery targets (by top layer and by ward)

Performance Indicators

Revenue and Expenditure by Vote

Council

Administration

## The SDBIP Process

The process for preparing and approving the SDBIP, as depicted in MFMA Circular No.13, is diagrammatically summarized as follows:

Strategic direction and priorities set by Council

Municipal Budget Policy Statement with indicative allocations for revenue and expenditure including initial tariff modeling, etc

Draft Dept SDBIP with proposed monthly and quarterly projections for the 1st year and annual projections for the two outer years rolled up into the draft SDBIP

Draft Budget with proposed annual measurable performance indicators and projections for the two outer years

Approved Budget

Approved SDBIP with monthly projections for revenue and expenditure and quarterly projections for service delivery targets and performance indicators

Approve annual performance agreements for Municipal Manager and Senior Managers

Strategic Outcomes

| KPA | STRATEGIC OBJECTIVES (IDP) |
| --- | --- |
| - Basic Service Delivery | Access to electricity |
|  | Access to solid waste disposal |
|  | Free basic services |
|  | Access to roads |
|  | Community and public facilities |
|  | Human Settlements |
|  | Managing health facilities |
|  | Safe and secure environment |
| - Municipal Institutional Development & Transformation | Human Resources Development |
|  | Batho Pele principles |
|  | Integrated development plan |
|  | Performance Management systems |
|  | Telecommunications |
|  | IT System |
| - Local Economic Development (LED) | Economic growth |
|  | Poverty alleviation |
|  | Tourism development |
|  | Development of prioritized groups and learnerships |
|  | Promotion of local economy |
| - Municipal Financial Viability & Management | Revenue enhancement |
|  | Financial management |
|  | Budgeting and reporting |
|  | Expenditure control |
| - Good Governance & Public Participation | Community awareness |
|  | Public participation |
|  | Stakeholder liaison |
|  | Policy development |
|  | Internal auditing function |
|  | Anti-corruption strategy |

Below are monthly estimates that were developed to ensure effective implementation of the service delivery and budget implementation plan MONTHLY PROJECTIONS OF REVENUE TO BE COLLECTED BY SOURCE

MONTHLY PROJECTIONS OF OPERATING EXPENDITURE AND REVENUE FOR EACH VOTE

MONTHLY PROJECTIONS OF CAPITAL EXPENDITURE FOR EACH VOTE

MONTHLY CASH FLOW PROJECTIONS BY SOURCE

# QUARTERLY PROJECTIONS OF SERVICE DELIVERY TARGETS AND PERFORMANCE INDICATORS

| IDP Indicator No. | IDP Reference | National KPA | Strategic Objective | Measurable Objective / Output | Performance Measure/Indicator (Unit 0f Measure) | Demand | Baseline (2012/ 13 estimates) | Backlog | Annual Target | Q1 | Q2 | Q3 | Q4 | Responsible Department | Financial Implications / Budget | Wards |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  | Jul - Sep | Oct - Dec | Jan - Mar | Apr - June |  |  |  |
| IDP 2013/001 |  | Municipal Transformation and Institutional Development | To provide efficient and effective Human Resource Services | An organogram reviewed annually | Date approved | 30 June 2014 | 30-Jun-13 | 0 | 30-Jun-14 | 0 | 0 | 0 | 30 June 2014 | Corporate services | 150 000 | All |
| IDP 2013/002 |  |  |  | Approved Workplace Skills Plan | Date approved | 30 June 2014 | 29-Jun-13 | 0 | 30-Jun-14 | 0 | 0 | 0 | 30 June 2014 | Corporate services | 150 000 | All |
| IDP 2013/003 |  |  |  | Percentage of a municipality's Budget actually spent on Workplace Skills Plan | Percentage spent | 100% | 100% | 0% | 100% | 0 | 0 | 0 | 100% | Corporate services | Skills Levy | All |

| IDP 2013/004 |  |  |  | The number of people from employment equity target employed in the three highest levels of management in compliance with a municipality's approved equity plan | Number of staff employed in terms of the Plan | 6 | 5 | 1 | 1 | 0 | 1 | 0 | 0 | Corporate services | Salary Budget | N/A |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| IDP 2013/005 |  |  | To conform to the Principles of Batho Pele | Customer satisfaction survey to be conducted | Survey completed quarterly by 30 June 2014 | 1 | 0 | 1 | 30-Jun-14 | 1 | 1 | 1 | 1 | Corporate services | 150 000 | All |
| IDP 2013/006 |  |  |  | Performance Management System in place | Date of approval | 30-Jun-14 | 28/11/2012 | 0 | 30-Jun-14 | 0 | 0 | 0 | 30 June 2014 | Office of the MM | 150 000 | All |
| IDP 2013/007 |  |  | To develop and implement the Municipal Turnaround strategy | Implementation of the National Municipal Turnaround Strategy - (10 point plan) | Date adopted | n/a | 27/02/2013 | n/a | 30-Jun-14 | 0 | 30/10/2013 | 0 | 0 | Office of the MM | 50 000 | All |
| IDP 2013/008 |  | Basic Service Delivery and Infrastructure Development | To provide access to roads | Kilometres of tarred roads established | No of Kilometres established | 50 km | 0 | 50 | 0 | 0 | 0 | 0 | 0 | Technical services | R 0 | All |
| IDP 2013/009 |  |  |  | Kilometres of gravel roads established | No of Kilometres established | 19.4KM | 2.4KM | 17KM | 2.4KM | 0 | 2,4 KM | 0 KM | 0 | Technical services | 2,420,000 | ward 5 & 9 |
| IDP 2013/010 |  |  |  | Kilometres of roads maintained | Kilometres (tarred) | 50 KM | 30 KM | 20 KM | 20 KM | 5 | 10 | 10 | 5 | Technical services | R 3,000,000 | All |
| IDP 2013/011 |  |  |  |  | Kilometres (gravel) | 103.54 | 35 | 68,54 | 21 | 4 | 5 | 6 | 6 | Technical services | (part of 7250000) | All |
| IDP 2013/012 |  |  |  |  | No of creches constructed by 30/06/2014 | 9 | 2 | 7 | 2 | 0 | 1 | 0 | 1 | Technical services |  |  |
| IDP 2013/013 |  |  |  |  | No of parks / play areas / recreational areas established | 26 | 10 | 15 | 2 | 1 | 0 | 1 | 0 | PECS | external | 1,2 |
| IDP 2013/014 |  |  | To provide access to electricity | Percentage of Households with access to basic electricity | Percentage connected | 12,151 | 12,151 | 0 | 100% | 100% | 100% | 100% | 100% | Technical services | 150 000 | All |
| IDP 2013/015 |  |  | To provide access to solid waste disposal services | Number of Households with access to solid waste removal | Percentage service | 15232 (100%) | 7567 (100%) | 0 | 8000 (100%) | 100% | 100% | 100% | 100% | PECS | 170 000 | All |
| IDP 2013/016 |  |  | To provide access to free basic services | Number of Households earning less than two times the government pension with access to free basic electricity | Percentage of households | 3362 | 3362 | 0 | 100% connection on all applications received | 100% connection on all applications received | 100% connection on all applications received | 100% connection on all applications received | 100% connection on all applications received | Electricity | In House | All |
| IDP 2013/017 |  |  |  | Number of Households earning less than two times the government pension with access to free solid waste removal | Number of households | 3362 | 3362 | n/a | 3362 | 3362 | 3362 | 3362 | 3362 | PECS | 150 000 | All |
| IDP 2013/02 |  |  | To provide access to housing | New houses constructed | Number of units | 8,450 | 0 | 8,450 | 0 | 0 | 0 | 0 | 0 | Department of Human Settlements / PECS | Internal Process | All |
| IDP 2013//018 |  |  |  | Application to DoHS for approval of subsidy allocation | Number of subsidies approved by 30/06/2012 | 8,450 | 0 | 8,450 | 5000 APPROVAL | 0 |  | 2000 Cond Approal and 1000 Stage 1 Approval | 2,000 Stage two Approval | Department of Human Settlements / PECS | DOHS Subsidy | 5,8 and 9 |
| IDP 2013/019 |  |  | To provide safe and secure environment | Law Enforcement | Number of road traffic violence fines issued | n/a | 1000 | n/a | 1500 | 375 | 375 | 375 | 375 | Corporate services | 150 000 |  |
| IDP 2013//020 |  | Local Economic Development | To stimulate economic growth | Promotion of new investment and expansion through the municipality's incentive policy | Number of new investments in the municipality | n/a | 2 | n/a | 2 | 0 | 1 | 0 | 1 | PECS | N/A | All |
| IDP 2013//021 |  |  |  |  | Number of new business expansions within the municipality | n/a | 2 | n/a | 3 | 1 | 0 | 1 | 1 | Office of the MM |  | All |
| IDP 2013/022 |  |  | To alleviate poverty | Poverty Alleviation Programmes undertaken | Number of programmes | n/a | 2 | n/a | 2 | 0 | 0 | 0 | 2 | Office of the MM | 30 000 | All |
| IDP 2013//023 |  |  | To promote the development of prioritised groups | Capacity building initiatives undertaken | Number of SMME/s trained | n/a | 0 | n/a | 2 | 0 | 1 | 0 | 1 | PECS | 10 000 | All |
| IDP 2013//024 |  |  |  |  | Number of Co-Opts trained | 10 | 0 | 5 | 10 | 5 | 2 | 2 | 1 | PECS | 10 000 | All |
| IDP 2013//025 |  |  | To promote the local economy | Jobs created through the municipality’s LED initiatives including capital projects | Number of jobs created | n/a | 43 | n/a | 126 | 84 | 42 | 0 | 0 | PECS | N/A | All |
| IDP 2013/026 |  |  | To ensure effective expenditure control | MIG Expenditure as a % of annual allocation | % spent | 100% |  | n/a | 100% | 25% | 25% | 25% | 25% | Technical services | MIG Grant |  |
| IDP 2013//027 |  | Good Governance, Community Participation and Ward Committee Systems | To ensure an effective internal audit function | Functional Audit /Performance committee | Number of meetings held | Functional Committee | Functional Committee | 0 | 4 | 1 | 1 | 1 | 1 | Office of the MM | 45 000 | All |
| IDP 2013/028 |  |  |  | Mayoral imbizo's | Number of Imbizo's | 4 | 3 | 0 | 4 | 1 | 1 | 1 | 1 | Office of the MM | 30 000 | All |
| IDP 2013/029 |  |  |  | Budget and IDP roadshows | Number of roadshows | 8 | 8 | 0 | 8 | 0 | 0 | 4 | 4 | Office of the MM / | 30 000 | All |
| IDP 2013/030 |  |  |  | Functional Ward Committees | Number of meetings held in all wards | 36 | 9 | 27 | 36 | 9 | 9 | 9 | 9 | Corporate services | 20 000 | All |
| IDP 2013/031 |  |  |  | Business Forum / Chamber of Commerce meetings | Number of meetings held | 4 | 3 | 1 | 4 | 1 | 1 | 1 | 1 | Office of the MM | 10 000 | All |

| IDP 2013/032 |  |  | To actively participate in IGR structures | Mayoral Forum | Number of meetings held | 4 | 1 | 4 | 4 | 1 | 1 | 1 | 1 | Office of the MM | 10 000 | All |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| IDP 2013/033 |  |  |  | Municipal managers' Forum | Number of meetings held | 4 | 1 | 3 | 4 | 1 | 1 | 1 | 1 | Office of the MM | 10 000 | All |
| IDP 2013/034 |  |  |  | CFO Forum | Number of meetings held | 4 | 0 | 4 | 4 | 1 | 1 | 1 | 1 | Finance | 10 000 | All |
| IDP 2013/035 |  | Municipal Financial Viability and Management |  | Audit opinion 2012/13 | Unqualified audit opinion | Clean audit | Clean Audit | N/a | Clean Audit with no Queries | 0 | Clean Audit with no Queries | 0 | 0 | Finance | 300 000 | All |
| IDP 2013/036 |  |  |  | Percentage of a municipality's capital budget actually spent on Capital projects identified for a particular financial year in terms of the municipality's IDP | Percentage | 100% | 100% | N/a | 100% | 25% | 25% | 25% | 25% | Pecs / Technical Services | In house | All |
| IDP 2013/037 |  |  | Financial Viability | Financial viability - debt coverage ratio | Ratio per MSA regulation of 2001 | n/a | 01:01 | n/a | 01:01 | 01:01 | 01:01 | 01:01 | 01:01 | Finance | 150 000 | All |
| IDP 2013/038 |  |  |  | Financial Viability - outstanding service debtors to revenue | Ratio per MSA regulation of 2001 | n/a | none | None | 01:01 | 01:01 | 01:01 | 01:01 | 01:01 | Finance | 150 000 | All |
| IDP 2013/039 |  |  |  | Financial Viability - cost coverage ratio | Ratio per MSA regulation of 2001 | n/a | 01:01 | n/a | 01:01 | 01:01 | 01:01 | 01:01 | 01:01 | Finance | 150 000 | All |
| IDP 2013/040 |  |  | To ensure compliance to SCM prescripts | Compliance with SCM regulations | Total number of contracts / rand value awarded to BEE Compliant suppliers | 100% | 100% | n/a | 100% | 100% | 100% | 100% | 100% | Finance | 170 000 | All |
| IDP 2013/041 |  |  |  |  | % compliance with SCM policy | 100% | 100% | 0 | 100% | 100% | 100% | 100% | 100% | Finance | 170 000 | All |

# ORGANIZATIONAL AND INDIVIDUAL PERFORMANCE MANAGEMENT SYSTEM

## Objectives of the Umtshezi Municipality Performance Management System

As indicated in the previous section, the Municipality’s OPMS is the primary mechanism to monitor, review and improve the implementation of its IDP and to gauge the progress made in achieving the objectives set out in the IDP. The system should fulfill the following objectives:

Facilitate increased accountability: The performance management system should provide a mechanism for ensuring increased accountability between the local community, politicians, the Municipal Council and the municipal management team.

Support municipal oversight: The performance management system should support oversight by the Council and community over the performance of the Executive Committee and Municipal Administration.

Facilitate learning and improvement: The OPMS should facilitate learning in order to enable the Municipality to improve delivery.

Provide early warning signals: It is important that the system ensures decision-makers are timeously informed of performance related risks, so that they can facilitate intervention where necessary.

Facilitate decision-making: The performance management system should provide appropriate management information that will allow efficient, effective and informed decision-making, particularly on the allocation of resources.

The objectives listed above are not exhaustive, but summarise the intended benefits of the system. These intended objectives should be used to evaluate and review the performance management system on a regular basis.

## Annual Performance Report of the previous Year

Attached as an Annexure to this document.

## Managing and measuring performance at various levels

Performance management can be applied to various levels within any organisation. The legislative framework as set out above provides for performance management at various levels in a municipality including organisational (sometimes also referred to as municipal, corporate or strategic) level, operational (also referred to as services, departmental or section/team level) and lastly, at individual level as. These levels are however integrated and interdependent on each other.

### Strategic (Organisational) Performance linked to the integrated development plan (IDP) of a municipality

At this level the performance of the municipality is measured and managed against the progress made in achieving the strategic objectives as set out in the integrated development plan (IDP) of the municipality.  This is done on the basis of key performance indicators and targets set for each of the IDP objectives of a municipality.  Given that an IDP has a five-year timespan the measures set at this level should be of a strategic and mostly long-term nature with an outcome and impact focus.

The measures set for the Municipality at organisational level must be captured in an organisational scorecard structured in terms of the preferred performance management model of the Municipality.

### Departmental Indicators linked to outputs in the Performance Agreements

The performance of individuals is measured against personal performance targets, which are set in accordance with job descriptions and their roles linked to the strategy of the municipality and the business plans (SDBIP’s) of the operational units (departments) at a municipality. At section 57 level the 2006 Municipal Performance Regulations for Municipal Managers and Managers reporting directly to Municipal Managers has put in place a legislative framework for linking the individual performance of section 57 Managers to the strategy and operations of a municipality.

By cascading performance measures from organisational to operational to individual level, both the IDP and the SDBIP form the link to individual performance management. This ensures that performance management at the various levels relate to one another, which is a requirement of the 2001 Municipal Planning and Performance Regulations. The MFMA specifically requires that the annual performance agreements of managers must be linked to the SDBIP of a municipality and the measurable performance objectives approved with the budget.

### Individual Performance linked to OPMS and the individuals key performance areas and job descriptions

The validity of the strategy of the municipality and the extent to which it is successfully implemented is also measured and managed at operational (sometimes also referred to as departmental) level. At this level this is achieved by measuring the progress made with service delivery and implementing the budget of the municipality through service delivery measures and targets captured in the annual service delivery and budget implementation plan (SDBIP) of a municipality. Given that a SDBIP has a one-year timespan the measures set at this level should be of a operational and short to medium-term nature with an input (budget) and output (service delivery) focus.

# Annexures

| NO | SECTOR PLAN | COMPLETED? Y / N | ADOPTED? Y / N | ADOPTION DATE | DATE OF NEXT REVIEW |
| --- | --- | --- | --- | --- | --- |
| 1 | Disaster Management Plan | The Plan is outdated and currently being reviewed. It should be review before end of June 2014. | Y | 2010 | JUNE 2014 |
| 2 | Spatial Development Framework | The Plan is outdated and currently being reviewed. It should be review before end of June 2014. | Y | 2008 | JUNE 2014 |
| 3 | Integrated Waste Management Plan | The Plan is outdated and currently being reviewed. It should be review before end of June 2014. | Y | 2010 | JUNE 2014 |
| 4 | Local Economic Development Strategy | The Plan is outdated and currently being reviewed. It should be review before end of June 2014. | Y | 2012 | JUNE 2014 |

ANNEXURE A: SDF

ANNEXURE B: EMPLOYMENT EQUITY PLAN

ANNEXURE C: AG COMMENTS

ANNEXURE D: Annual Performance Report

APPENDIX B - CONTACT DETAILS

UMTSHEZI MUNICIPALITY

PHYSICAL ADDRESS:		VICTORIA STREET

ESTCOURT

3310

POSTAL ADDRESS:			P.O. BOX 15

ESTCOURT

3310

WEBSITE:				www.mtshezi.co.za

MAYOR:				036 342 7807

mayor@mtshezi.co.za

MUNICIPAL MANAGER :		036 342 7801

municipalmanager@mtshezi.co.za

IDP MANAGER		             036 342 7800

082 255 6654

vilakazit@mtshezi.co.za/

PREPARED BY:

IDP MANAGER, UMTSHEZI MUNICIPALITY, VICTORIA STREET, ESTCOURT, 3310

ANNEXURE “A”

SPATIAL DEVELOPMENT FRAMEWORK

UMTSHEZI SPATIAL DEVELOPMENT FRAMEWORK:

EXECUTIVE SUMMARY

- Introduction

The Spatial Development Framework is a principal spatial planning instrument which guides and informs all planning, land management, development and spatial decision-making in a municipality. It aims to create a spatial interpretation of the strategies and projects already contained within the IDP. The main purpose of the SDF is to guide the form and location of future spatial development within a Municipal area in order to address the imbalances of the past. Its attributes are as follows:

As the SDF is a legislative requirement it has legal status and it supersedes all other spatial plans that guide development at local government level.

The SDF will enable the municipality to manage its land resources effectively in a sustainable manner.

Through the SDF, the municipality is able to develop and implement appropriate strategies and projects to address spatial problems.

In addition, the SDF will promote effective use of scarce land resources, speed up delivery of spatial bound projects and services, and help attract additional external funds where it is needed, strengthen democracy and institutional transformation, promote intergovernmental coordination on spatial issues, and provide guidance to more detailed Land Use Management Systems.

- Umtshezi Municipality

Umtshezi Municipality is located in the midlands area of KwaZulu-Natal approximately 200km west of Durban along the N3. Umtshezi Municipality is bordered on its south-eastern portion by the Mooi Mpofana Municipality, Msinga Municipality on its eastern portion, Indaka Municipality on its north-eastern portion, both by Emnambithi and Okhahlamba Municipalities on its north-western portion and Imbabazane Municipality on its south-western portion.

The Municipal boundaries are not just administrative, but are also intended to promote social and economic development. Other key characteristics of the area include the following:

At a provincial scale, Mtshezi Municipality is located along the foothills of the Drakensburg Mountain. The N3 rums through the municipal area and almost divides it into two.

The area also has a rich heritage and sites of historical significance. As such, it fall within two tourism regions.  Estcourt is the only major town in the area and provides service to areas beyond the municipal boundaries, particularly Ntabamhlophe and Loskop, which forms part of Imbabazane Municipality.

The other small town is Weenen, which also has a catchment beyond the municipal boundaries including portions of Msinga Municipality.

It forms part of Uthukela River catchment through Bushman’s River and Umtshezi River and is dominated by commercial farmlands.

- Alignment with National, Provincial and District Spatial Initiatives

  - National Development Plan Vision 2030

The NDP recalls that the overarching national challenges are that there are too few people who work, poor standard of education for black learners, poorly located infrastructure, spatial pattern that excludes the poor from fruits of development. In addition the economy is overly and unsustainably resource intensive, failing public health system, uneven and often poor quality public service. It identified strategies for long term (2030) development intervention which covers the following key areas:

Economy and employment.

Economic infrastructure.

Transitioning to a low carbon economy.

Inclusive rural economy.

Positioning South Africa in the World.

Human Settlements.

Improving education, innovation and training.

Promoting Health.

Social Protection.

Building safer communities.

Building a capable state.

Building accountability and fighting corruption.

Transforming society and uniting the country.

The NDP does not make any specific reference to Umtshezi; however there are two projects that have been proposed within KwaZulu-Natal which has implications for development within Umtshezi. These are the development of Durban to Johannesburg Trade Corridor as well as Maputo Corridor (trade route connecting north-eastern South Africa, Swaziland and south-western Mozambique) this is intended to open up markets.

  - The New Growth Path

The New Growth Path identifies areas where employment creation is possible, both within conventional economic sectors and in cross-cutting activities. It thus identifies “fostering rural development and regional integration” as one of the five key job drivers. The other four are:

Substantial public investment in infrastructure.

Targeting more labour-absorbing activities across the main economic sectors - the agricultural and mining value chains, manufacturing and services.

Taking advantage of new opportunities in the knowledge and green economies.

Leveraging social capital in the social economy and the public services.

A critical element of the New Growth Path is to ensure that the drivers leverage and reinforce each other based on their inter-linkages.

It further notes that while urbanisation will continue, a significant share of the population will remain in rural areas, engaged in the rural economy. As such, enhancing rural employment in Amajuba requires the preparation of a spatial perspective that sets out the opportunities available and the choices that have potential to form the basis for aligning government spending, infrastructure and housing investment and economic development initiatives.

  - Provincial Spatial Development Vision

The provincial spatial development vision is outlined in a document called Provincial Spatial Economic Development Strategy which is a contribution towards the Provincial Growth and Development Strategy (PGDS). This strategy recognizes the strategic location and potential of Umtshezi Municipality, and acknowledges that the area has potential for tourism and agricultural development.  It identifies Estcourt as a tertiary node (a centre which should provide service to the sub-regional economy), and two corridors linking Estcourt with other centres within the province:

Existing corridor, which is essentially the N3.

Tourism corridor linking Estcourt with Greytown and beyond.

PSEDS calls for a developmental approach to the land reform program so as to prevent the loss of agricultural land and manage impact on the agricultural and tourism sectors. It also requires the municipality to consider the economic realities of the emerging farmers when developing systems and procedures for the implementation of the Municipal Property Rates Act (MPRA). It is therefore, important to clarify the role of Umtshezi Municipality generally and Estcourt in particular in the provincial space economy.

  - District Spatial Development Vision

Umtshezi Municipality accounts for at least 19% of the total district area and accommodates about 10% of the district population. Estcourt/Wembezi is the second largest urban area in the district. Its threshold extends beyond Umtshezi Municipal boundaries to include almost the whole of Imbabazane Municipality and portions of Okhahlamba Municipality. This document refers to this as the Greater Estcourt Functional Region.

The district corridors that runs through Umtshezi serve as access routes to the tourist areas such as Ukhahlamba-Drakensburg Park.

- Spatial Analysis

  - Population Distribution and Density

Umtshezi Municipality population is estimated at 59 822 individuals or 13 965 households. This marks an increase of about 4.7% from the situation in 1996. It is spread unevenly among the seven municipal wards with ward 6 being the most populated ward.

Population density is generally low with most of the urban centres and major rural settlements having between 80 and 285 households per km2. However, pockets of relatively higher density settlements with households ranging between 285 and 614 households per km2 have developed in the outskirts of Wembezi and Estcourt. Unless growth and spread of these settlements is controlled, they are likely to degenerate into slums.

  - Access to Basic Services

Generally, Umtshezi is well provided with basic services. However, the growth of peri-urban settlements outside Estcourt has led to an increase in the number of poorly serviced households. These settlements, particularly Emabhanoyini and Rensburg Drift are increasing at a fast rate. Other areas that experience service backlog include the following:

Wembezi Township where there is a higher concentration of the people.

Thembalihle and Cornfields, which developed because of the land reform program.

Weenen where the quality and condition of infrastructure has deteriorated.

  - Access to Basic Services

Spatial structure of Umtshezi Municipality has been highly influenced by apartheid spatial planning policies, demarcation of municipal boundaries and reflects a highly fragmented pattern with the following features:

Location of Wembezi about 30km away from Estcourt.

Separation of land use such as residential, industrial and commercial.

Former black only areas located away from areas of opportunity.

  - Current Land Use

Current land use pattern has evolved in response to the settlement pattern, the natural environment and regional access routes. The following broad land use categories are found in Umtshezi Municipality:

Urban nodes are Estcourt, Wembezi and Weenen. Each of these plays a different role in the space economy.

A sizeable portion of the municipal area comprises commercial agricultural areas.

While there are no proclaimed Traditional Authority Areas within Umtshezi, there are several areas of dense rural settlement.  They include settlements such as Frere, Chiveley, Cornfields and Thembalihle.

Conservation areas include nature reserves (namely the Weenen, Wagendrift and Moor Park Nature Reserves), game farms and heritage sites.

  - Land Use Control

Umtshezi Municipality has developed a wall-to-wall Land Use Management Systems (LUMS). However, only the Estcourt and Weenen Town Planning Schemes (TPS) are currently being implemented.

  - Spatial Economy

A review of a Local Economic Development Plan for Umtshezi Municipality reveals that the area is supported by three main economic sectors, namely:

Tourism, which centres on the strategic location of the area in relation to Ukhahlamba-Drakensburg Mountain, the proposed Ngongola Game Reserve and the game farms currently found in this area, Weenen Nature Reserve and Wagendrift Dam.

Commercial and industrial activities found mainly in Estcourt town. Estcourt is a hub of commercial activity developed with many chain retail stores as well as local businesses. It serves as a sub-regional commercial centre with a threshold that transcends the municipal boundaries to include areas such as Ntabamhlophe and Loskop located in Imbabazane Municipality.

Agricultural land, which ranges in production potential. Areas with high production potential are concentrated to the south of Estcourt Town and around Weenen.

  - River Catchment Areas

Umtshezi Municipality is a major contributor to the provinces water supply and play a major role in the agricultural and industrial sectors of the economy in KZN.  Three of the rivers in the province flow through the municipality area, namely:

Boesman River,

Bloukrans River,

Sikhehlenga River, and

Uthukela River

  - Biodiversity

The Umtshezi Municipality is rich in biodiversity. The western and southern portions of the municipality are particularly high in species diversity and habitats. The eastern parts in particular and portions of the central areas of the municipality have intermediate sensitivity to species diversity. In the central parts and areas centrally placed towards the north, species diversity and communities tend to be irregular with some areas having intermediate sensitivity and others having low sensitivity.

Majority of the municipality is accorded very low irriplaceability values. Areas considered as initially excluded correspond with those areas of low irriplaceability values. This implies that development planning in these areas is not likely to infringe significantly on biodiversity conservation issues. However, care needs to be taken in planning infrastructure in particular and developments that are likely to take up large extends of land in areas that are labelled as negotiated reserves especially in areas around Weenen and north east of Colenso.

  - Conservation

There are three main conservation areas in Umtshezi, namely:

Weenen nature reserve, which offers a number of attractions including the following game viewing, hide and waterhole, vulture feedings site, self-guided trails and picnic sites.

New Formosa Nature Reserve. This small nature reserve is located to the west of the R102 as it leaves Estcourt to the South. Facilities at this reserve are limited, although the reserve has a number of nature trails.

Wagendrift Nature Reserve.

  - Land Reform

The implementation of the land reform program in Mtshezi Municipality has progressed very slowly. The area is characterised by a relatively large number of complex and overlapping labour tenant claims and land restitution claims. Land redistribution program has delivered just more than 21000ha while the land restitution is hovering at about 114934ha. Labour tenant program has delivered about 7000ha.

- Development Nodes

  - Estcourt

The town has developed in line with a typology common in most towns and cities in South Africa wherein the structure relates to a central core in the central business district (CBD) with several major access and/or exit routes radiating outwards. In Estcourt, these occur in the form of the east-west and north south axis linking different parts of the town through the city centre. Linkage back to the N3 is significant for regional and provincial integration as the N3 is identified in the NSDP and the PSEDS as a development corridor of national and provincial significance.

Estcourt is a typical apartheid town characterised by the following spatial patterns

Low-density sprawl, which is fuelled, among other, values of suburbia, which promotes large plots as an image of good urban living.

Historical separation of land uses, urban elements, races and income groups.

Spatial fragmentation with land use pattern resembling a series of relatively homogenous blobs of different uses tied together by high-speed transport routes.

Dual character of the CBD with one part being well developed and well maintained while down town is characterised by urban decay, grime and deteriorating quality of infrastructure.

Fragmented open space system.

  - Wembezi

Wembezi Township was developed on Ingonyama Trust land (former KwaZulu Government area) to accommodate black people working in Estcourt and forcefully removed from Kwezi Township which was located just outside Estcourt. It is generally well provided with social infrastruture (although most of it requires maintenance annd upgrading), and has the basics to become a sustainable human settlement. With the exception of local convenient shops, the area is poorly developed with commercial facilities,  thus forcing local residents to undertake most of their shopping activities in Estcourt. Nevertheless, there are huge opportunities for commercial development given the lcoation of Wembezi in relation to expansive rural settlements that form part of Imbabazane Municipality.

Wembezi can broadly be divided into four development areas or precincts, namely

The original township area characterised by the four-roomed dwelling units developed under apartheid past.

Middle income housing area located across the road from the original township.

Section C that has recently been upgraded in terms of the low housing program of the Department of Housing.

Rural settlement located to the west of Section C. A large portion of this area is situated in a wetland.

  - Weenen

Weenen performs a range of functions. It is a residential area to those who live in and around the town, a service centre for those who access a variety of services in the area, and business area to those whose business operations are based in town. Its administrative functions are now limited to a few government departments that still have offices in the area.

The village, which is the main urban area.

The area of Weenen could be divided into four main development areas as follows

KwaNobamba, which was established in the 1960s as a temporary emergency camp for people, evicted from the neighbouring farms.

Weenen town in surrounded by about 200 agricultural properties, which is indicative of the importance of agriculture in the local economy.

A small mixed land use node is located to the south the town centre.

Expansive agricultural land with limited potential and located almost around the town.

- Settlements

Major settlements found in Umtshezi Municipality area as follows:

Cornfields;

Thembalihle;

Frere;

Cheverly;

Mimosa;

Emabhalonini

Rensburg Drift

- Key Issues and Inflluences

Future spatial transformation of Umtshezi Municipality will be shaped by a number of factors and influences. Although these are a function of different sectors including social, economic, physical and environmental, they can broadly be categorised as follows:

Spatial development opportunities associated with strategic location of the area in relation to the national and provincial development corridors and focus areas, as well as the availability of well located land for commercial, industrial and tourism related developments.

Spatial development constraints which includes unfavourable slope, high representation of areas with low agricultural potential and spatial fragmentation and separation of places.

Spatial patterns and trends which includes development of settlements on agricultural land arising from the implementation of the land reform program.

- Concept Plan

  - Municipal Development Vision

Umtshezi Municipality SDF is a strategic document that gives a spatial translation to the development vision and program as outlined in the IDP. Umtshezi Municipality development vision was developed as part of the Integrated Development Planning process in line with the requirements of the Municipal Systems Act. The vision commits the municipality to sustainable development and the creation of a safe environment.

The attainment of this vision requires the municipality to facilitate the development of a spatial system that:

Is sustainable from a social, economic, financial, physical and institutional perspective;

provides for an efficient movement system, use of scarce resources and decision-making processes;

Promotes integrated development; and

Equitable access to development opportunities.

Such a spatial system will create an environment conducive to economic development and growth. It will promote social and economic development and contribute to the achievement of the development objectives as outlined in the IDP.

  - Spatial Planning Approach

Umtshezi spatial system comprises of the following main components:

Development nodes with varying levels of impact and spheres of influence.

Development corridors whose role is mainly defined in terms of the associated economic development sectors, land use pattern and role in the sub-regional economy.

Settlements located in different environments including urban, peri-urban and rural areas.

Agricultural land

Environmentally sensitive areas.

Each of these plays an important role in the functioning of the spatial system.

  - Spatial Planning Strategies

The application of the service centre (nodes and corridor) approach in the context of Umtshezi follows logic of spatial planning strategies as indicators of a desired future spatial situation, and broad policy positions to guide decision making. The follwing has been adopted as overarching spatial planning strategies:

Enhancing the Quality of the Environment

Protection of High Value Agricultural Land

Supporting an Efficient Movement System

Development Corridors as Investment Routes

Focusing Development in Strategic Nodal Points

Integration between Different Landscapes/Land Use Zones

Developing Sustainable Human Settlements

Establishing Framework for Growth and Development

- Spatial Development Framework

Umtshezi Spatial Development Framwork is presented in the form of a series of overlays dealing with a range of spatial development issues. Accompying the overlays, is a set of spatial planning directives which gives clear indication of type, nature and extent of development in different development zones.

  - Environmental Management

The areas considered suitable for development fall outside the environmentally sensitive areas, high potential agricultural land and the archaeologically sensitive areas. However, there may be other issues that may hamper planning and development in these areas, hence these are given as guides only and more detailed investigation will be needed at the planning/development stage. Environmental management overlay identifies the following:

Areas where there are endemic species and where land uses other than conservation should not be allowed. This occurs mainly to the south Wagendrift Dam and is already earmarked for a game reserve and the associated facilities.

Management of water resources in terms of which rivers are identified as green corridors and areas suitable for environmental management, irrigated crop production in selected areas and public open space system.

Guidelines for veld management.

Municipal open space system.

  - Preservation of High Potential Agricultural Land

As a general aim, the municipality together with the Department of Agriculture has a responsibility to protect agricultural land from development that leads to its alienation from its primary purpose or to diminished productivity. Any proposal for non-agricultural development on agricultural land is subject to an application made to, and assessed by, the Department of Agriculture in terms of the Sub-division of Agricultural Land Act, (Act No. 70 of 1970).  On the other hand, the municipality has a responsibility to implement wall-to-wall land use management system within its area of jurisdiction. This includes setting land aside for agricultural development purposes.

Agricultural land in Umtshezi Municipality could broadly be divided into three main categories as follows:

Good agricultural land in located along the southern and western boundaries of the municipal area.  Patches of similar land are found along Umtshezi River and around Weenen.

Moderate potential agricultural land is located generally in the area stretching from Estcourt in the south to Weenen in the north.

Land with low agricultural potential is located in the low-lying areas towards Indaka and Msinga Municipalities and falls largely within the Bloukrans River catchment area.

Agricultural potential should be used to establish agricultural zones in terms of the land use scheme, and provide for a continuum of agricultural zones from predominantly agriculture only zones to zones that allows for a mixture of agricultural and non-agricultural uses.

  - Development Corridors

Development corridors are a potential instrument to restructure the municipal area into robust, efficient and well-connected spatial system as well as contributing to region-wide (Uthukela District) economic growth and job creation.

The SDF identifies the N3 as a national and provicnial corridor, and a development opportunity area for the municipality.

Primary development corridors are as follows:

Giant Castle to Weenen Nature Reserve Corridor (north–south axis);

Regional road from Colenso in the west through Weenen to Greytown and beyond (east-west axis); and

R103, which runs parallel to, and north of the N3. For the purposes of the SDF, R103 is seen as part of the broader N3 corridor.

Secondary Development Corridors are as follows:

Road from Winterton to Colenso running along the western boundary of Umtshezi Municipality. This corridor links Winterton with Colenso and beyond.

P170-D385 corridor from Wagendrift dam through Estcourt town to Weenen running along the eastern boundary of the municipal area.

The road from Winterton to Colenso serves as a major link at a district level knitting together small towns from Bergville through Winterton to Ladysmith, Weenen and beyond. It runs mainly along agricultural land.

P170-D385 corridor is a proposed corridor linking the eco-tourism and leisure node of Wagendrift Dam through Estcourt town with the proposed Big Five Game Reserve but running along the eastern boundary of the municipal area.

Tertiary corridors are as follows:

D489 – D721 (Cornfields-Thembalihle Corridor).

P179 from Loskop road through Wembezi to Wagendrift Dam and the surrounding proposed conservation areas.

Cornfields-Thembalihle Corridor serves as a major link between the two parallel secondary corridors and has potential to improve access to Thembalihle and Cornfields

P179 from Loskop road through Wembezi to Wagendrift Dam and the surrounding proposed conservation areas is also an emerging corridor intended to reinforce linkages and integrate Wembezi and the surrounding settlements to the agricultural and the proposed eco-tourism areas approximately the Wagendrift Dam.

In addition, it identifies the road linking Estcourt and Wembezi as a low impact mixed land use corridor This will ensure protection of the existing agricultural land while also opening opportunities for tourism, leisure, housing and commercial development. The proposed N3 off-ramp gives further impetus to the development of a mixed land use node which accords well with the proposed corridor.

  - Development Nodes

Activity nodes have the potential to be an important sub-regional structuring device. They serve as points in the spatial structure where potentially access to a range of opportunities is greatest, where networks of association create diversity and where people are able to satisfy the broadest range of their day to day needs. Being points of maximum economic, social and infrastructure investment, as well as representing established patterns of settlement and accessibility, these nodes must be regarded as primary devices on which to anchor the structure of the sub-regional spatial system.

Estcourt in the primary node and should be prioritised for sub-regional commercial and social facilities. It should be developed as an industrial hub and is well positioned to tap on the opportunities the N3 presents.

Two secondary activity nodes have been identifieds in Umtshezi Municipality, namely:

Weenen, which is a small rural town that has experienced economic decline and deterioration of infrastructure. The implementation of the land reform program in the area and well-developed irrigable land around the town presents an opportunity for the town to be redeveloped as an agri-processing centre.

Wembezi, which is essentially a township, should be transformed into a mixed land use area through the creation of opportunities for economic development, provision of public facilities and upgrading of infrastructure.

In addition, the following should be developed as community centres or tertiary nodes within a cluster of settlements, as follows:

Thembalihle and Cornfields

Frere

Chiverly

Rensbergdrift

Nhlawe

None of these is currently developed. They are proposed nodes.

  - Land Reform Framework

Umtshezi Municipality recognizes the importance of the land reform; particularly the role it can play in addressing historical land related conflicts in the area, overcrowding and congestion, as well as promoting agricultural development. As such, the following should guide future implementation of the land reform program within Umtshezi Municipalit:

Clustering of projects in a geographic area (across products) so as to optimise development potential, rationalise support services and promote efficient use of scarce resources.

Settlement of the emerging farmers in terms of the Land Redistribution for Agricultural Development (LRAD) or Pro-active land Acquisition Strategy should be located close to transport axes on good agricultural land

There is a need to promote off-farm settlement as a land delivery approach where the main need for land is settlement.

Identification of high impact projects and integration into the local value chain or development proposals.

  - Housing Delivery Framework

Umtshezi Municipality has developed a Housing Sector Plan as a guide to the execution of its housing mandate. As such, housing is not construed as an end in itself, but a strategic intervention for addressing an assortment of development objectives.

Although Estcourt, Wembezi and Weenen account for about 50% of the municipal population, the housing sector plan concludes that the highest housing need is found in the rural settlements. The majority of housing in these settlements occurs in the form of traditional huts. Moreover, they have not benefitted from any housing scheme, yet they account for about 35% of the municipal population. A a result, the following areas have been prioritised for housing development:

Thembalihle

Cornfields

Frere

Chiverly

Rensbergdrift

Nhlawe

Rama

Papkulisfontein

Bambanani Machunu

Msobotsheni, Engodini and Nhlawe

Owl and Elephant

  - Spatial Economic Development Framework

The Provincial Spatial Economic Development Strategy primarily identifies Estcourt as being:

On the exiting N3 corridor;

Being a service node; and

Being part of a tourism corridor.

In addition the area has potential to develop economically as follows:

Estcourt town for major commercial and industrial development. Particular focus should be paid on the processing of raw material produces in and around Umtshezi Municipality area.

Eco-tourism, leisure and game farming should be promoted around Wagendrift Dam and the area to the south the N3.

A range of agricultural practices on land identified as high potential agricultural land.

Big Five Game Reserve in the area between Weenen and Estcourt, and towards Mpofana Municipality.

Small game farms and related tourism facilities along the corridor linking Weenen and Colenso to the west and Greytown to the east.

Irrigated crop production along the major rivers and around Weenen town.

Urban regeneration in Wembezi and Weenen town.

  - Urban Development and Management Framework

Urban development program focuses mainly in the three urban nodes within Umtshezi Municipality, namely:

Wembezi where the main focus on the initiation and implementation of an urban renewal program.

Weenen where the main focus also on urban renewal and intensive urban agriculture.

Estcourt where the focus is on land use integration and developing the town into an efficient sub-regional centre. There functional linkages with the N3, proposed tourism developments and agricultural production.

- Corridor Development Study and Small Town Rehabilitation

  - Weenen as part of Small Towns Rehabilitation Programme

The Department of Co-operative Government and Traditional Affairs identified 25 nodes make up the small towns in the province. The parent municipalities in these nodes are the poorest with limited rates base-grant dependent. Weenen was subsequently identified as one of the small towns that needs support from the programme. The KZN government has made an MTEF allocation of R244m towards the small town rehabilitation progrogramme. The programme is aimed at making the small towns more attractive for investment as part of Rural Development in line with priorities of government.

The programme has “ONE” aim and that is; to ensure that the competitiveness of these small towns is enhanced in order to attract investment and to retain the current investors. Support to the municipalities will be provided through grant funding for initiatives that will enhance these rural towns and create a clean and safe environment. The outcome will be the retention and attraction of investment thereby retaining and creating new work opportunities.

  - Estcourt as part of the Corridor Development Programme

The Department of Co-operative Government and Traditional Affairs (CoGTA) has a programme for funding Corridor Development Initiatives. CoGTA recalled that the Provincial Spatial Economic Development Strategy (PSEDS) identified three (3) primary corridors and fourteen (14) secondary corridors within the province of KwaZulu-Natal. R103 which provides a direct link to the town of Estcourt is identified as Secondary Corridor (SC). PSEDS states that a corridor serve areas of high poverty levels with good economic development potential within one or two sectors. This implies that Estcourt should be assisted and resourced by this programme in order for its economic potential to be realised.

ANNEXURE “B”

EMPLOYMENT EQUITY PLAN

- UMTSHEZI MUNICIPALITY

- EMPLOYMENT EQUITY

- PLAN

FIRST DRAFT

AUGUST 2013

- INTRODUCTION:

| EMPLOYER | UMTSHEZI MUNICIPALITY |
| --- | --- |
| REGISTRATION NUMBER | KZN234 |
| SARS REGISTRATION NUMBER | 4470101991 |
| UFF NUMBER | 4390709295 |
| INDUSTRY SECTOR: | LOCAL GOVERNMENT |
| CONTACT PERSON | HB CHOTOO |
| ADRESS | P.O. BOX 15 ESTCOURT 3310 |
| TOWN / CITY | ESTCOURT |
| POSTAL CODE | 3310 |
| TELEPHONE NUMBER | 036 342 7800 |
| FAX NUMBER | 036 352 5829 |
| E-MAIL ADRESS | chotoo@mtshezi.co.za |
| SKILLS DEVELOPMENT NUMBER | L390709295 |

Is UMTSHEZI Municipality

- Organ of state

| YES | NO |
| --- | --- |
| x |  |

- Are you voluntarily complying with this Act as specified in section 14?

| YES | NO |
| --- | --- |
| x |  |

The uMtshezi Local Municipality embarked on drafting the Employment Equity Plan, which reflects the primary areas of the course of action to follow. This Plan is for all intent and purposes binding and should balance considerations of strategic business and with a justifiable equity rationale. The intention is that the policy be tabled at the Employment Equity Committee, since it is an integral part of the committee’s objective to gain acceptance of the policy throughout the Municipality at all levels. This is compliance to the Employment Equity Act of 1998.

The Municipality have constructively taken cognizance of the results of an in-depth strategic analysis and preliminary information gathering process, as well as the need identified during the process.

This Employment Equity Plan presents proposals that will ensure that the workforce of the UMtshezi Local Municipality will be more reflective of the demographics of the Municipality with five (5) years. After five (5) years, the progress of the plan shall be reviewed.

In designing this Plan, great care has been taken to consult all stakeholders and to reach consensus with them, to ensure that this plan enjoys wide support throughout the Municipality.

The targets set in these terms of employment levels are more primarily aimed at top management and middle management, operative and supportive transformation. Other elements cover wide field and will, by their nature, affect all employees within the UMtshezi Local Municipality.

- OBJECTIVES OF THE EMPLOYMENT EQUIT PLAN

In developing the employment Equity Plan, the Municipality had due regard for the overriding purpose of the Employment Equity Act, namely to:

- Promote the Constitutional right to equality

- Give effect to all labour legislations, in particular the Employment Equity Act and Skills Development Act;

- Give Effect to the mission, transformation, vision and strategic plan of the UMtshezi Local Municipality;

- Give effect to the policy on the promotion of equality, diversity and the elimination of unfair discrimination.

- Promote employees participation through the involvement of employees and their trade union representatives, as well as other stakeholders in the development and monitoring of employment equity.

- Ensure the implementation of affirmative action measures to redress the effects of discrimination;

- Achieve a diverse workforce broadly representative of the demographics of the uMtshezi Local Municipality – especially at tom management and middle management level and operative level.

- Promote economic development and efficiency in the workforce of the uMtshezi Local Municipality.

Any Employment Equity Plan cannot take effect in a vacuum. It is therefore important that uMtshezi Local Municipality consider its strategic direction in tackling a plan of this nature to achieve a long-term plan of the Plan. The integrated Development Plan has to a limited degree indicate a direction Employment Equity Plan has to take. Critical to all Municipalities, will be a content and development context of the IDP. Inherent in the IDP is its ability to have visible impact on local economic development and tax – based generation. It also the aim of the Municipality to be self – funded, instill a participating culture in its communities and successfully participate in the current global environment, which compels it to provide visionary leadership., political stability, social security and futuristic plans and programmes – the Equity Plan being one of them.

Though much have been done to try and address representation as per Regional Demographics, it is still the Municipality’s primary goal to transform the representation in all Management levels, its developmental role being paramount. At present, while going through this process, the Municipality very mindful of and dependence of local economic climate.

Responsibility for implementing the Employment Equity Plan

The responsibility for implementing Employment Equity Plan rests with the Employment Equity Committee, the management and Corporative Directorate. All these people will be responsible for the successful implementation of The Employment Equity Plan for the next five (5) years.

- DEFINITIONS AND INTERPRETATIONS

For the purpose of this Plan, the following terms are defined as:

  - AFFIRMATIVE ACTION MEASURES

    - Affirmative measures refers to the measures and additional corrective steps taken to ensure that those who were historically disadvantaged by unfair discrimination are able to derive full benefits from the equitable employment environment.

    - A short and long –term strategy and process to address the imbalances in the employment profile in terms of race, gender and disability.

    - Education, training and development that actively equip designated employees with skills to enter any level of employment.

    - Human resources Policies and practices that actively direct designated employees towards upwards mobility (through accelerated development and mentorship programmes), unrestricted by any considerations other than the inherent requirements of the job.

    - Practices that ensure equal opportunity and treatment in recruitment and selection process of those seeking employment, and acting and promotion opportunities, and for those already in employment, in selection, planning, performance appraisal, promotion and all other staff development policies and practices that enhance staff career opportunities.

    - Practices and procedures that eliminate patronage, nepotism, favoritism, unfair discriminations and sexual or racial harassment.

    - Diversity management programmes to re-orientate all employees affected by this Policy to prevent unacceptable discriminatory attitudes and actions based on race, gender, sexual orientation, disability or any other stereotype.

  - DISCRIMINATION:

    - Discrimination shall mean any form of treatment, restriction of opportunity or differentiation based on race, gender, disability, ethnic, or religious conviction or other stereotypes.

    - Indirect discrimination shall mean any practice or procedure that adversely exclude or impact on more persons of one racial, religious or social group or gender than another.

    - Unfair discrimination shall mean any distinction, exclusion or preference made on basis of race, gender, social or personal treatment that directly or indirectly prejudices, or make separate provision or provides les favorable treatment for any employee or potential employee. Unfairness in this context shall mean:

      - Any discrimination that is not founded on the basic requirement

of the job

      - Practices that may nullify or impair the equity, opportunity or

treatment in employment, promotion or advancement in the

workplace.

  - FAIR DISCRIMINATION

Section 6(2) of the EE Act qualifies action that is not unfair:

- Discrimination for affirmative action purposes

- Discrimination based on the inherent requirement of the job.

    - The above divinations include those practices and procedures designated as affirmative action.

3.3.1.1 Designated group refers to blacks, females and people living with disabilities.

      - Black is a generic term refers to African, Colored and Indian people.

      - A person with a disability is any individual who’s prospect of securing, retaining and advancing in suitable employment are substantially reduced as a result of physical, sensory or mental impairment of a permanent nature.

  - DISADVANTAGED

    - Disadvantaged groups or historically disadvantaged group refers to those groups identified as having been unfairly discriminated against, through past legislations, polices, prejudice and stereotype; or

    - People who have been adversely affected economically, politically, socially or by non-utilization of ability on the grounds of race, religion, gender, national origin or physical disability and or have been physically discriminated against by any form of distinction, preference or exclusion or personal treatment that directly or indirectly restricted development, and / or provided less favorable treatment on the grounds of race, gender or physical disability.

    - Employment equity refers to the elimination of unfair discrimination, as well as implementation of specific measures to accelerate the advancement of designated groups towards the achievement of equality.

    - Equal employment opportunity refer to the formal right of all to be treated equally on employment, irrespective of race , gender and disability

  - SUITABLE QUAIFIED PERSONNEL

    - Those persons who may be suitably qualified for a job as a result of any one of or combination of the following:

3.3.5.1	 Formal qualifications;

3.3.5.2.	Prior Learning

3.3.5.3.	Relevant Experience

3.3.5.4.	Capacity to acquire, within reasonable time, the ability to do the job.

- COMPLIANCE WITH PROHIBITION OF UNFAIR DISCRIMINATION

As required in terms of Chapter 2 of the EEA, the Municipality finalized an exercise to ensure unfair discrimination does not exist in the workplace. The following table indicates the actions that were taken

| Form of Prohibition | Actions taken |
| --- | --- |
| No discrimination in any relevant policy or practice | All relevant policies were implemented, submitted for approval or in development as stated in Paragraph 13 below, including sexual harassment / bullying |
| Medical testing | Medical testing only utilised if required or permitted by legislation or if it is justified in the light of medical facts with regard to the inherent requirements of the job |
| HIV status | No HIV testing takes place |
| Psychological testing | The integrity of assessment techniques and processes is sound, i.e. not biased and only intended to measure what is needed, however, it is not carried out but in the pipeline. |
| Employee Survey | In addition to the compliance requirements to address unfair discrimination in a meaningful way, The uMtshezi Municipality also conducted an employee survey to assist in identifying any specific barriers to eliminate unfair discrimination and to progress towards representatively of the designated groups. |

- UMTSHEZI MUNICIPALITY – POLICIES AND PRACTICES

As required in terms of section 19(1) of the EEA, the Municipality completed an analysis of all relevant employment policies and practices to identify any barriers to employment equity. The barriers identified and the remedial actions taken or in process are included in the table under paragraph 4.1

The status of the Human Resources policies is as indicated in the schedule below:

| No. | Policies | Status | Comments |
| --- | --- | --- | --- |
| 1 | Employment Equity Policy | Approved |  |
| 2 | Recruitment and Selection Policy | Approved |  |
| 3 | Collective Agreement Conditions of Service | Approved (SALGABC) |  |
| 4 | Collective Agreement Disciplinary Grievance Procedure | Approved (SALGABC) |  |
| 5 | Municipal Code Of Conduct | Draft | To be presented to relevant committees for Council’s recommendation |
| 6 | Uniform / Protective Clothing | To be developed | Being researched and to be developed before the end of current financial year 2013-14 |
| 7 | Training And Development | Approved |  |
| 8 | Employee Wellness Policy | Approved |  |
| 9 | HIV/ Aids Policy | Approved |  |
| 10 | Succession Planning | To be developed | Being researched and to be developed before the end of current financial year 2013-14 |
| 11 | PMS Implementation | Approved |  |
| 12 | Rewards and Incentives |  | Being researched and to be developed before the end of current financial year 2013-14 |
| 13 | Induction / Orientation and Retention of New Staff | Approved |  |
| 14 | Retirement Planning | To be developed | Being researched and to be developed before the end of current financial year 2013-14 |
| 15 | Sexual Harassment | Approved |  |
| 16 | Promotions And Remuneration | Approved |  |
| 17 | Affirmative Action | Approved |  |
| 19 | Employment Policy | Approved |  |
| 20 | Recruitment, Selection and Placement | Approved |  |

- AFFIRMATIVE ACTION MEASURES

6.1.	 Compliance Measures

An assessment of the Umtshezi Municipality workforce, employment policies and practices, enabled management to identify specific affirmative action measures to be implemented on an ongoing basis to ensure any possible barriers are addressed and the aims and principles of employment equity archived.

6.2.	Specific Initiatives

In addition to the legislative requirements for compliance, the Umtshezi Municipality also implemented an initiative to specifically indicate in positions advertisements, the preferable candidate for addressing representation.

6.3. 	Enhancement of Practical Experience

The Municipality has embarked on an initiative to provide for funding in the form of stipends for graduates who gains practical exposure through Umtshezi Municipal facilities.

6.4.	Local Labour Promotions Projects (LLPP)

The LLPP is devised as a means of effecting socio-economic upliftment to bring about poverty alleviation through job creation.

The LLPP provide opportunities to people from the local communities where unemployment and poverty is rive, to be part of municipal service delivery and construction of new facilities.

Those in construction are provided with necessary training to acquire required skills that will sustain them in a long rung even after projects have been concluded.

In return, participants are paid monthly stipends.

- THE DEMOGRAPHIC FRAMEWORK

During the planning stages, a number of demographic characteristics emerged that were considered in drafting reasonable targets for this Plan.

  - TOTAL GROWTH RATES FOR UTHUKELA DISTRICT

| DISTRICT | TOTAL POPULATION | POPULATION GROUTH RATE |
| --- | --- | --- |
| UTHUKELA | 668 848 | 0.2 |

  - TOTAL GOUTH RATES FOR UMTSHEZI MUNICIPALITY

| DISTRICT | TOTAL POPULATION | POPULATION GROUTH RATE |
| --- | --- | --- |
| UMTSHEZI | 83 153 | 3.2 |

  - KEY DEMOGRAPHICS FOR UTHUKELA DISTRICT.

    - The total population for Uthukela District geographical area is as follows:

| POPULATION GROUP | MALES | FEMALES | TOTAL POPULATION | PERCENTAGE OF TOTAL POPULATION |
| --- | --- | --- | --- | --- |
| AFRICAN | 295 021 | 341 374 | 636 394 | 95.4 |
| WHITES | 5 608 | 5 829 | 11 437 | 1.6 |
| INDIAN / ASSIANS | 8 042 | 7 981 | 16 023 | 2.4 |
| COLOUREDS | 1 876 | 2 046 | 3 923 | 0.6 |
| TOTALS | 310 547 | 357 230 | 667 777 | 100 |

    - Distribution of population aged between 15 and 64 years by employment status per municipality -1996, 2001 and 2011 (STATS SA)

|  | EMPLOYED |  |  | UNEMPLOYED |  |  | UNEMPLOYMENT RATE |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| MUNICIPALITY | 1996 | 2001 | 2011 | 1996 | 2001 | 2011 | 1996 | 2001 | 2011 |
| UThukela District Municipality | 69 019 | 75 515 | 88 527 | 65 171 | 107 794 | 58 281 | 48.6 | 58.8 | 39.6 |
| UMtshezi Municipality | 9 090 | 9 988 | 13 264 | 5 826 | 12 720 | 10 376 | 61.8 | 58.9 | 43.4 |

Distribution of employment rate per race - uMtshezi Municipality (STATS SA)

| POPULATION | African | % | White | % | Asian | % | Colored | % | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Employed Economically Active | 10 353 | 78.14 | 928 | 7% | 1 677 | 12.66% | 291 | 2.2% | 13 249 |
| Unemployed / Not Economically Active | 7 411 | 95.26 | 33 | 0.43% | 271 | 3.48% | 65 | 0.84% | 7 780 |
| TOTAL | 17 764 |  | 961 |  | 1 948 |  | 365 |  | 21 038 |

DISTRIBUTION OF EMPLOYMENT RATE PER RACE AND GENDA- UMTSHEZI MUNICIPALITY AS AN INSTITUTION

| Employment Level | Gender | African | % | White | % | Asian | % | Coloureds | % |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Top Management | Males | 2 | 0.54% | 0 | 0 | 1 | 0.27% | 0 | 0 |
|  | Females | 1 | 0.27% | 0 | 0 | 0 | 0 | 1 | 0.27% |
| Middle Management | Males | 4 | 1.1% | 0 | 0 | 1 | 0.27% | 1 | 0.27% |
|  | Females | 1 | 14.28% | 0 | 0 | 0 | 0 | 0 | 0 |
| Professionals | Males | 5 | 1.4% | 1 | 0.27% | 0 | 0 | 0 | 0 |
|  | Females | 4 | 1.1% | 0 | 0 | 2 | 0.54% | 0 | 0 |
| Technicians & Trade workers | Males | 5 | 1.4% | 1 | 0.27% | 5 | 1.4% | 1 | 0.27% |
|  | Females | 1 | 0.27% | 0 | 0 | 0 | 0 | 0 | 0 |
| Community & Personal Workers | Males | 11 | 3.02% | 2 | 0.55% | 0 | 0 | 1 | 0.27% |
|  | Females | 6 | 28.57% | 1 | 4.76% | 1 | 4.76% | 0 | 0 |
| Clerical & Admin Workers | Males | 21 | 5.8% | 4 | 1.1% | 14 | 3.84% | 6 | 1.65% |
|  | Females | 16 | 4.4% | 0 | 0 | 3 | 0.82% | 2 | 0.55% |
| Machine Operators & Drivers | Males | 31 | 8.52% | 0 | 0 | 0 | 0 | 0 | 0 |
|  | Females | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Elementary Workers | Males | 52 | 14.3% | 0 | 0 | 0 | 0 | 1 | 0.27% |
|  | Females | 127 | 34.9% | 0 | 0 | 1 | 0.27 | 3 | 0.82% |
| Physically Challenged | Males | 1 | 0.27 | 1 | 0.27 | 0 | 0 | 0 | 0 |
|  | Females | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |

The analysis indicates that the Municipality, as an employer, is unrepresentative of this demographic profile Stakeholders also agree that steps should be taken to ensure that the municipality abides by the Employment Equity Act in this regard.

  - TOP MANAGEMENT PROFILE

In Estcourt component of the UMtshezi Municipality, top management is deem to be those posts on section 57.

TOP MANAGEMENT STAFF PROFILE

| Population Group | POP 2001 | % OF POP | POP 2011 | % OF POP | Number Employed | % Employed | Variance | Target Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| White | 2803 | 4.66% | 1907 | 2.13% | 0 | 0 | -2.13 | 2.13 |
| African | 50391 | 83.86% | 75024 | 83.89 | 4 | 80 | +3.89 | 80 |
| Indian / Asian | 5365 | 8.93% | 4836 | 5.41 | 1 | 20 | +14.59 | 5.41 |
| Coloured | 1528 | 2.54% | 1135 | 1.27 | 0 | 0 | -1.27 | 1.27 |
| Males | 28558 | 47.53% | 45011 | 50.33 | 4 | 80 | +30.33 | 50.33 |
| Females | 31530 | 52.47% | 44425 | 49.67 | 1 | 20 | -29.67 | 49.67 |
| Totals | 60088 |  | 89436 |  | 5 |  |  |  |

TNR		 = TARGET NOT REACHED

AT		 = ABOVE TARGET IF VIRIANCE IS BELOW 30%

WT		 = WITHIN TARGET	 IF VARIANCE IS LESS THAN 30%

  - MIDDLE MANAGEMENT PROFILE

| POPULATION GROUP | POP 2001 | % OF POP | POP 2011 | % OF POP | NUMBER EMPOYED | % EMPLOYED | VARIANCE | TARGET STATUS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| White | 2803 | 4.66% | 1907 | 2.13% | 1 | 4% | +1.87 | 2.13 |
| African | 50391 | 83.86% | 75024 | 83.89 | 15 | 60 | -23.89 | 83.89 |
| Indian / Assian | 5365 | 8.93% | 4836 | 5.41 | 3 | 12 | +6.59 | 5.41 |
| Coloured | 1528 | 2.54% | 1135 | 1.27 | 2 | 8 | +6.73 | 1.27 |
| Males | 28558 | 47.53% | 45011 | 50.33 | 17 | 68% | +17.67 | 50.33 |
| Females | 31530 | 52.47% | 44425 | 49.67 | 8 | 32% | -17.67 | 49.67 |
| Totals | 60088 |  | 89436 |  | 25 |  |  |  |

TNR		 = TARGET NOT REACHED

AT		 = ABOVE TARGET IF VIRIANCE IS BELOW 30%

WT		 = WITHIN TARGET	 IF VARIANCE IS LESS THAN 30%

WHITES: ARE WITHIN TARGET

AFRICANS: WIITHIN TARGET

INDIANS: ARE ABOVE TARGET

COLOURED:

    - SUPPORT STAFF PROFILE

The profile and support staff, which are on Task Grades 1 to 11, is as follows:

SUPPORT STAFF PROFILE

| POPULATION GROUP | POP 2001 | % OF POP | POP 2011 | % OF POP | NUMBER EMPOYED | % EMPLOYED | VARIANCE | TARGET STATUS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| White | 2803 | 4.66% | 1907 | 2.13% | 7 | 1.98% | -0.15 |  |
| African | 50391 | 83.86% | 75024 | 83.89 | 275 | 78.13% | -5.67 |  |
| Indian / Asian | 5365 | 8.93% | 4836 | 5.41 | 27 | 7.67% | +2.26 |  |
| Coloured | 1528 | 2.54% | 1135 | 1.27 | 14 | 3.98% | +2.71 |  |
| Males | 28558 | 47.53% | 45011 | 50.33 | 231 | 65.63% | +15.33 |  |
| Females | 31530 | 52.47% | 44425 | 49.67 | 121 | 34.37% | -15.23 |  |
| Totals | 60088 |  | 89436 |  | 352 |  |  |  |

TNR		 = TARGET NOT REACHED

AT		 = ABOVE TARGET IF VIRIANCE IS BELOW 30%

WT		 = WITHIN TARGET	 IF VARIANCE IS LESS THAN 30%

4.4.2 TOTAL NUMBER OF EMPLOYEES AT EACH OCCUPATIONAL LEVEL

| Occupational Category | Females |  |  |  | Males |  |  |  | Total |  |  |  | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | A | C | I | W | A | C | I | W | A | C | I | W |  |
| Managers | 3 | 2 | 0 | 0 | 8 | 0 | 2 | 1 | 11 | 2 | 2 | 1 | 16 |
| Professionals | 4 | 0 | 2 | 0 | 5 | 0 | 0 | 1 | 9 | 0 | 2 | 1 | 12 |
| Technicians and Trade Workers | 1 | 0 | 0 | 0 | 5 | 1 | 5 | 1 | 6 | 1 | 5 | 1 | 13 |
| Community & Personal Services Workers | 6 | 0 | 1 | 1 | 11 | 1 | 0 | 2 | 17 | 1 | 1 | 3 | 22 |
| Clerical & Administrative Workers | 21 | 6 | 14 | 4 | 16 | 2 | 3 | 0 | 37 | 8 | 17 | 4 | 66 |
| Sales Workers | 3 | 0 | 0 | 0 | 2 | 0 | 3 | 0 | 5 | 0 | 3 | 0 | 8 |
| Machine Operators & Drivers | 0 | 0 | 0 | 0 | 31 | 0 | 0 | 0 | 31 | 0 | 0 | 0 | 31 |
| Elementary Workers | 52 | 1 | 0 | 0 | 127 | 3 | 1 | 0 | 179 | 4 | 1 | 0 | 184 |
| TOTALS | 91 | 10 | 17 | 5 | 216 | 7 | 16 | 7 | 307 | 17 | 33 | 12 | 369 |

The above also needs attention, although Africans are in the majority, most of them are unskilled.

- ANNUAL OBJECTIVES

In the introduction, it was mentioned that the municipality’s intension was to concentrate on numerical targets insofar as these relates to Middle Management and skilled support staff. These remains the focus, owing to the considerable underrepresentation of people from the designated groups, as identified in the analysis conducted earlier.

The adjustment of the employment profile in the Umtshezi Local Municipality to the demographics profile of the municipality is admittedly a complex matter, as it involves issues of gender, especially at top ten post levels Section 57 and task grade 11 to 17. The Employment Equity Plan covers a five - year period and the transformation of specifically the Top and Middle Management structures have started bearing fruits.

The municipality has paid more focus to employees who are 50 years of age and above and doing everything in its power to address the imbalances in workplace. Vacant positions as per approved organogram are earmarked for previously disadvantaged groups. It is also part of our recruitment process, that positions adverts indicates that preference will be given to previously disadvantaged groups. This is the Council strategic move in ensuring that races in the employment of the Umtshezi Municipality is a true reflection of UThukela regional demographics.

In considering the above, Umtshezi Local Municipality have designed the following matrix, which illustrate the number and nature of appointments necessary during the period September 2013 to September 2018,

The following represents a 5-year transformation programme for all levels of employment of the Council.

5.1 TOP MANAGEMENT (SECTION 56 AND 57)

Key

Mean current staff

|  | AF | AM | CF | CM | IF | IM | WF | WM | DISAB |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2013-14 | X1 , (1) | X3, (3) | X0, (0) | X0, (0) | X0, (0) | X1, (1) | X0, (0) | X0, (0) | X0, (0) |
| 2014-15 | X1 , (1) | X3, (3) | X0, (0) | X0, (0) | X0, (0) | X1, (1) | X0, (0) | X0, (0) | X0, (0) |
| 2015-16 | X1 , (1) | X3, (3) | X0, (0) | X0, (0) | X0, (0) | X1, (1) | X0, (0) | X0, (0) | X0, (0) |
| 2016-17 | X1 , (1) | X3, (3) | X0, (0) | X0, (0) | X0, (0) | X1, (1) | X0, (0) | X0, (0) | X0, (0) |
| 2017-18 | X1 , (1) | X3, (3) | X0, (0) | X0, (0) | X0, (0) | X1, (1) | X0, (0) | X0, (0) | X0, (0) |
|  | X1 | X3 | X0 | X0 | X0 | X1 | X0 | X0 | X0 |

EMPLOYEES REPRESENTATION IN TOP MANAGEMENT LEVEL FOR UMTSHEZI MUNICIPALITY IN PERCENTAGE

|  | 2013 | 2014 | 2015 | 2016 | 2017 |
| --- | --- | --- | --- | --- | --- |
| WHITES | 0% | 0% | 0% | 0% | 0% |
| AFRICAN | 60% | 60% | 60% | 60% | 60% |
| COLOUREDS | 20% | 20% | 20% | 20% | 20% |
| INDIANS | 20% | 20% | 20% | 20% | 20% |
| FEMALES | 40% | 40% | 40% | 40% | 60% |
| MALES | 60% | 60% | 60% | 60% | 40% |
| DISABLED | 0 | 0 | 0 | 0 | 0 |

Over the next five (5) years from 2013 to 2017, it is proposed to target Coloured Female, Coloured Male or Indian Female representation at Top Management level of the uMtshezi Local Municipality.

This can only be realized if there is vacant position in this level due to resignation between 2013 and 2016. It is recommended to council that it consider addressing representation in employment level as per regional demographics by 2016-17 when most of the contracts expires at this level (Top Management).

The following is the transformation transition for Middle Management employees over the next five (5) years

5.2. MIDDLE MANAGEMENT

|  | AF | AM | CF | CM | IF | IM | WF | WM | DISAB |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2013-14 | 7 | 18 | 0 | 1 | 3 | 4 | 0 | 1 | 0 |
| 2014-15 | 12 | 19 | 1 | 1 | 4 | 4 | 1 | 1 | 0 |
| 2015-16 | 17 | 21 | 1 | 1 | 4 | 4 | 1 | 1 | 1 |
| 2016-17 | 22 | 22 | 1 | 1 | 4 | 4 | 1 | 1 | 1 |
| 2017-18 | 23 | 23 | 1 | 1 | 4 | 4 | 1 | 1 | 1 |

|  | 2013 | 2014 | 2015 | 2016 | 2017 |
| --- | --- | --- | --- | --- | --- |
| WHITES | 2.94% | 4.76% | 4.16% | 3.57% | 3.50% |
| AFRICAN | 73.52% | 73.81% | 79.17% | 78.57% | 78.74 |
| COLOUREDS | 2.94% | 4.76% | 4.16% | 3.57% | 3.50 |
| INDIANS | 20.58% | 19.05% | 16.66% | 14.29% | 14.04% |
| FEMALES | 29.41% | 42.86% | 47.91% | 50% | 50.87% |
| MALES | 70.59% | 57.14% | 52.09% | 50% | 49.13%` |
| DISABLED | 0 | 0 | 2.08% | 1.78% | 1.75% |

- COMMUNICATION, AWARENESS AND CONSULTATION

6.1. INTRODUCTION

6.1.1. Employment Equity Act, No55 of 1998 section 16 requires that all designated employers must take reasonable steps to consult with organized labour and or employees in absence of unions.

6.1.2. Section 17 of Employment Equity Act, No 55 of 1998 prescribe the matters for consultations as follows:

      - The conduct of analysis, as prescribed, of its employment policies, practices,

procedures and working environment, in order to identify employment

barriers, which adversely affect people from designated groups

      - The preparations and implementation of the employment equity plan referred

to in section 20 of the EE Act No. 55 of 1998, i.e.

- Objectives to be achieved for each year of the plan; the affirmative action measures to be implemented as required by section 15(2),

- Where underrepresentation of people from designated groups has been identified by the analysis,

- The numerical goals to achieve the equitable representation of suitable qualified people from the designated groups within each occupational category and level in the workplace, the timetables within which this is to be achieved, and strategies intended to achieve those goals.

- The timetables for each year of plan for the achievement of goals and objectives other than numerical goals

- The duration of the plan, which may not be shorter than one year or longer than five (5) years

- The procedure that will be used to monitor and evaluate implementation of the plan and whether reasonable progress is being made towards implementing employment equity

- The internal procedure to resolve any dispute about the interpretation or implementation of the plan.

- The person in the workforce, including senior managers, responsible for monitoring and implementing the plan; and

- Any other prescribed matter.

      - And report Employment Equity submitted to the Director General

    - In fulfilment of these responsibilities, the Corporate Service Director:

- Held sensation seminars with all stakeholders to make them aware of Employment Equity and all anti- discriminatory issues;

- Placed at notice boards in each Department to post the most updated information on employment equity and make it available to all employees;

- Facilitate the appointment or delegate one of the Senior Managers to drive Employment Equity to further advance the process.

    - The Employment Equity Manager / Delegated Senior Manager – consistent with the requirement of the Employment Equity Act

    - Consult with all established stakeholders and organizational structures within the Umtshezi Municipality

- Gather inputs by employees

- Summary and conclude reports

    - The participants shall make two types of contributions – one, in the form of a confidential written communication in response to a specific question, the other in the form of oral interventions in which specific views were expressed about the work situation in general in the context of employment equity.

- BARRIERS TO EMPLOYMENT EQUITY

  - INTRODUCTION.

7.1.1 	The Employment Equity Plan requires the employer to identify any barriers

that may  contribute to the underrepresentation or underutilization of

employees from the designated groups

    - The act also requires that the employer identify any barriers or factors that may contribute to the lack of affirmation of diversity in the workplace.

    - The Act specifically requires the employer to review all policies, practices and procedures of the working environment in order to identify any barriers that may be responsible for underrepresentation or underutilization of employees from the designated groups. This work is set out in the Annexure attached to this Plan.

  - The schedule below is a reflection of barriers and inhibitors in achieving Employment Equity Plan

Umtshezi Municipality – Employment Equity Plan September 2013

| Policies & Practices | Situational Analysis and the way forward 2013 -2017 | Measures Taken / To be Taken |
| --- | --- | --- |
| Recruitment procedure and processes | - Lack of numerical goals - Opportunities for internal promotions not enhanced | - Numerical goals now determined for all levels and categories - Preference given to suitably qualified internal staff when recruiting |
| Selection, Screening and Short-listing | - Employment criteria must be appropriate to the requirements of the job. | - All candidates are assessed against specific job requirements as advertised and then short-listed in compliance with the EEA guidelines for suitable qualified candidates |
| Job design / specification | - Job design and person specification places emphasis on formal qualifications and lacks a proper definition of the competencies required | - Tasks still in progress ensured that each position has its own job description signed by the employee, supervisor and recognized unions. 132 tasks outcome have been finalized |
| Advertisements - Advertisements not reaching the required groups | Advertisements EE and gender linked and placed as widely as possible to ensure maximum access by the designated groups (within the financial means of the Municipality) | External advertisements for vacancies are placed in all local newspapers, placed on all municipal notice boards, in municipal libraries and distributed to all departments in the municipality. |
| Application form - Advertisements not reaching the required groups | Format of the application from now more simplified and based job related information | Status quo maintained. |
| Referencing checking and rating - Lack of proper references and rating disabled persons - No specific efforts to identified positions for disabled employees | - Lack of referencing not used to disqualify an applicant - Referencing relates to the inherent requirement of the job, rating against competencies and based on standardized methodology in which selection panel is trained / will be trained - Identify positions that could reasonably be expected to be occupied by disabled persons and actively attempt to recruit them for such positions - Introduce specialized equipment in these positions to promote the employment of disabled persons, e.g. switchboard. - Special attention to be given to career development of disabled employees | Primary focus is on suitable qualified candidates as per the EEA requirements As at the end of September 2013 there were 2 disabled personnel employed by the municipality 1x black male 1x white male |
| TRAINING ADD DEVELOPMENT |  |  |
| Induction and orientation - Inadequate guidance for new employees. | - Timeous and structured induction programmes, including all policies , for new employees is being provided - Guidance and counselling through initial problems, irrespective of whether these are work related, concerning hygiene or of social nature - Where possible the inclusion of a socialization component in the induction programme | - Induction sessions for all new employees on the 1St working day of the month - Will also introduce diversity awareness and employment equity as part of induction - Post induction support to new employees now tracked and recorded as per the IDP for Human Resources |
| ABET- remains at the core of training and not to be neglected | Effective implementation of ABET programmes – as far a possible also including the community. | - Structured methodology to promote ABET training has been introduced - Candidates can obtain GETC certificate equivalent to an NQF level 1. - Progress is reported to a Training Committee |
| Recognition of prior learning (RPL) – Lack of recognition of prior learning | Municipality’s Training and development Section setting up structures to assist employees to obtain better qualifications through RPL of their competencies | - Awareness of RPL amongst employees and line management. - Primary responsibility applies lies with employees and educational institution. - RPL forms an integral part of new TASK, and recruitment and selection processes in compliance with NQF standards |
| Focused training and development – inadequate to assist employees to identify educational and experience deficiencies | As part of the induction process linked to coaching, the line managers to develop training and development plans in consultation with person involved to monitor the transfer of appropriate skills to the new employees. | - Status quo maintained |
| Performance Related Training - Development plans to be linked to formal performance appraisal | The training and development plans to be linked to the performance appraisal system. This implies that line management will, in consultation with employees, formulate and address deficiencies in the work performance as well as enhance employees promote-ability through focused training | Performance management is currently linked to section 56 and 57 employees. Rolling out of programme to all staff being consulted with Trade Unions. Once consultation has been finalized, the programme will be rolled out to all staff. |
| Competency Based - Lack of competency based approach to training | Each department and section to re-evaluate posts to identify essential competencies required for effective job performance and to be used for career pathing purposes. | Tasks will provide |

ANNEXTURE

“C”

AG COMMENTS

ANNEXTURE “D”

ANNUAL PERFORMANCE REPORT